## Slide 1: CART Resource Needs Dashboard
7
Unit of measure
* Footnote
Source: Source
Working Draft - Last Modified 8/24/2007 2:36:55 PM
-50
Workstream
CCAR
IHC
ELS
Risk Transformation
Model Development
Operational Risk
Finance Transformation
Data & IT
Model Risk Management
Current | 30 Days (Aug) | 60 Days | 90 Days | Year End | Peak
11 | 14 | 19 | 24 | 28 | 28
6 | 27 | 35 | 32 | 23 | 28
17 | 41 | 54 | 56 | 51 | 56
1 | 7 | 10 | 10 | 10 | 10
0 | 3 | 3 | 3 | 3 | 3
0 | 10 | 13 | 13 | 13 | 13
Included in Finance Transformation |  |  |  |  | 
20 | 27 | 30 | 31 | 30 | 32
14 | 14 | 14 | 14 | 13 | 13
34 | 41 | 44 | 45 | 43 | 45
9 | 25 | 30 | 32 | 35 | 43
26 | 32 | 32 | 32 | 30 | 32
35 | 57 | 62 | 64 | 65 | 75
31.5 | 35 | 39 | 42 | 46 | 55
7 | 22 | 21 | 20 | 20 | 13
38 | 57 | 60 | 62 | 66 | 68
21 | 24 | 23 | 23 | 23 | 24
5 | 33 | 33 | 33 | 33 | 35
26 | 57 | 56 | 56 | 56 | 59
98 | 117 | 123 | 132 | 138 | 146
47 | 58 | 67 | 67 | 62 | 59
145 | 175 | 190 | 199 | 200 | 205
143 | 143 | 167 | 190 | 237 | 261
175 | 175 | 179 | 183 | 191 | 195
318 | 318 | 346 | 373 | 428 | 456
334 | 393 | 441 | 484 | 547 | 566
280 | 363 | 383 | 383 | 374 | 398
613 | 756 | 824 | 867 | 921 | 964
FTE
FTC
Sub-Total
FTE
FTC
Sub-Total
FTE
FTC
Sub-Total
FTE
FTC
Sub-Total
FTE
FTC
Sub-Total
FTE
FTC
Sub-Total
FTE
FTC
Sub-Total
FTE
FTC
Sub-Total
Totals
FTE
FTC
Sub-Total

## Slide 2: CART Resource Needs Dashboard- By Role
7
Unit of measure
* Footnote
Source: Source
Working Draft - Last Modified 8/24/2007 2:36:55 PM
-50
Role | Current | 30 Days (Aug) | 60 Days | 90 Days | Year End | Peak
Senior Project Manager | 4 (1) | 12 (3) | 13 (2) | 14 (1) | 14 (1) | 14 (3)
Project Manager | 2 (1) | 12 (8) | 14 (8) | 16 (8) | 17 (7) | 17 (8)
Business Analyst | 0 (0) | 7 (7) | 8 (7) | 8 (7) | 10 (9) | 14 (13)
Senior Business Architect | 0 (0) | 1 (1) | 1 (1) | 1 (1) | 1 (1) | 1 (1)
Business Architect | 0 (0) | 3 (3) | 3 (3) | 3 (3) | 3 (3) | 3 (3)
Senior Business SME | 17 (2) | 33 (9) | 32 (9) | 32 (9) | 31 (8) | 33 (9)
Business SME | 16 (3) | 27 (11) | 30 (11) | 30 (11) | 30 (10) | 30 (11)
Senior Data Analyst | 0 (0) | 0 (0) | 1 (0) | 1 (0) | 1 (0) | 1 (0)
Data Analyst | 1 (0) | 1 (0) | 1 (0) | 1 (0) | 1 (0) | 1 (0)
Senior Financial Analyst | 0 (0) | 3 (2) | 3 (2) | 4 (2) | 4 (2) | 4 (2)
Financial Analyst | 2 (0) | 4 (0) | 4 (0) | 4 (0) | 6 (0) | 6 (0)
Financial Specialist/SME | 116 (16) | 138 (25) | 154 (34) | 170 (39) | 171 (36) | 174 (41)
Senior Risk Manager | 4 (0) | 4 (0) | 4 (0) | 4 (0) | 4 (0) | 4 (0)
Risk Manager | 7 (0) | 7 (0) | 9 (0) | 9 (0) | 9 (0) | 9 (0)
Risk Director | 2 (0) | 2 (0) | 2 (0) | 3 (0) | 2 (0) | 3 (0)
Manager Model Dev/Risk | 14 (1) | 25 (8) | 27 (8) | 28 (8) | 29 (7) | 30 (8)
Director Model/Risk | 12 (0) | 20 (0) | 20 (0) | 20 (0) | 21 (0) | 21 (0)
Officer Model Dev/Risk | 45 (30) | 57 (38) | 58 (38) | 59 (38) | 61 (38) | 62 (38)
Legal Specialist | 1 (0) | 1 (0) | 1 (0) | 1 (0) | 1 (0) | 1 (0)
Tax Specialist | 2 (2) | 4 (2) | 7 (2) | 7 (2) | 7 (2) | 7 (2)
Technology Senior Manager | 6 (0) | 7 (0) | 8 (0) | 9 (0) | 12 (0) | 12 (0)
Senior Technical PM | 0 (0) | 1 (1) | 1(1) | 1(1) | 1(1) | 2 (1)
Technical PM | 32 (18) | 32 (18) | 35 (18) | 38 (18) | 47 (20) | 47 (20)
Functional Analyst | 71 (26) | 71 (26) | 79 (27) | 86 (29) | 108 (32) | 108 (32)
Development Manager | 0 (0) | 0 (0) | 1 (1) | 1 (1) | 1 (1) | 1 (1)
Developer/Programmer | 74 (55) | 74 (55) | 77 (56) | 80 (57) | 90 (61) | 90 (61)
Technical Data Analyst | 33 (16) | 33 (16) | 38 (16) | 43 (16) | 58 (16) | 58 (16)
Technical Analyst | 33 (16) | 33 (16) | 39 (16) | 45 (17) | 62 (19) | 62 (19)
Tester | 55 (37) | 55 (37) | 56 (37) | 57 (38) | 61 (39) | 61 (39)
Architect | 13 (7) | 13 (7) | 14 (7) | 15 (7) | 18 (8) | 18 (8)
Technical Writer | 0 (0) | 0 (0) | 3 (0) | 3 (0) | 3 (0) | 5 (0)
TOTALS | 613 (283) | 756 (363) | 824 (383) | 867 (383) | 921 (374) | 964(398)
Incremental |  | 143 (80) | 68 (20) | 43 (0) | 54 (-9) | 43(24)
Total Resources (External)

## Slide 3: CART program will require an immediate ramp up of internal resources
  886
  891
  903
  Mar-16
  928
  871
  Feb-16
  938
  May-16
  Jun-16
  Apr-16
  Jul-16
  Nov-15
  953
  Dec-15
  Oct-15
  897
  Jul-15
  Jan-16
  867
  921
  756
  Sep-15
  614
  824
  Aug-15
55
94
129
153
175
197
202
204
208
209
209
210
Internal1:
Full-time employees (FTE) and full-time consultants (FTC) needed across CART workstreams
FTE and FTC
Current
  External FTC
  Internal FTE
  Entities / Factories FTE
Incremental to current:
84
104
104
101
95
97
76
63
34
20
15
0
External:
4
13
20
29
37
45
45
46
46
47
47
47
Entities / Factories:
1 SHUSA CART related resources; T&O Internal includes SHUSA and SBNA

## Slide 4: Significant new hiring / reallocation is required across Model Dev, MRM, Finance and CCAR workstreams for internal FTEs
  17
  10
  5
  17
  1
  2
  5
  17
  5
  10
  9
  0
  CCAR
  Model Dev
  8
  483
  Ops Risk
  Dec-15
  MRM
  Finance
  Risk
  Jun-16
  Mar-16
  478
  449
  Sep-15
  9
  Jul-15 (Current)
  274
  16
  11
  IHC
  Data & IT
  11
  8
  11
  15
  367
  Data & IT
  MRM
  IHC
  CCAR
  Ops Risk
  Finance
  Model Dev
  Risk
Cumulative additional internal resources needed by workstream
Internal FTE

## Slide 5: CART Dashboard by Role (1/4)
7
Unit of measure
* Footnote
Source: Source
Working Draft - Last Modified 8/24/2007 2:36:55 PM
-50
Role | Type | Current | 30 Days | 60 Days | 90 Days | Year End | Peak
Senior Project Manager | FTE | 3 | 9 | 11 | 13 | 13 | 13
 | FTC | 1 | 3 | 2 | 1 | 1 | 0
 | Sub-Total | 4 | 12 | 13 | 14 | 14 | 13
Project Manager | FTE | 1 | 4 | 6 | 8 | 10 | 11
 | FTC | 1 | 8 | 8 | 8 | 7 | 6
 | Sub-Total | 2 | 12 | 14 | 16 | 17 | 17
Business Analyst | FTE | 0 | 0 | 1 | 1 | 1 | 1
 | FTC | 0 | 7 | 7 | 7 | 9 | 13
 | Sub-Total | 0 | 7 | 8 | 8 | 10 | 14
Senior Business Architect | FTE | 0 | 0 | 0 | 0 | 0 | 0
 | FTC | 0 | 1 | 1 | 1 | 1 | 1
 | Sub-Total | 0 | 1 | 1 | 1 | 1 | 1
Business Architect | FTE | 0 | 0 | 0 | 0 | 0 | 0
 | FTC | 0 | 3 | 3 | 3 | 3 | 3
 | Sub-Total | 0 | 3 | 3 | 3 | 3 | 3
Senior Business SME | FTE | 15 | 24 | 23 | 23 | 23 | 23
 | FTC | 2 | 9 | 9 | 9 | 8 | 8
 | Sub-Total | 17 | 33 | 32 | 32 | 31 | 31
Business SME | FTE | 13 | 16 | 20 | 20 | 20 | 19
 | FTC | 3 | 11 | 11 | 11 | 10 | 10
 | Sub-Total | 16 | 27 | 30 | 30 | 30 | 29
Senior Financial Analyst | FTE | 0 | 1 | 1 | 2 | 2 | 2
 | FTC | 0 | 2 | 2 | 2 | 2 | 2
 | Sub-Total | 0 | 3 | 3 | 4 | 4 | 4
Financial Analyst | FTE | 2 | 4 | 4 | 4 | 6 | 4
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 2 | 4 | 4 | 4 | 6 | 4

## Slide 6: CART Dashboard by Role (2/4)
7
Unit of measure
* Footnote
Source: Source
Working Draft - Last Modified 8/24/2007 2:36:55 PM
-50
Role | Type | Current | 30 Days | 60 Days | 90 Days | Year End | Peak
Financial Specialist / SME | FTE | 100 | 113 | 120 | 131 | 135 | 133
 | FTC | 16 | 25 | 34 | 39 | 36 | 41
 | Sub-Total | 116 | 138 | 154 | 170 | 171 | 174
Senior Risk Manager | FTE | 4 | 4 | 4 | 4 | 4 | 4
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 4 | 4 | 4 | 4 | 4 | 4
Risk Manager | FTE | 7 | 7 | 9 | 9 | 9 | 9
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 7 | 7 | 9 | 9 | 9 | 9
Risk Director | FTE | 2 | 2 | 2 | 3 | 2 | 3
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 2 | 2 | 2 | 3 | 2 | 3
Manager Model Dev/Risk | FTE | 13 | 17 | 19 | 20 | 22 | 23
 | FTC | 1 | 8 | 8 | 8 | 7 | 7
 | Sub-Total | 14 | 25 | 27 | 28 | 29 | 30
Director Model Dev/Risk | FTE | 12 | 20 | 20 | 20 | 21 | 21
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 12 | 20 | 20 | 20 | 21 | 21
Officer Model Dev/Risk | FTE | 15 | 19 | 20 | 21 | 23 | 24
 | FTC | 30 | 38 | 38 | 38 | 38 | 38
 | Sub-Total | 45 | 57 | 58 | 59 | 61 | 62
Legal Specialist | FTE | 1 | 1 | 1 | 1 | 1 | 1
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 1 | 1 | 1 | 1 | 1 | 1
Tax Specialist | FTE | 0 | 2 | 5 | 5 | 5 | 5
 | FTC | 2 | 2 | 2 | 2 | 2 | 2
 | Sub-Total | 2 | 4 | 7 | 7 | 7 | 7

## Slide 7: CART Dashboard by Role (3/4)
7
Unit of measure
* Footnote
Source: Source
Working Draft - Last Modified 8/24/2007 2:36:55 PM
-50
Role | Type | Current | 30 Days | 60 Days | 90 Days | Year End | Peak
Technical Senior Management | FTE | 6 | 6 | 7 | 8 | 12 | 12
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 6 | 6 | 7 | 8 | 12 | 12
Senior Technical PM | FTE | 0 | 0 | 0 | 0 | 0 | 1
 | FTC | 0 | 1 | 1 | 1 | 1 | 1
 | Sub-Total | 0 | 1 | 1 | 1 | 1 | 2
Technical PM | FTE | 14 | 14 | 17 | 19 | 27 | 27
 | FTC | 18 | 18 | 18 | 18 | 20 | 20
 | Sub-Total | 32 | 32 | 35 | 38 | 47 | 47
Senior Data Analyst | FTE | 0 | 0 | 1 | 1 | 1 | 1
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 0 | 0 | 1 | 1 | 1 | 1
Data Analyst | FTE | 1 | 1 | 1 | 1 | 1 | 1
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 1 | 1 | 1 | 1 | 1 | 1
Development Manager | FTE | 0 | 0 | 0 | 0 | 0 | 0
 | FTC | 0 | 1 | 1 | 1 | 1 | 1
 | Sub-Total | 0 | 1 | 1 | 1 | 1 | 1
Developer / Programmer | FTE | 19 | 19 | 21 | 23 | 29 | 29
 | FTC | 55 | 55 | 56 | 57 | 61 | 61
 | Sub-Total | 74 | 74 | 77 | 80 | 90 | 90
Technical Business Analyst | FTE | 45 | 45 | 51 | 57 | 76 | 76
 | FTC | 26 | 26 | 27 | 29 | 32 | 32
 | Sub-Total | 71 | 71 | 79 | 86 | 108 | 108
Technical Data Analyst | FTE | 17 | 17 | 22 | 27 | 42 | 42
 | FTC | 16 | 16 | 16 | 16 | 16 | 16
 | Sub-Total | 33 | 33 | 38 | 43 | 58 | 58

## Slide 8: CART Dashboard by Role (4/4)
7
Unit of measure
* Footnote
Source: Source
Working Draft - Last Modified 8/24/2007 2:36:55 PM
-50
Role | Type | Current | 30 Days | 60 Days | 90 Days | Year End | Peak
Technical Analyst | FTE | 18 | 18 | 23 | 28 | 43 | 43
 | FTC | 16 | 16 | 16 | 17 | 19 | 19
 | Sub-Total | 33 | 33 | 39 | 45 | 62 | 62
Tester | FTE | 18 | 18 | 19 | 20 | 22 | 22
 | FTC | 37 | 37 | 37 | 38 | 39 | 39
 | Sub-Total | 55 | 55 | 56 | 57 | 61 | 61
Architect | FTE | 6 | 6 | 7 | 8 | 10 | 10
 | FTC | 7 | 7 | 7 | 7 | 8 | 8
 | Sub-Total | 13 | 13 | 14 | 15 | 18 | 18
Technical Writer | FTE | 0 | 3 | 3 | 3 | 3 | 5
 | FTC | 0 | 0 | 0 | 0 | 0 | 0
 | Sub-Total | 0 | 3 | 3 | 3 | 3 | 5
Other | FTE | 1 | 2 | 2 | 2 | 2 | 2
 | FTC | 49 | 70 | 78 | 70 | 56 | 70
 | Sub-Total | 50 | 72 | 80 | 72 | 58 | 72

## Slide 9: Risk Transformation resource plan

## Slide 10: Model Development resource plan

## Slide 11: Model Risk Management resource plan

## Slide 12: Operational Risk resource plan

## Slide 13: Finance Transformation resource plan (1/2)

## Slide 14: Finance Transformation resource plan (2/2)

## Slide 15: Data & IT resource plan

## Slide 16: CCAR resource plan

## Slide 17: IHC resource plan