## Slide 1: Contents
Risk Transformation
Model Development
Model Risk Management
Operational Risk
Finance Transformation
Data and IT
CCAR
IHC
ELS (included in Finance Transformation)

## Slide 2: Risk Transformation - Summary
Key deliverables
Key dependencies
Due by
Sub-workstreams in Risk Transformation
Summary of FRB feedback
Potential execution risks
Risk management framework is not sufficiently developed to provide full subsidiary oversight and support capital adequacy framework
Lack of aligned enterprise-wide and legal entity specific Risk Appetite Statements
Risk identification process does not identify nor appropriately account for all risks when assessing capital needs
Lack of process to consider early warning indicators in the stress scenarios
Risk governance and organization: organizational structure of risk management to enforce the risk appetite statement, and oversight by the SHUSA Boards
Risk appetite: establish and communicate Board approved risk appetite
Risk ID & measurement: tools and processes to quantify the enterprise’s risks
Risk management processes: measurement and management of the enterprise’s risks and application to strategic business decisions
Risk monitoring / Risk reporting: summarize enterprise’s key risks for internal and external stakeholders
Risk data & systems: IT architecture to support effective risk management (integration with IT workstream TBC)
    Data availability and data quality across enterprise
    Management of dependencies and related activities spanning multiple Risk workstreams (e.g. RAS, target operating model, reporting framework and templates)
    Execution risk due to effective transfer of knowledge and capabilities from external resources / consultants
    Staffing and skills requirements of the Target Operating Model will be determined for all three lines of defense during the implementation planning process; significant gaps may affect deliverables in years 2-3
    Model Development: Development of commercial ratings models
    Model Risk Management: Validation of commercial ratings models
    Finance:
      Liquidity Data Mart and tools to support analytics process by second line of defense liquidity risk management
      Implementation of the TOM across IHC entities to support LRM Framework implementation including stress testing scenarios and LST calculations (stressed inflows/outflows >90 days, non-maturity deposits)
    Data & IT:
      IT development to support Commercial Risk Rating implementation / embedding in relevant processes
      IT development for RAS, Risk ID and Risk reporting (pending planned definition of business/data requirements)
    First Line: Input to Material Risk Program (business line / segment Material Risk Inventories)
12/31/15
SHUSA, SCUSA, SBNA RAS design and approval
01/12/16
Initial embedding of top-level RAS in material SHUSA processes and plan further embedding across the enterprise
01/15/16
Develop and execute Material Risk Program
10/02/15
Implement near-term enhancements to Risk org / reporting lines
09/30/16
Assess Risk Culture and define enhancement objectives
TBD
Implement Target Operating Model for each Risk Type / Function
    Roll out new commercial risk ratings for CRE and C&I
08/12/16
11/30/15
    Draft SHUSA’s Governance and Oversight Framework Document
04/01/16
    Risk Operating Model design and implementation planning
TBD
Design and roll-out foundational Risk ID processes
01/08/16
Enhanced Top-level risk policies and 3 LOD articulation
09/07/15
    Define target exec. mgmt. risk reporting landscape
07/31/15
    Implement routine Risk-Business reviews with reports

## Slide 3: Risk Transformation: Project Plan (1/4)
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
  11/30/15xx
  07/31/15xx
  8/15/15xx
  09/30/15xx
  09/30/15xx
  09/30/15xx
  10/31/15xx
  11/30/15xx
  01/31/16xx
  01/15/16xx
  01/31/16xx
Ongoingxx
07/31/15xx
01/08/16xx
TBD
  10/02/15xx
  10/02/15xx
  11/06/15xx
  10/02/15xx
  11/06/15xx
  01/22/16xx
  04/01/16xx
  TBD
  TBD
  Ongoing
  07/15/15xx
  07/15/15xx
  07/15/15xx
  08/01/15xx
  08/01/15xx
  07/15/15xx
  10/01/15xx
  11/01/15xx
  12/01/15xx
  12/01/15xx
  01/3/16xx
02/01/16xx
07/13/15xx
07/13/15xx
08/03/15xx
  08/03/15xx
  08/03/15xx
  08/31/15xx
  08/31/15xx
  10/05/15xx
  11/16/15xx
  02/01/16xx
  11/09/15??xx
  TBD
  01/25/16xx
  B. Gunn
  B. Gunn
  B. Gunn
  B. Gunn
  B. Gunn
  B. Gunn
  B. Gunn
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
  Draft overarching Governance and Oversight Framework Document for SHUSA1; syndicate and finalize xx
    Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company xx
    Define target state committee structure including Board and Management committees xx
    Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries xx
    Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines xx
    Develop policy framework, establish overall policies including guidelines for approval of policies xx
    Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries xx
    Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize xx
  Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans xx
    Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting xx
    Establish comprehensive implementation plans to address these gaps over a multi-year period xx
Execute against multi-year plan for Risk Transformation xx
Implement routine Risk-Business reviews with standardized materials and reports xx
Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) xx
Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement xx
    Identify and implement near term changes to the risk organization and reporting lines across SHUSA xx
    Determine the prioritization of detailed operating model design and rollout by risk type / function xx
    Design detailed operating model and implementation plans for Risk Type / Function A & B (Most likely Credit, ERM + RAS + Strategic) xx
      Define detailed organizational structure and assess talent needs including target headcounts and skill sets xx
      Develop rollout plan xx
    Design detailed operating model and implementation plans for Risk Type / Function C & D (Most likely Market & Liquidity, Compliance) xx
    Design detailed operating model and implementation plans for Risk Type / Function E & F (Most likely Risk Management Information, Capital Risk)xx
    Implement the redesigned Operating Model for each Risk Type / Function1 ??xx
    Conduct post-implementation reviews x2
  Rollout communication and training for organizational changes related to 3 LOD xx
  1 SHUSA to be designated as the IHC 2 Dates dependent on the implementation plans to be developed as a prior step

## Slide 4: Risk Transformation: Project Plan (2/4)
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
  10/02/16xx 09/30/16xx
  12/18/15xx
  01/02/17xx
  04/04/17xx
  08/03/16xx
  07/01/16xx
  06/15/16xx
  04/01/16xx
  07/01/16xx
  B. Gunn
  B. Gunn
  B. Gunn/C. Briongosx
  B. Gunn/C. Briongosx
  B. Gunn/C. Briongosx
  E. Smith/ R. Parrish
  E. Smith/ R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  D. Allaire
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
  Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment xx
  Define multiyear plan to achieve a sound target state risk culture xx
  Assess existing Risk Management Performance Scorecards and identify gaps xx
  Rollout systematic performance assessments and risk-based compensation structures xx
  Diagnose retention challenge and design recruitment and retention mechanisms xx
Risk Appetite Statement (RAS)
  Develop interim RAS for SBNA and SCUSA, and begin ongoing monitoring xx
  Develop SHUSA, SBNA, and SCUSA RAS, and obtain approvals xx
    Develop SHUSA-level RAS (top-down approach)
    Develop SBNA- and SCUSA-level RAS (bottom-up approach), ensuring alignment to SHUSA RAS xx
    Establish related processes and documentation for ongoing management of RAS (e.g. breach escalation and remediation process – including consequences)
    Secure Board approval of SHUSA, SBNA, and SCUSA RAS xx
Communicate Board-approved SHUSA, SBNA, and SCUSA RAS to enterprise xx
Design RAS for remaining subsidiaries (NY, Puerto Rico, Miami) and obtain approvals
    NY RAS design and approval
    Puerto Rico RAS design and approval
    Miami RAS design and approval
Initiate embedding of RAS in material SHUSA processes and plan for embedding RAS across the enterprise
    Identify key processes (e.g. strategic planning, capital planning) and update process maps with explicit RAS links
    Initiate implementation of RAS in all material processes
    Continue to cascade the risk appetite statement for the remainder of subsidiaries and business units and ensure alignment with overall SHUSA risk appetite statement
    Cascade the embedding of the risk appetite statement for key processes across the organization
    Continue to communicate risk appetite statement throughout the enterprise, including training in the new escalation and remediation process
    Periodically enhance risk appetite statement based on the latest results of material risk identification and improved risk measurement across the enterprise; including incorporation of risk-based capital metrics
06/08/15xx
06/08/15
  06/08/15
  06/08/15xx
  07/06/15
  08/31/15xx
  12/01/15xx
  02/01/16
  02/01/16
  02/01/16
  02/01/16
  11/02/15
  11/02/15
  11/30/15
  01/01/16
  01/01/16
  04/01/16
  10/03/16
09/30/15xx
12/31/15xx
  08/28/15
  11/20/15xx
  11/20/15xx
  12/31/15
  02/24/16
  06/30/16
  06/30/16
  06/30/16
  06/30/16
  01/12/16
  11/27/15
  01/12/16
  06/30/16
  06/30/16
  09/30/16
  06/30/17
Risk ID & Measurement
  01/15/16xx
  05/01/15
  10/02/15 push out 1 month for all??xx
  07/31/15
  10/02/15 push out 1 month for all??xx
  02/02/15
  02/02/15
  05/28/15
  05/28/15
  08/03/15xx
    Design and execute the Material Risk Program across SHUSA
    Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance)
    Create risk inventory for the Subsidiaries / Business Entities and hold workshops for aggregation
    Compile Business Line / Segment Material Risk Inventory
    Hold Subsidiary / Business Entity Aggregation Workshops (include 2nd LOD challenge) and Governance (Material Risk Inventory Reviews / Approvals)

## Slide 5: Risk Transformation: Project Plan (3/4)
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
Risk ID & Measurement
  Review Foundational Risk ID Processes and Build Multi-Year Enhancement Objectives
    Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place
    Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes
    Develop Foundational Risk Process remediation plan
  01/18/16
  01/18/16
  02/01/16
  03/14/16
  E. Smith
  03/28/16
  01/29/16
  03/14/16
  03/28/16
  Updated SHUSA Risk taxonomy
  Updated material risk inventory template and guidance
  Develop training materials, policies and procedures based on updated Material Risk Program process
  Identify technology needs, requirements definition and implementation planning to support risk identification
  Develop and implement planned data and technology solutions (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.)
  11/30/15xx
  01/04/16xx
  02/08/16xx
  05/16/16xx
  05/16/16xx
  E. Smith
  E. Smith
  E. Smith
  E. Smith
  E. Smith
  01/01/16xx
  02/05/16xx
  05/13/16xx
  07/22/16xx
  01/13/17xx
Risk Management Processes
  Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements
  Design Liquidity Stress Test Challenge Process Framework and get approvals xx
  Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA xx
  Rollout Commercial Risk Ratings xx
    Establish governance and oversight on commercial risk ratings governance x
    Rollout redesigned CRE rating models x
      CRE model development and validation (refer to Model Dev. / Model Risk workstreams)
      CRE UAT / pilot testing x
      CRE end-user training x
      CRE initial model implementation / rollout x
  TBC
  12/31/15xx
  03/31/16xx
  08/12/16 xx
  07/31/15
  TBC
  TBC1
  04/01/16xx
  05/27/16xx
  05/06/16
  TBC
  06/01/15xx
  02/01/16xx
  05/04/14
  06/01/15
  TBC
  TBC1
  02/01/16xx
  02/01/16xx
  04/04/16
  M. Aya
  M. Aya / M. Lasso
  J. Hennessy / C. Cuervo
  D. Spector
  1 Refer to Model Development and Model Risk Management workstreams for relevant dates on development and validation
  Deliverables
    Milestones under the deliverable
    Completed
    Create risk inventory for the SHUSA, hold workshops for aggregation
    Preparation for Aggregation to create SHUSA Material Risk Inventory
    Hold SHUSA Aggregation Workshops (include 2nd LOD challenge)
    Execute on SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge)
    Obtain approvals for Material Risks of SHUSA (final aggregation, Board and Management review and challenge)
    Draft Risk ID and Assessment Policy and obtain approvals
    Establish clear linkage of MRP outputs to capital planning scenario design process
  10/05/15xx
  10/05/15xx
  10/12/15xx
  10/26/15xx
  11/09/15xx
  10/26/15xx
  10/12/15xx
  01/15/16xx
  10/19/15xx
  10/26/15xx
  11/09/15xx
  12/04/15xx
  01/15/16xx
  12/04/15xx

## Slide 6: Risk Transformation: Project Plan (4/4)
Risk Management Processes
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
    Rollout redesigned C&I rating models
      C&I model development and validation (refer to Model Dev. / Model Risk workstreams)
      C&I UAT / pilot testing
      C&I end-user training
      C&I initial model implementation / rollout
    Create requirement definitions for technology solution or CRE and C&I model implementation x
    Develop and implement technology solution for CRE and C&I models) x
  Conduct gap analyses across risk types focusing on methodology, tools, processes, and expectations as defined by the operating model and benchmark to industry practice xx
  Create remediation plans to address gaps and initiate remediation actions xx
  TBC
  TBC1
  06/03/16xx
  07/29/16xx
  07/01/16xx
  04/15/16xx
  08/12/16xx
  09/30/16
  12/04/16xx
  TBC
  TBC1
  04/04/16xx
  04/04/16xx
  06/06/16xx
  05/04/15
  06/01/15
  07/01/16
  08/03/16xx
Risk Monitoring / Risk Reporting
  Assess current reporting landscape and make quick-win enhancements to priority reports (Board and Level 1 Risk Committees) and reporting protocols
  Define target exec. mgmt. risk reporting landscape and scope of remediation (linked to committee structure) x
  Identify risk aggregation needs and cultivate dedicated resources to manage reporting
  Develop and implement Wave 1 of exec. mgmt. reporting enhancements x
    Develop template reports for Wave 1 and socialize
    Roll-out of Wave 1 reports (similar process for all waves)
      Review business/data requirements for interim and target state of Wave 1 reports and update as needed
      Identify and document data gaps and develop remediation plans
      Pilot reports using available data (manual where necessary)
      Collect feedback from key stakeholders and refine reports
      Implement refined reports in-production
  Develop and implement Wave 2 of exec. mgmt. reporting enhancements x
    Development of template reports and socialization of Wave 2 (based on materiality)
    Roll-out of Wave 2 reports (similar process as Wave 1)
  Develop and implement Wave 3 of exec. mgmt. reporting enhancements x
    Development of template reports and socialization of Wave 3 (Remaining Entities)
    Roll- out of Wave 3 reports (similar process as Wave 1)
  Execute on Remediation Plans and Roll-out Enhanced Reports
  Develop and launch additional waves of reporting enhancements as needed
  Refine data requirements/resources to enhance quality of reports
  Develop quality assurance plans and controls for newly enhanced reports
  Assess resource needs and implement additional refinements to monitoring requirements
  08/17/15
  09/07/15
  01/29/16
  11/09/15
  09/25/15
  11/09/15
  10/23/15
  11/09/15
  10/09/15
  11/06/15
  11/09/15
  12/28/15
  10/30/15
  12/28/15
  04/01/16
  01/29/16
  04/01/16
  01/02/17
  09/30/16
  09/30/16
  09/30/16
  03/31/17
  06/15/15
  07/27/15
  08/31/15
  08/31/15
  08/31/15
  09/28/15
  09/28/15
  09/28/15
  09/28/15
  10/26/15
  11/06/15
  10/05/15
  10/05/15
  11/02/15
  12/28/15
  12/28/15
  02/01/16
  04/01/16
  04/01/16
  04/01/16
  04/01/16
  04/01/16
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  Deliverables
    Milestones under the deliverable
    Completed
  J. Hennessy / E.Smith
  J. Hennessy / E.Smithx
  1 Refer to Model Development and Model Risk Management workstreams for relevant dates on development and validation