## Sheet2
Oliver Wyman Comments
Draft overarching Governance and Oversight Framework Document for SHUSA1; syndicate and finalize | 07/15/15 | 11/30/15
Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 07/15/15 | 07/31/15
Document guiding principles and foundational elements (e.g., business ownership of risks, lines of defense, shared services, RAS, Board and management respective R&R etc.) | 07/15/15 | 07/24/15
Syndicate with key stakeholders and get necessary approvals for the guiding principles | 07/27/15 | 07/31/15
Define target state committee structure including Board and Management committees | 07/15/15 | 08/15/15 | Central Team: Please confirm that this is SHUSA only
Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 2015-08-01 | 09/30/15
Articulate Governance mechanisms between SHUSA and the Group | 2015-08-01 | 2015-08-22
Define Board and management committee reporting lines - Risk and compliance
Create committee charters capturing composition, roles, decision rights, escalations etc. - Risk and compliance | 2015-08-01 | 2015-09-12
Define Board and management committee reporting lines - Finance
Create committee charters capturing composition, roles, decision rights, escalations etc. - Finance | 2015-08-15 | 2015-09-26 | Caveat: Little visibility here
Define Board and management committee reporting lines - Business
Create committee charters capturing composition, roles, decision rights, escalations etc. - Business (Executive, ALCO etc.) | 2015-08-15 | 2015-09-26 | Caveat: Little visibility here
Define Board and management committee reporting lines - Other committees
Create committee charters capturing composition, roles, decision rights, escalations etc. - Other committees (e.g. T&O) | 2015-08-15 | 2015-09-26 | Caveat: Little visibility here
Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 09/30/15
Document organization structure for SHUSA and subsidiaries, along with reporting lines | 2015-08-01 | 09/30/15
Define roles and responsibilities, including decision rights, escalation protocols etc. | 2015-08-01 | 09/30/15
Define reporting lines for legal and audit |  |  | Caveat: Little visibility here
Develop policy framework, establish overall policies including guidelines for approval of policies | 07/15/15 | 09/30/15
Establish overarching Policy Framework including guidelines for approval | 07/15/15 | 2015-08-12 | Central Team: could we confirm who is doing EPA ?
Establish prioritized policies and procedures across functions |  |  | Central team: please confirm what is meant by "prioritized"
Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 10/31/15
Create the overall reporting framework - core principles, cadence and rhythm of reporting, broad definition of report types (production reports vs. custom reports) | 2015-10-01 | 10/31/15 | Central team: there already is a reporting initiative, could you please confirm that this is not rework?
Define priority reports for each function across SHUSA and its subsidiaries | 2015-10-01 | 10/31/15
Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 11/30/15
Syndicate with subsidiaries, and refine framework document | 2015-11-01 | 2015-11-22 | Relying on the date given above
Get approvals from SHUSA and subsidiary Boards | 2015-11-22 | 2015-11-29
Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 01/31/16 | Central Team: Should we be developing "multi year remediation plan" ?
Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 2015-12-01 | 01/15/16 | Central Team: Is a gap analysis necessary ? Maybe should be going through TOM / key processes instead
Conduct gap assessment for SHUSA and subsidiaries against Framework Document | 2015-12-01 | 2016-01-12
Synthesize key gaps and syndicate with stakeholders | 2016-01-12 | 2016-01-26
Establish comprehensive implementation plans to address these gaps over a multi-year period | 2016-01-03 | 01/31/16
Execute against multi-year plan for Risk Transformation | 2016-02-01 | Ongoing
Note on C12: Chatin, Antoine: overlap of 3 weeks with Risk
Note on C13: Chatin, Antoine: Same as Finance
Note on D13: Chatin, Antoine: Same as Finance
Note on C14: Chatin, Antoine: Same as Finance
Note on D14: Chatin, Antoine: Same as Finance
Note on C16: Chatin, Antoine: Same as Finance
Note on D16: Chatin, Antoine: Same as Finance