## Inventory Instructions
CART- Deliverable Inventory Instructions
The CART Master Deliverable Inventory is a document to be used by each workstream to document all year 1 deliverables and associated milestones.
The expectation is that all items defined as a Year 1 priority will have at least one concrete year 1 deliverable associated with them. Each deliverable is expected to have between 1-5 major milestones associated with achieving the deliverable. The number of milestones will vary based on the nature of the deliverables.
To use the Deliverable Inventory and add a deliverable please do the following:
1. Select the tab associated with your workstream
2. In column A, select the Priority from the pull down menu that the deliverable you are creating is associated with
3. Enter a description for the new deliverable in Column B, next to the priority you have just selected
4. In Column C, please identify a proposed owner for the deliverable if it is currently known
5. In Column D, please enter the proposed delivery date (if currently known)
6. In column E, please identify if the deliverable has any IT dependency (if currently known)
7. In columns F- O, please enter any associated milestones (and known dates) with the deliverable
8. Columns P-S are intended to be completed later this week, but can be completed now if data is known
9. To enter the next deliverable on the following line, repeats steps 1-8.
Please note that you can have more than one deliverable associated with a priority. To do this, just select the priority in column A for as many deliverables that are associated with the priority. For example, if you have 5 deliverables associated with your first priority on your list, the first 5 lines in your inventory would have the same priority selected with a different deliverable on each line.

## Master Deliverable Inventory
|  |  | Yes | [12 empty] | High
|  |  | No | [12 empty] | Medium
Low
Workstream | Sub Work-Stream | Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Finance Transformation
Finance Transformation | Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | Enhanced SOX Internal Control framework and methodology | M. Munoz | 2015-12-31 | No | [10 empty] | Medium | High | Yes | #REF!
Finance Transformation | Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | SOX based CCAR Internal Control framework and methodology | M. Munoz | 2015-12-31 | No | Conduct gap assessment against SOX framework | 2015-06-30 | Enhance framework to align with CCAR internal controls requirements | 2015-09-30 | Benchmark framework against industry standard/regulatory expectations | 2015-12-31 |  |  |  |  | Medium | Medium | Yes
Finance Transformation | Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | EUA Internal Conttrol Framework and Methodology | M. Munoz | 2015-12-31 | No | [10 empty] | Medium | Medium | No
Finance Transformation | Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | BSI SOX/COSO Internal Control program | M. Munoz | 2015-12-31 | yes | Approve and hire resources for open SOX positions across SHUSA | 2015-07-31 | Acquire tool (Archer) to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-06-30 | Configure (Archer) tool to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-07-31 | Source clean data into the tool to enable adherence with enhanced SOX methodology | 2015-11-30 | Complete testing and certification for SOX | 2015-12-31 | High | Medium | No
Finance Transformation | Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | BSI/PR SOX based CCAR Internal Control Program | M. Munoz | 2015-12-31 | yes | Approve and hire resources for open SOX positions across SHUSA | 2015-07-31 | Leverage tool used for SOX compliance to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-11-30 | Conduct gap assessment against existing CCAR controls and documentation | 2015-09-30 | Develop and execute on remediation plan based on gap findings | 2015-09-30 | Complete testing and certification for CCAR | 2015-12-31 | Medium | Medium | No
Finance Transformation | Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | SHUSA (All IHC Entities) EUA Internal Control Program | M. Munoz | 2015-12-31 | No | Operationalize existing tool across all new SHUSA subsidiaries to remediate existing MRIA on spreadsheet risk management | 2015-06-30 | Execute active identification and management of critical spreadsheets | 2015-12-31 | [6 empty] | Medium | High | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | 2015 Strategic Plan Timeline (Planning Calendar) | D. Budington | 2015-06-15 | No | Draft of the 2015 Strategic Plan Timeline framework has been developed and reviewed with stakeholders | 2015-06-05 | Revisions are incorporated and the 2015 Strategic Plan Timeline has been finalized | 2015-06-15 | 0 | 0 | 0 | 0 |  |  | Medium | Medium | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | FP&A Policy Documentation and Implementation | D. Budington | 2015-07-30 | No | Governance Model Design has been reviewed and approved by SHUSA and subsidiary EMCs | 2015-06-30 | Planning process design has been reviewed and approved (same approvars) | 2015-06-30 | Data flow map and reconciliation points has been review and approved | 2015-07-30 |  |  |  |  | Medium | Medium | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | 2015 Strategic Planning Forecasting Process Design and Implementation | D. Budington | 2015-11-15 | No | [10 empty] | High | High | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | Critical positions within strategic planning and PPNR teams are staffed to execute 2015 FP&A activities | D. Budington | 2015-07-30 | Yes | All positions posted and recuriters engaged | ongoing | Develop skills assessment gaps and remediation and training plans | ongoing | Identify and manage succession and operational risks | 0 |  |  |  |  | High | High | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | Board approved and well documented Strategic Plan (SP18) | D. Budington | 2015-12-31 | No | [10 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | 2016 Budget | D. Budington | 2015-12-31 | No | Mapping process of Budget to Strategic Plan has been completed | 2015-09-15 | Entity submission has been completed | 2015-11-01 | Review & challenge process has been completed | 2015-12-01 | Final submission has occurred | 2015-12-15 | Final Board approval has been received | 2015-12-31 | Medium | Medium | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational SHUSA Management Reporting function
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational SHUSA Management Reporting function
Finance Transformation | Finance Planning and Analysis | Establish and implement foundational SHUSA Management Reporting function | Systemic production of monthly reporting packages | D. Budington | 2015-10-30 | No | [10 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Incorporate cost of Contingent Liquidity across all SHUSA | Methodology and Interim Solution for Contingent Liquidity | D. Budington | 2015-12-31 | No | [10 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Develop cost allocation policies and implementation plan to support organizational and product profitability analysis used in strategic planning and performance management | Cost allocation policies and implementation plan | D. Budington | 2015-12-31 | No | [10 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Finance Planning and Analysis | Develop FP&A's Target Operating Model requirements and implementation plan | Detailed FP&A TOM (end state) implementation plan | D. Budington | 2015-12-31 | Yes | [10 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Treasury | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions | Established policies, procedures and MIS per regulatory requirements and enhanced internal practices | Manuel Aya | 2015-10-20 | No | [10 empty] | Medium | Medium | No | #REF!
Finance Transformation | Treasury | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions | Independent Review of LRM adequacy and effectiveness | Manuel Aya | 2015-10-20 | No | [10 empty] | Medium | Low | No | #REF!
Finance Transformation | Treasury | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate | Established Policies and Procedures to Consolidate Intraday Liquidity Management | Manuel Aya | 2015-09-30 | No | [10 empty] | High | Medium | Yes | #REF!
Finance Transformation | Treasury | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate | Established Policies and Procedures to Consolidate Intraday Collateral Management | Manuel Aya / Ed Cipullo | 2015-09-30 | Yes | [10 empty] | High | Medium | Yes | #REF!
Finance Transformation | Treasury | Incorporate intraday procedures in SHUSA’s Cash Management and Funding policy and procedures | Incorporated intraday procedures and intraday metrics into SHUSA’s Liquidity Management and Funding policy and procedures | Manuel Aya, Bill Brundige, Andy Withers | 2015-12-31 | Yes | [10 empty] | High | High | Yes | #REF!
Finance Transformation | Treasury | Develop first version of Board-approved Enterprise and Operating policies, procedure and charter for Interest Rate Risk | Produced Board approved Enterprise Operating Liquidity Risk Management Policy (OLRPM) and associated procedure(s) | Victor Morillo | 2015-12-31 | No | Enterprise Operating Liquidity Risk Management Policies (OLRMP) developed | 2015-06-30 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) approved by all applicable management committees | 2015-06-30 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) implemented for SHUSA, SCUSA, SBNA | 2015-09-23 |  |  |  |  | Medium | Medium | No
Finance Transformation | Treasury | Enhance QRM operating environment including prudent mix of Chart of Accounts and dimensions, access controls and optimization of processes | Analyzed and Revised QRM environment including Chart of Accounts, dimensions, controls and optimization of processes | Niraj Biswas | 2015-12-31 | Yes | QRM Chart of Accounts and Dimensions analyzed, reviewed and enhanced | 2015-09-30 | [8 empty] | High | High | Yes
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Cash Flow Projections Completed | Manuel Aya | 2015-12-31 | Yes | Baseline Cashflow Projections | 2015-06-01 | Cash Flow Projection tool / reporting developed and deployed | 2015-12-31 | [6 empty] | High | Medium | No
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Model Validation Completed | MRM | 2015-12-31 | Yes | Conduct formal Model Validation on Stress testing Scenarios | 2015-12-31 | 0 | 0 | 0 | 0 |  |  |  |  | High | Medium | No
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | First round of stress testing completed and documented | Manuel Aya | 2015-05-29 | Yes | Stress Testing Tool developed and available | 2015-05-04 | First round of stress test generating scenarios and assumptions approved by all applicable management committees | 2015-05-29 | First round of stress test scenarios executed and complete results generated | 2015-05-29 | First round of stress test results fully documented and analyzed | 2015-05-29 |  |  | High | Medium | No
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Enhanced stress testing process with additional "framework" scenarios | Manuel Aya | 2015-12-31 | Yes | First round of enhanced stress test generating scenarios and assumptions approved by all applicable management committees | 2015-12-31 | Enhanced first round of stress test scenarios executed and complete results generated | 2015-12-31 | Enhanced first round of stress test results fully documented and analyzed | 2015-12-31 | Enhanced first round of stress test results published to all applicable management parties | 2015-12-31 |  |  | High | Medium | No
Finance Transformation | Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Enhanced stress testing process | Manuel Aya | 2016-04-18 | No | Conduct regression analysis of stress testing scenarios and assumptions for applicability, accuracy, and adjustment | 2016-04-18 | Revalidate, via formal Model Risk Management process, proposed adjustments to stress testing scenarios and / or assumptions | 2016-04-18 | Revised (if applicable) stress testing scenarios and assumptions approved by all applicable management committees | 2016-04-18 |  |  |  |  | High | Medium | No
Finance Transformation | Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Operationalization of stress testing completed and documented | Manuel Aya | 2016-04-18 | Yes | Second round of stress test generating scenarios and assumptions approved by all applicable management committees | 2016-04-18 | Second round of stress test scenarios executed and complete results generated | 2016-04-18 | [6 empty] | High | Medium | No
Finance Transformation | Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Updated Liquidity Buffer | Manuel Aya | 2015-09-30 | No | Evaluate results of second round of stress testing to identify required adjustments to the Liquidity Buffer | 2015-06-30 | [8 empty] | Medium | Medium | No
Finance Transformation | Treasury | Develop capability to submit 2052a reports by 1/1/16 | Developed solution for data acquisition and storage to support 2052A regulatory reporting | Manuel Aya | 2015-12-31 | Yes | All required source data identified and availability/ location confirmed and documented | 2015-12-31 | All required source data extracted from identified source(s) and available for testing | 2015-12-31 | 2052A reporting solution developed and available for testing | 2015-12-31 | Quality Assurance testing for 2052A Reporting solution complete | 2015-12-31 | 2052A Reporting solution tested and deployed. | 2015-12-31 | High | High | No
Finance Transformation | Treasury | U.S. LCR reporting (though not currently required, is expected to be produced as a result of the granularity of 2052a reporting) | Developed reporting solution to generate Liquidity Coverage Ratio (LCR) reporting based upon data submitted via 2052A | Manuel Aya | 2015-12-31 | Yes | Liquidity Coverage Ratio (LCR) reporting solution developed and available for testing | 2015-12-31 | Quality Assurance testing for Liquidity Coverage Ratio (LCR) reporting solution complete | 2015-12-31 | 0 | 0 | 0 | 0 |  |  | High | High | No
Finance Transformation | Accounting, Tax, & Reporting | Establish a set of reconciled and clean current and historical financial data (internal sources where possible) to use for reporting and to support forecasting capabilities (CCAR and Strategic Planning) | Historical reporting requirements (from CCAR/Strategic Plan perspective) | Eric Ratican | 2015-12-31 | No | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | High | High | Yes
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation implemented at SBNA | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SBNA to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SBNA GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SBNA to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from SBNA to Hyperion, including control testing scope | 2015-05-22 |  |  | High | High | Yes
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation implemented at SCUSA | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SCUSA to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SCUSA GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SCUSA to Hyperion | 2015-05-22 |  |  |  |  | High | High | Yes
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation Implemented at BSI | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map BSI to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in BSI GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from BSI to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from BSI to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at BSI | 2015-05-22 | High | High | Yes
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidations Implemented at PR | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map PR to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in PR GL mapping | 2015-05-22 | [6 empty] | High | High | Yes
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidations Implemented at SIS | Nancy Reinhard | 2015-11-06 | Yes | [10 empty] | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation Implemented at other IHC entities | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map IHC-Other to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in IHC-Other GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from IHC-Other to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from IHC-Other to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at IHC-Other | 2015-05-22 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Hyperion DRG Implemented | John Moore | 2015-11-12 | Yes | DRG: Complete Assess Phase | 2015-06-24 | DRG: Complete Design Phase | 2015-07-23 | DRG: Complete Construct Phase | 2015-08-28 | DRG: Complete Implement Phase | 2015-09-24 | DRG: Complete Operate & Review Phase | 2015-11-12 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Hyperion DRM Implemented | John Moore | 2015-11-12 | Yes | DRM: Complete Assess Phase | 2015-05-08 | DRM: Complete Design Phase | 2015-06-24 | DRM: Complete Construct Phase | 2015-08-11 | DRM: Complete Implement Phase | 2015-10-02 | DRM: Complete Operate & Review Phase | 2015-11-12 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Formal Governance over CoA/Hierarchies | John Moore | 2015-12-31 | No | Define roles/responsibilities for managing CoA | 2015-06-24 | Obtain acknowledgement from entities of understanding of Governance process | 2015-06-24 | Implement formal governance | 2015-12-31 | 0 | 0 | 0 | 0 | High | Medium | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | FRS fed from HFM | Sean Mulcahy | 2015-12-31 | Yes | Map expected HFM capability to FRS reporting requirements | 2015-12-31 | Identify gaps in HFM/FRS mapping | 2015-12-31 | Develop plan for remediation of HFM/FRS mapping gaps | 2015-12-31 | Remediate HFM/FRS mapping gaps | 2015-12-31 | Design HFM/FRS integration | 2015-12-31 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | Moody's fed from HFM | Eric Ratican | 2015-12-31 | Yes | Map expected HFM capability to Moody's reporting requirements | 2015-12-31 | Identify gaps in HFM/Moody's mapping | 2015-12-31 | Develop plan for remediation of HFM/Moody's mapping gaps | 2015-12-31 | Remediate HFM/Moody's mapping gaps | 2015-12-31 | Design HFM/Moody's integration | 2015-12-31 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | Workiva fed from HFM | Kerry Marshall | 2016-02-29 | Yes | Map expected HFM capability to Workiva reporting requirements | 2016-02-29 | Identify gaps in HFM/Workiva mapping | 2016-02-29 | Develop plan for remediation of HFM/Workiva mapping gaps | 2016-02-29 | Remediate HFM/Workiva mapping gaps | 2016-02-29 | Design HFM/Workiva integration | 2016-02-29 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Fully functional CoA with hierarchy dimensionality | Nancy Reinhard | 2015-09-30 | Yes | Complete HFM implementation (dependency placeholder) | 2015-11-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Reconciliation process In place between GL's and Hyperion | Nancy Reinhard | 2015-09-30 | Yes | Establish reconciliation process for SHUSA | 2015-09-30 | Establish reconciliation process for SBNA | 2015-09-30 | Establish reconciliation process for SCUSA | 2015-09-30 |  |  |  |  | Medium | Medium | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Reconciliation process In place between Hyperion and Financial/regulatory reporting tools | Nancy Reinhard | 2015-09-30 | Yes | Establish reconciliation process for FRS | 2015-09-30 | Establish reconciliation process for Moody's | 2015-09-30 | Establish reconciliation process for Workiva | 2015-09-30 | 0 | 0 | 0 | 0 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Reconciliatio process between reporting tools in place. | Nancy Reinhard | 2015-09-30 | Yes | Identify common elements between reporting | 2015-09-30 | Complete 4-way recon between Hyperion-FRS-Moody's-Workiva | 2015-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Comprehensive documentation of controls over reporting process (centralized and distributed components) | SOX level control documentation approved | Manuel Munoz | 2015-09-30 | No | Revise process for tax reporting | 2015-09-30 | Revise process for parent reporting | 2015-09-30 | Revise process for reg reporting | 2015-09-30 | Revise process for CCAR reg reporting | 2015-09-30 | Revise process for SEC reporting | 2015-09-30 | Medium | Medium | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Comprehensive documentation of controls over reporting process (centralized and distributed components) | Change management process for SOX level control documentation in place. | Manuel Munoz | 2015-09-30 | No | Coordinate with internal controls (dependency) | 2015-09-30 | [8 empty] | Medium | Medium | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Improve efficiency of Regulatory Report production (Incorporate all legacy systems not completed as part of the original FRS implementation). | FRS source data optimization | Sean Mulcahy | 2015-12-31 | Yes | Enhance FRS: Complete Analysis | Completed | Enhance FRS: Complete Design | 2015-06-30 | Enhance FRS: Complete Development | 2015-09-30 | Enhance FRS: Complete Testing | 2015-10-31 | Enhance FRS: Complete UAT | 2015-12-31 | High | High | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | Inventory of SHUSA (SBNA/SCUSA) critical EUA's | John Moore | 2015-06-30 | Yes | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | High | High | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | Risk Rating of of SHUSA (SBNA/SCIUSA) critical EUA's and prioritized plan for compliance | John Moore | 2015-07-31 | Yes | 0 | 0 | 0 | 0 | [6 empty] | High | High | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | SHUSA (SBNA/SCUSA) critical EUA's remediated | John Moore | 2015-12-31 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | High | High | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Current State Assessment | Mike Boyle | Completed | No | Develop Data Flows (of pain points) from source to report | Completed | [8 empty] | Medium | Medium | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Conduct Quality Gap Assessment | Mike Boyle | Completed | No | Document areas of deficiency | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium | Medium | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Develop Recommendations | Mike Boyle | Completed | No | [10 empty] | Medium | Medium | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Prioritize Data Areas | Mike Boyle | Completed | No | [10 empty] | Medium | Medium | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Roadmap for remediation of Group reporting processes. | Mike Boyle | 2015-06-12 | No | [10 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Revised approach for remediation of data sources for Group reporting processes | Mike Boyle | 2015-09-30 | Yes | Revised approach to data sourcing | 2015-09-30 | [8 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Improve the quality of information in the general ledger needed to complete the chart of accounts and execute reporting | Remediate gaps in feeds from entity GL's | Nancy Reinhard | 2015-11-06 | Yes | 0 | 0 | [8 empty] | 0 | 0 | 0 | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Improve the amount of general ledger information available from direct system feeds rather than manual processes | Hyperion fed from RDA | Ignacio Garijo Garde | 2015-12-31 | Yes | Inventory Manual Processes (SBNA) | TBD | [8 empty] | 0 | 0 | 0 | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Deployment of a uniform reconciliation tool (SHUSA and subsidiaries) | Unifrom Automated reconciliation | John Moore | 2015-12-31 | Yes | Evaluate and select the appropriate reconciliation tool | 2015-08-31 | [8 empty] | 0 | 0 | 0 | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Finalize the implementation of Target Operating Model | Target Operating Model | Ken Goldman | 2015-12-31 | No | Complete Definition of Target Operating Model | 2015-12-31 | [8 empty] | Low | Low | No | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SHUSA adherence to revised accounting policies | Jessie Velazquez | 2015-12-31 | No | Procedures revised at SHUSA | 2015-10-01 | [8 empty] | Medium | Medium | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SBNA adherence to revised accounting policies | M Ballenger | 2015-12-31 | No
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SCUSA adherence to revised accounting policies | J Kulas | 2015-12-31 | No | Procedures revised at SCUSA | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SCUSA | 2015-11-30 | 0 | 0
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | BSI adherence to revised accounting policies | E Franco Espinosa | 2015-12-31 | No | Procedures revised at BSOI | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at BSI | 2015-11-30 | 0 | 0
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | PR adherence to revised accounting policies | A. Guzman | 2015-12-31 | No | Procedures revised at PR | 2015-10-01 | [8 empty] | Medium | Medium | Yes
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SIS adherence to revised accounting policies | F. Sempre | 2015-12-31 | No | Procedures revised at SIS | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SIS | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | #REF!
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Other IHC entities adherence to revised accounting policies | Jessie Velazquez | 2015-12-31 | No | Procedures revised at Other Entities | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at Other Entities | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | #REF!
Finance Transformation | Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Enhance SHUSA Capital policy | Bart Simon | 2015-12-31 | No | Governance: -Enhance the roles and responsibilities of the Board members, senior management and auxiliary functions -Prescribe more specific governance including approval hierarchy and committees for subsidiary capital decisions -Policy Board approval, including all milestones for this deliverable | 2015-12-31 | Capital goals and targets methodology : - At sub level ID and quant critical stakeholder requirements in stress - Enhance study of experience in stress - Determine capital goals at each sub & analysis impact of changes at subs on SHUSA -Include analysis for each entity and document the associated loss absorbency at the subsidiary and the consolidated capital position. A key focus of the analysis will include management’s evaluation of the SCUSA minority interest within consolidated capital - Improve alignment between the risk identification process and target setting --Develop analysis to demonstrate how the post-stress minimum will support the target debt rating in stress and allow each entity to maintain funding plans and actions -Consider liquidity risk management strategies and metrics in identifying capital goals -Document impact of modifications to strategies or metrics on changes to capital goals on a dynamic basis -Analyse the impact on the consolidated capital position if all subsidiaries operating at their post-stress minimum -Set capital goals such that the capital required to access capital markets is differentiated from requirements to remain a going concern. -Complete analysis of capital required to absorb stress at a subsidiary level and demonstrate how those directly build to the consolidated stress absorption buffer -Include procedures to consider changes to the composition and inherent risks on the balance sheet to update capital targets on a dynamic basis | 2015-09-05 | Capital assessment methodology: - Enhance doc of process & responsibilities & deliverables - ID specific analysis (ratios, changes in biz profile, strategic initiatives, risk tolerance metrics, etc.) required for assessment - Develop draft of capital assessment report (companion to current deck) -Present capital assessment and deployment report each quarter at operating entities -Clarify the linkage between the capital assessment and the capital ratio forecasts under different scenarios as well as time horizons | 2015-09-05 |  |  |  |  | Medium | Low | No | #REF!
Finance Transformation | Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Enhance SHUSA Capital contingency policy | Bart Simon | 2015-12-05 | No | Incorporate FRS and IA feedback into existing draft policy - Align capital contingency process with updated capital policy methodology documents - Include 'capital triggers' analysis | 2015-11-30 | Develop appropriate governance over capital contingency process across entities. | 2015-12-02 | Deliver contingency policy to policy admin | 2015-11-30 |  |  |  |  | Medium | Low | No | #REF!
Finance Transformation | Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Capital Policies for subs (SBNA, SCUSA and IHCs) commensurate with size / complexity | Bart Simon | 2015-12-31 | No | Establish capital management governance structure at each entity | TBD | Capital goals and targets methodology document - ID and quant critical stakeholder requirements in stress - Enhance study of experience in stress - Risk Inventory from Risk ID w/ quant source - Roles & Responsibilities | 2015-09-05 | Dividend and capital action methodology document - ID all metrics and analysis required to develop 'capital triggers' - Compile data required for analysis of indicators that could drive changes to capital actions - Determine roles & responsibilities for analysis - Determine governance/communication expectations | TBD |  |  |  |  | Medium | Medium | Yes | #REF!
Finance Transformation | Capital Management | Operationalize processes for escalation to board, potential suspension of capital actions, and implementation of contingency plans (improve analysis and documentation of contingency actions) | Enhance/Update Contingent Capital Plan | Bart Simon | 2016-04-05 | No | Re-define process for which contingent actions are identified, quantified and assessed | 2015-10-15 | Update inventory of potential contingent capital actions | 2015-10-30 | Align potential contingent capital actions with liquidity, strategic planning, & resolution planning (dependencies…) | 2015-10-15 |  |  |  |  | Medium | Low | No | #REF!
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Improved quality of information presented | Simon / Watson | 2015-09-30 | No | Establish team for template creation and population | TBD | Create common templates | TBD | Develop process for review of content prior to presentation | TBD |  |  |  |  | High | High | Yes | #REF!
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Improve completeness of info presented | Simon / Watson | 2015-12-31 | No | Review final structures to determine 'new' reporting expectations and locations | TBD | Develop full inventory of models and processes for review | TBD | Develop full inventory of results for review | TBD | Schedule and track review of inventories at appropriate level of governance body | TBD |  |  | Low | Medium | No
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Add clarity to material provided for consideration of dividend | Bart Simon | 2015-12-31 | No | See SHUSA Capital Policy for details | TBD | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Enhance Board and Snr. Management Training | Simon / Watson | 2015-12-31 | No | Outline required training at Board and Senior Management | TBD | Schedule training | TBD | Determine training provider (internal / external) | TBD | 0 | 0 | 0 | 0 | Low | Low | Yes
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Detailed Procedures for E2E processes | Bart Simon | 2015-12-31 | No | Determine review governance / review process for E2E procedures | TBD | Confirm E2E process map owners and responsibilities for procedures | TBD | First draft of procedures for all E2E process steps | TBD | Central review of draft procedures | TBD | 0 | 0 | High | Medium | Yes
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Establish clear accountabilities | TBD-McKinsey to provide dates | TBD | No | This needs to be part of the 'bigger' Governance discussion. | TBD | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Establish staffing and conduct adequate training across the end-to-end CCAR review cycle | Establish Staffing & Conduct Training - TBD | TBD-J. Watson to provide dates | TBD | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Establish set of reconciled as-of and clean historical data | IT/IMAD | TBD | Yes | Complete gap assessment against data quality | TBD
Finance Transformation | Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Develop end-to-end stress-testing platform | TBD | TBD | Yes | Develop BHC specific Scenarios that are clearly linked to the RISK ID process and that are BHC specific | TBD | Develop model execution platform (for PPNR, Credit Loss, etc.) | TBD | Develop SAS balance-walk engine | TBD |  |  |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Base and stress forecasts for each IHC entity | TBD | TBD | No | Communicate modeling strategy | TBD | Develop forecasting processes for non-modeled line-items (PPNR) | TBD | Develop forecasting processes for non-modeled line-items (Credit) | TBD | Develop supporting documentation | TBD |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Detailed E2E processes maps | Bart Simon | 2015-12-31 | No | Build team for compilation of E2E process maps | TBD
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Comprehensive Assessment from Internal Audit | Vik Soni | 2016-03-31 | No
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Comprehensive Assessment from Internal Controls | M. Munoz | 2015-12-31 | No | 0 | 0 | 0 | 0 | 0 | 0
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Model Validation / MRM | TBD | TBD | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Increase the granularity of forecasting of on and off balance sheet product level information. This process will be extended to include all material IHCs for CCAR 2016 inclusion | John Barris | 2015-11-30 | No | Management Control/Strategic Planning build out SAS forecasting models | 2015-09-30 | SAS Models validated | 2015-12-31 | GAP level of forecasts with RWA needed levels | 2015-10-30 | Develop any methodologies or assumptions for gaps and obtain governance approvals | 2015-12-31 | 0 | 0 | Medium | Low | No
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Finalization of the Basel III methodology that is approved and fully documented and Forecasting methodology that is consistent with the final approved SHUSA Basel III methodology | John Barris | 2015-07-06 | No | RCRD/Accounting to produce final Basel III methodology for numerator and denominator | 2015-04-01 | CPG to incorporate final Basel III methodology into forecasting | 2015-07-06 | Update forecasting documentation obtain final approval | 2015-07-06 |  |  |  |  | Medium | Medium | No
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Internal Audit to review the RWA methodology for both actuals and forecasts for CCAR 2016 | John Barris | 2015-12-31 | No | Review of Actual methodology for RWA | 2015-06-01 | Review of forecasting methodology for Forecasting | 2015-12-31 | 0 | 0 | 0 | 0
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | RWA methodology will be well documented and all assumptions will be approved by the appropriate governance committees prior to use, including validated SSFA methodology developed and run by 3rd party external vendor | John Barris | 2015-12-31 | No | Obtain approval for SSFA 3rd Party Vendor | 2015-07-31 | Vendor to develop methodology with CPG | 2015-09-30 | MRM to validate SSFA models | 2015-12-31 | Provide Cusips and produce results | 2016-03-01 | 0 | 0
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Implement a framework for RWA sensitivity analysis and back testing for CCAR 2016 that is well documented | John Barris | 2016-04-04 | No | Develop necessary analysis and back testing needs | 2015-09-30 | Gap needs to abilities | 2015-10-30 | Develop plan for analysis and back testing for CCAR 2016 | 2015-12-31 | Document results of analysis and back testing | 2015-04-04 | 0 | 0
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | RWA process will be reviewed and tested by internal controls for CCAR 2016 | John Barris | 2016-03-31 | No | Work with IC to produce necessary RWA control framework | 2015-07-30 | Add controls into the RWA process as outlined | 2015-12-31 | Produce RWA for CCAR 2016 | 2016-04-04 | IC to conduct control test | 2016-05-30 |  |  | Low | Low | No
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Review of Previous Capital Plan with comments on areas for improvement | Bart Simon | 2015-06-01 | No
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Consolidated and legal entity historical results in Planning Tree delivered | TBD | TBD | Yes
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Strategic plan at consolidated and legal entity in Planning Tree | D. Budington | TBD | Yes
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Baseline and Stress at consolidated and legal entity in Planning Tree | John Barris | TBD | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | High | High | Yes
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Financial analysis in Capital Plan | John Barris | TBD | Yes | Determine roles and review expectations | TBD | Establish "team" for review | TBD | Preplan all charts graphs | TBD |  |  |  |  | Medium | Medium | Yes | #REF!
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Develop / Enhance Monthly Report | John Barris | TBD | No | Gap Current Report to Management Needs | TBD | Develop remediation plan for executions | TBD | [6 empty] | 0 | 0 | 0
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Align to GL and RCRD | John Barris | TBD | Yes | Integrate Proforma forecast for monthly cycle | 2015-04-01 | Align to GL through Essbase | TBD | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Enhance with Current Capital LOB Allocations | John Barris | TBD | No | Integrate LOB allocations into report | TBD | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Develop forecasting ability with Stress overlays | John Barris | TBD | No | Develop process to use monthly actuals to true up forecast | TBD | Develop methodology to overlay CCAR/Mid Cycle stress impacts | TBD | Finalize Reporting format and governance approval | TBD | 0 | 0 |  |  | 0 | 0 | 0
Finance Transformation | Capital Management | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements | Quarterly Decks for MCC | Bart Simon | 2016-04-06 | No | Q1 Deck | 2015-06-25 | [8 empty] | Low | Low | No
Finance Transformation | Capital Management | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements | Quarterly Report for Board | Bart Simon | 2016-04-06 | No
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Review 2014 Capital Plan | Bart Simon | 2015-06-01 | No
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Align results & methodology presentation with 'new' segmentation | Bart Simon | 2015-09-30 | Yes | [10 empty] | High | High | No
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | IHC Capital Plan | Bart Simon | 2016-04-04 | No | Create Project Plan for each entity: SBNA, SCUSA, Miami, NY, Puerto Rico | 2015-07-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | High | High | Yes
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Methodology Appendix for Capital Plan | Contributors | 2015-12-31 | No | Contributors Draft/Revise Methodology Sections | 2015-08-01 | Improve existing summary documentation in Capital Plan in workiva per ROPE | 2015-08-01 | Review Team - Capital Management, Working Groups, Peer Review | 2015-12-31
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Results for CCAR Run | Contributors | 2016-03-20 | No | Contributors Draft/Update Results for CCAR Run | 2016-03-10 | Improve existing summary documentation in Capital Plan in workiva per ROPE | 2016-03-10 | [9 empty] | #REF!
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Enhance Capital Plan Documentation | Bart Simon | 2016-03-20 | No | Improve automation / linkage to wDesk | 2016-03-20
Finance Transformation | Capital Management | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board | Procedures for developing and review of alternative capital actions | Bart Simon | 2015-12-31 | No | Determine Roles & Responsibilities | TBD | Determine Governance | TBD | 0 | 0
Finance Transformation | Capital Management | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board | Alternative Capital Actions | Bart Simon | 2016-04-04 | No | Execute process to develop alternative capital actions | TBD | Review alternative actions w/ appropriate governance bodies | TBD | Include alternative actions in 2016 Capital Plan | TBD | 0 | 0 |  |  | Low | Low | No
Finance Transformation | Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Develop, document and test customized SAS forecast and aggregation tool | D. Budington | 2015-10-09 | Yes | Define preliminary data requirements for forecast execution (based on 2015 CCAR process) | 2015-04-15 | Design customized SAS forecast and aggregation tool, including detailed specification of capabilities and hand-offs | 2015-05-15 | Build customized SAS forecast solution, including initial testing and sign-off of capabilities and design | 2015-06-30 |  |  |  |  | 0 | 0 | 0
Risk Transformation |  | Re-design SHUSA RAS | SHUSA RAS reporting and breach escalation processes | Edward Smith | 2015-08-10 | No | Draft RAS |  | Final RAS |  | Draft process |  | Final process |  |  |  | High | Low | Yes
Risk Transformation |  | Re-design SHUSA RAS | SHUSA-level RAS | Edward Smith | 2015-08-10 | Yes | Delivery of training | [9 empty] | Medium | Low | Yes
Risk Transformation |  | Re-design SHUSA RAS | Board approval for SHUSA RAS | Edward Smith | 2015-09-07 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Re-design SHUSA RAS | RAS business and data requirements | Edward Smith | 2015-09-25 | Yes | Draft of materials |  | Final materials and delivery of communication | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Re-design SHUSA RAS | Board-level RAS communications | Edward Smith | 2015-09-25 | No | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Low | No
Risk Transformation |  | Cascade RAS to priority subsidiaries | RAS for priority subsidiaries (SBNA & SCUSA) | Edward Smith | 2015-11-06 | Yes | Draft approach |  | Final approach | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Cascade RAS to priority subsidiaries | Delivery of enterprise-level RAS comms. & socialization materials | Edward Smith | 2015-12-28 | No | Draft RAS for priority subs and list of metrics |  | Input from subs |  | Final RAS for priority subs and list of metrics | [5 empty] | High | Low | Yes
Risk Transformation |  | Initialize embedding of RAS in material processes | Updated process maps for key processes with explicit RAS links | Edward Smith | 2015-11-27 | No | Draft process |  | Final process | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Board risk committee training | Board risk training curriculum and schedule | Edward Smith | 2015-07-27 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Board risk committee training | Board risk training sessions delivered - e.g. RAS | Edward Smith | 2015-09-28 | No | Draft of training materials, including training schedule |  | Final training materials, including training schedule |  | Delivery of two training sessions | [5 empty] | Medium | Low | Yes
Risk Transformation |  | Board risk committee training | Board risk training sessions delivered - e.g. CCAR Governance | Edward Smith | 2015-11-30 | No | Key stakeholder engagement |  | Draft governance and coordination mechanisms |  | Final governance and coordination mechanisms | [5 empty] | High | Medium | Yes
Risk Transformation |  | Strengthen SHUSA Board / Mgt. Committee guidance | Diagnostic of Risk Mgt. Committee (includes relationship with parent) | John Hennessey | 2015-06-29 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Strengthen SHUSA Board / Mgt. Committee guidance | Definition of composition / mandates / charters for priority committees | John Hennessey | 2015-09-28 | No | Group approval | [9 empty] | Medium | Medium | Yes
Risk Transformation |  | Strengthen SHUSA Board / Mgt. Committee guidance | Board approval for high priority committee changes | John Hennessey | 2015-09-28 | No | Draft of diagnostic materials |  | Final materials and delivery of diagnostic | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Strengthen SHUSA Board / Mgt. Committee guidance | Definition of composition / mandates / charters for remaining committees | John Hennessey | 2015-12-28 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Risk Transformation |  | Strengthen SHUSA Board / Mgt. Committee guidance | Board approval for low priority committee changes | John Hennessey | 2015-12-28 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Change & enforce Risk Leadership reporting lines | Updated Risk leadership reporting lines | John Hennessey | 2015-06-15 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Risk Transformation |  | Change & enforce Risk Leadership reporting lines | Board-approved Risk leadership organization | John Hennessey | 2015-06-29 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Articulate 3 LoD across SHUSA-subsidiary relationships | Board-approved SHUSA frameworks | John Hennessey | 2015-07-27 | No | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Risk Transformation |  | Articulate 3 LoD across SHUSA-subsidiary relationships | Cascaded SHUSA frameworks to subsidiaries | John Hennessey | 2015-09-28 | Yes | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Risk Transformation |  | Articulate 3 LoD across SHUSA-subsidiary relationships | Standardized policies and procedures, aligned to new frameworks for key risk types | John Hennessey | 2015-12-28 | No | Draft 3LoD principles |  | Final 3LoD principles | [7 empty] | Low | Low | Yes
Risk Transformation |  | Design Risk management organizational structures & staffing | Operating model design including headcount analysis | John Hennessey | 2015-08-03 | No | Draft reporting lines |  | Key stakeholder engagement |  | Final (formalization of) reporting lines | [5 empty] | Low | Low | Yes
Risk Transformation |  | Design Risk management organizational structures & staffing | Recruitment of senior Risk and other high priority staff | Kerrie Maitland | 2015-11-30 | No | Board approval | [9 empty] | Medium | Low | Yes
Risk Transformation |  | Detail interactions between risk groups for critical processes | Interaction definition | John Hennessey | 2015-10-03 | No | Draft of operating model |  | Final operating model | [7 empty] | High | Medium | Yes
Risk Transformation |  | Detail interactions between risk groups for critical processes | Critical processes updated | John Hennessey | 2015-09-14 | No | Draft headcount |  | Delivery of skills / staffing assessment |  | Hiring / redeployment strategy | [5 empty] | High | Medium | Yes
Risk Transformation |  | Talaent management | Perform a talent review and assessment of key risk staff and develop a strategy to address gaps (e.g. hiring, training, leadership programs, etc.) and begin rolling out hiring strategy to fill staffing gaps | John Hennessey | TBC | No | Draft of communication and training materials for enterprise-wide communication |  | Delivery of final communication and training materials for enterprise-wide communication |  | Development of job descriptions |  | Delivery of enterprise-wide training |  |  |  | High | Medium | Yes
Risk Transformation |  | Talaent management | Articulation of a strong and desired risk culture and creation of risk communication forums (e.g. intranet, Risk Town Halls, etc.) | John Hennessey | TBC | No | Validation of updated frameworks | [9 empty] | Low | Low | No
Risk Transformation |  | Enhance Risk ID and Assessment process | Documentation of top-down risk aggregation | Edward Smith / Diane Allaire | 2015-06-29 | No | Board approval | [9 empty] | Low | Low | No
Risk Transformation |  | Enhance Risk ID and Assessment process | Framework to identify material risks, including tools, templates, risk taxonomy, guidance, policies and procedures | Edward Smith / Diane Allaire | 2015-07-27 | No | Draft of assessment |  | Delivery of assessment |  | Prioritization of enhancements |  | Final plan for enhancements, given stakeholder input |  | Standardization of all policies / procedures |  | Medium | Low | No
Risk Transformation |  | Enhance Risk ID and Assessment process | Definition of risk ID foundational elements, multi-year enhancement goals | Edward Smith / Diane Allaire | 2015-09-07 | No | Draft definition of risk ID/assessment process and plan for execution |  | Final definition of risk ID/assessment process and plan for execution |  | Communication to key stakeholders | [5 empty] | Low | Medium | No
Risk Transformation |  | Enhance Risk ID and Assessment process | Clear linkages established between Risk ID output to capital planning scenario generation process | Edward Smith / Diane Allaire | 2015-11-01 | No | Board approval | [9 empty] | Low | Low | No
Risk Transformation |  | Enhance Risk ID and Assessment process | Risk ID / Assess. business and data requirements, drawing upon process to create risk register | Edward Smith / Diane Allaire | 2015-11-01 | Yes | Conduct bottom-up risk identification |  | Aggregate, review & challenge |  | Conduct top-down risk identification |  | Draft of risk register |  | Final risk register |  | High | High | Yes
Risk Transformation |  | Enhance Risk ID and Assessment process | Risk register for modeled and non-modeled risk with reporting to Board and Snr mgt. | Edward Smith / Diane Allaire | 2015-11-01 | Yes | Draft policy and procedures for risk ID and assessment cycle |  | Final policy and procedures for risk ID and assessment cycle |  | Communication of policies/procedures to key stakeholders | [5 empty] | Medium | Low | No
Risk Transformation |  | Conduct high level of credit risk management | High level wholesale credit process review incl. limits / controls and DoA at SCUSA and SBNA | TBD | 2015-11-15 | No | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Medium | No
Risk Transformation |  | Conduct liquidity risk gap analysis | Definition of target liq. risk capabilities, current state review and remediation plan | TBD | 2015-12-14 | No | Proposed recommendations |  | Approved recommendations |  | Updated Credit Policy | [5 empty] | Medium | Medium | Yes
Risk Transformation |  | Enhance internal reporting | Assessment of current reporting landscape with quick win enhancements | Edward Smith | 2015-06-29 | No | Draft framework |  | Final framework | [7 empty] | Medium | Medium | Yes
Risk Transformation |  | Enhance internal reporting | Definition of target risk reporting landscape | Edward Smith | 2015-08-10 | Yes | Definition of liquidity risk capabilities |  | Current state vs. capabilities |  | Remediation plan | [5 empty] | Medium | Medium | Yes
Risk Transformation |  | Enhance internal reporting | Template reports and socialization of high priority reports | Edward Smith | 2015-09-21 | No | Initial review of risks |  | Scenario and impact analysis |  | Remediation plan |  | Business and data requirements |  |  |  | TBD | TBD | Yes
Risk Transformation |  | Enhance internal reporting | Operationalization of high priority reports e.g. allocate reporting resources | Edward Smith | 2015-11-15 | Yes | Initial review of framework |  | Process and associated tools |  | Documented decision authority |  | Business and data requirements |  |  |  | TBD | TBD | Yes
Risk Transformation |  | Enhance internal reporting | Template reports and socialization of low priority reports | Edward Smith | 2015-12-28 | No | Risk reporting landscape outline | [9 empty] | Low | Low | Yes
Operational Risk | Risk Appetite | Simplify SHUSA Operational Risk Tolerance Statement Limits | Enhanced SHUSA operational risk limits implemented, monitored and reported | Sean O'Malley |  | No | A documented set of recommended enhanced operational risk limits with clear rationale, definitions and thresholds |  | SHUSA Board-approved enhanced operational risk limits and thresholds. |  | Implemented processes to effectively monitor and report on enhanced operational risk limits. | [5 empty] | High | Medium | No
Operational Risk | Risk Appetite | Align with Capital Measures described in the Basel Consultative document (Total Potential OR Losses as a % of Gross Income, Single OR Loss Event > $10MM) | Enhanced SHUSA operational risk limits implemented, monitored and reported | Sean O'Malley |  | No | A documented set of recommended enhanced operational risk limits with clear rationale, definitions and thresholds |  | SHUSA Board-approved enhanced operational risk limits and thresholds. |  | Implemented processes to effectively monitor and report on enhanced operational risk limits. | [5 empty] | High | Medium | No
Operational Risk | Governance & Organization | Determine OR organizational structure between SHUSA and Subsidiaries | Approved short term (year 1) operational risk management operating model for SHUSA and it subsidiaries | Steve Bhatti |  | No | A documented, recommended short term (year 1) operational risk management operating model for SHUSA and it subsidiaries including roles and responsibilities clearly defined using the RACI method | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Determine OR organizational structure between SHUSA and Subsidiaries | Approved medium term (years 2/3) operational risk management operating model for SHUSA and its subsidiaries | Steve Bhatti |  | No | A documented, recommended medium term (years2/3) operational risk management operating model for SHUSA and its subsidiaries including roles and responsibilities clearly defined using the RACI method | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Determine and select short-term / medium-term resource requirements (internal and external) to deliver Year 1/2/3 priorities | Approved operational risk management staffing assessment for both the short term (year 1) and medium term (years 2/3) operating models | Steve Bhatti |  | No | Documented results from an operational risk management staffing assessment for both the short term (year 1) and medium term (years 2/3) operating models | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Recruit and onboard necessary talent | Active recruitment of SHUSA ORM staff for short term (year 1) operating model | Steve Bhatti |  | No | Initial recruitment for SHUSA ORM based on the short term (year 1) operating model | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Recruit and onboard necessary talent | Active recruitment of SHUSA subsidiaries ORM staff for both 1st and 2nd lines of defense for short term (year 1) operating model | Steve Bhatti |  | No | Initial recruitment for all SHUSA subsidiares ORM 1st and 2nd lines of defense based on the short term (year 1) operating model | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Establish a SHUSA Operational Risk Management Framework (Develop ORM principles, 3 LoD roles and responsibilities, SHUSA ORM organizational structure, ORM ERM methodology) | SHUSA Operational Risk Framework approved by SHUSA BERC | Brian McVane |  | No | A draft SHUSA Operational Risk Management Framework |  | Socialized Framework with obtained acknowledgement by CRO's and 1st line of defense with acknowledgement of roles and responsibilities |  | Obtained approval from SHUSA BERC | [5 empty] | High | Low | No
Operational Risk | Governance & Organization | Perform gap analysis of policy inventory in line with regulatory guidance supporting SHUSA policy requirements | Completed mapping of all operational risk management enterprise policies and regulatory requirements in a tool | Brian McVane |  | Yes | Tool selected |  | Tool implemented |  | Obtained authoritative sources for regulatory requirements |  | Uploaded regulatory and policy requirements into tool |  |  |  | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Operational Risk Management Policy | Brian McVane |  | No | Updated operational risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for operational risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Information Risk Management Policy | Brian McVane |  | No | Updated information risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Information Risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Third Party Risk Managment Policy | Brian McVane |  | No | Updated Third Party risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Third Party Risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Business Continuity & Disaster Recovery Policy | Brian McVane |  | No | Updated Business Continuity & Disaster Recovery risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Business Continuity & Disaster Recovery enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Gap analysis to identify training needs for staff of SHUSA and Subsidiaries with respect to SHUSA enterprise Ops Risk policies and standards | Documented operational risk management knowledge/skill assessment to inform initial training requirements | Brian McVane |  | No | Developed centralized, criterion based operational risk management knowledge/skill assessment for SHUSA and its subsidiary 2nd LoD |  | Completed operational risk management knowledge/skill assessment | [7 empty] | Medium | High | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved operational risk management standards and communication strategy | Brian McVane |  | No | Creation of operational risk management Standards Inventory |  | Drafted operational risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved information risk management standards and communication strategy | Brian McVane |  | No | Creation of information risk management Standards Inventory |  | Drafted information risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved third party risk management standards and communication strategy | Brian McVane |  | No | Creation of third party risk management Standards Inventory |  | Drafted third party risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved business continuity and disaster recovery standards and communication strategy | Brian McVane |  | No | Creation of business continuity & disaster recovery Standards Inventory |  | Drafted business continuity & disaster recovery standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Risk Identification & Measurement | Establish the process to enforce and improve the identification and management of open issue and remediation efforts | SHUSA known issues are reflected in an issues management tool enhancing issue governance and management. | Sean O'Malley |  | No | Enterprise issue management process ownership and oversight centralized within SHUSA Operational Risk |  | A documented process/standard to improve the centralization of issue management. | [7 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Implement the issue management tool for the identification, capture and management of issues | SHUSA known issues are reflected in an issues management tool enhancing issue governance and management. | Sean O'Malley |  | Yes | Issue management tool selected |  | Issue management tool implemented |  | Completed data migration of all known issues into an issue management tool | [5 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Documented analysis of material event thresholds for peer institutions (primarily SBNA peers) | Sean O'Malley |  | No | Completed peer review of event escalation thresholds with results and recommendations for threshold modifications (if applicable) documented | [9 empty] | Low | Low | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Document of strategic mitigation program to be completed in collaboration with 1st Line of Defense | Sean O'Malley |  | No | Documented strategic mitigation program designed to address material operational risk event root causes | [9 empty] | Low | Low | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Documented analysis of material event back-testing | Sean O'Malley |  | No | A documented plan for back testing related to material operational risk events to ensure data is complete, accurate and timely. | [9 empty] | Low | Low | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review, evaluate and select RCSA methodology based on industry standards | RCSA Methodology document | Sean O'Malley |  | No | Develop an RCSA methodology |  | Approved RCSA methodology (through appropriate governance) | [7 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Review, evaluate and select RCSA methodology based on industry standards | Documented approval (ORC meeting minutes) for RCSA methodology | Sean O'Malley |  | No | Develop an RCSA methodology |  | Approved RCSA methodology (through appropriate governance) | [7 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Evaluate Scenario Analysis Tools and Processes | Documentation of discussion points raised in Scenario Analysis workshops and loss estimates based on subjective results (SHUSA and Subsidiaries) | Sean O'Malley |  | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries | [9 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Evaluate Scenario Analysis Tools and Processes | Scenario analysis Methodology document | Sean O'Malley |  | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries | [9 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Complete scenario analysis program for SHUSA and Subsidiaries | Scenario analysis Methodology document | Sean O'Malley |  | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries |  | Provide documented methodology of scenario analysis in line with regulatory standards | [7 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Complete CCAR OR Loss Estimates | ORM Loss Estimation Methodology document | Sean O'Malley |  | No | Provide documented methodology of ORM Loss Forecasting in line with regulatory standards | [9 empty] | High | High | Yes | 3rd Party & Internal
Operational Risk | Risk Identification & Measurement | Refine operational risk loss forecasting model - Internal/External Loss Data Tools and Processes | Complete Y14A submission for CCAR 2016 | Sean O'Malley |  | Yes | A completed submission of operational risk loss estimates for CCAR (Y14A) | [9 empty] | High | High | Yes | 3rd Party & Internal
Operational Risk | Risk Identification & Measurement | Improve manual processes for OR Loss Event/Incident identification and collection | Documentation for OR Loss Event/Incident identification and capture across SHUSA and Subsidiaries (working with 1st Line of Defense) | Sean O'Malley |  | Yes | Produce documented changes to OR Loss Event/Incident identification and collection process that increase the level of automation | [9 empty] | High | High | Yes | 3rd Party & Internal
Operational Risk | Risk Identification & Measurement | Refine methodology to focus on emerging threats and vulnerabilities | IRM Gap analysis | Geoffrey Hauge |  | No | Created IRM Risk Assessment cross entity working group |  | Kickoff IRM Risk Assessment gap analysis across regulatory guidance and industry standards |  | Completed Analysis for the IRM Risk Assessment | [5 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Refine Third Party Inherent Risk Classification methodology to determine scope and frequency of third party reviews | Documented methodology for third party inherent risk classification | Gregory Hamilton |  | Yes | A documented Third Party Inherent Risk Classification methodology |  | Rollout for the Third Party Inherent Risk Classification methodology completed for SHUSA entities | [7 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Complete the new Inherent Risk Classification questionnaire for critical third party services | Updated inherent risk classifications for all critical third party services | Gregory Hamilton |  | Yes | Inherent risk classifications completed for all critical third party services of SHUSA entities | [9 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Perform onsite reviews for all critical third parties (scope/frequency will be driven by inherent risk questionnaire) | Onsite schedule for critical third parties. Critical third party assessment final reports. | Gregory Hamilton |  | Yes | Completed onsite reviews for a selection of critical third parties based on results of inherent risk classifications | [9 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review for program changes as a result of regulatory and SHUSA Policy changes | Business Continuity Management Policy -- review and enhance existing policy; Working individually with each subsidiary: | Danny Phillips |  | No | Finalized BCM policy for submission through approval process and distribute to all subsidiaries (see Enhance Ops Risk Policies for governance); | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Identification & Measurement | Review and refine existing Business Impact Analysis (BIA) of SBNA and SCUSA | Complete review of existing SBNA and SCUSA BIAs supporting SHUSA and subsidiary teammates: -- identify critical processes; -- to investigate and update in existing BIAs where applicable; | Danny Phillips |  | Yes | Completed review of existing BIAs and current dependencies for SBNA and SCUSA entities | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Identification & Measurement | Identify gaps from current BIAs for SBNA and SCUSA critical processes, applications and testing | - Review 2014 - 2015 SBNA and SCUSA BCM (BR and DR) testing reports: -- identify issues and remediations completed and pending: -- identify responsible teams for issues and remediations; | Danny Phillips |  | Yes | Conducted BCM (BR and DR) of testing reports from 2014 to 2015 to identify all existing/pending, closed issues and remediation for SBNA and SCUSA | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Identification & Measurement | Review existing exercise results for each SBNA and SCUSA | Consolidate gap analysis report for SBNA and SCUSA of critical processes, -- critical applications, and testing for all subsidiaries: -- identify potential Risks; | Danny Phillips |  | Yes | Completed and consolidated a gap analysis against critical processes, critical applications and testing results for SBNA and SCUSA | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Management | Strengthen aggregated operational risk reporting to allow the SAN US/SHUSA Operational Risk Committee to better fulfill its obligation to oversee and manage the identification and monitoring of operational risks as well as to escalate risks/issues that need ERMC/BERC/Board transparency. (Establish baseline operational risk management reporting and dashboards for SHUSA and its subsidiaries including (1) a standard set up summary risk data such as RTS limits, risk profile, top risks, emerging risks, material events and program updates, (2) a standard set of risk data specific to operational risk, information risk, third party risk and business continuity) | Established operational risk dashboards, including risk data for ORM, IRM, TPRM and BCM, for SHUSA and its subsidiaries are included in monthly governance reporting. | Brian McVane |  | No | SHUSA operational risk management reporting framework is communicated to all subsidiaries |  | SHUSA defined processes and tools are utilized to support monthly operational risk reporting |  | SHUSA subsidiaries are producing operational risk reporting in line with SHUSA operational risk management requirements | [5 empty] | Medium | Medium | Yes
Operational Risk | Risk Monitoring | Develop timely reporting mechanisms and processes to satisfy OR Y-14Q reporting requirements | Completed automation of data collection for initial phase | Sean O'Malley |  | Yes | "Golden Source" repository populated with data for initial phase | [9 empty] | High | High | Yes | 3rd party & internal
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Material | Pete W. | 2015-08-31 | No | Presentation material drafted | 2015-08-31 | Presentation material reviewed and approved | 2015-08-31 | [6 empty] | High | Low | Yes
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Schedule (if beyond SHUSA) | Pete W. | 2015-08-31 | No | Presentation schedule drafted | 2015-08-31 | Presentation schedule reviewed | 2015-08-31 | Presentation Schedule published | 2015-08-31 |  |  |  |  | Low | Low | No
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Confirmation (Board Minute) | Pete W. | 2015-09-30 | No | Conduct Initial SHUSA Board Presentation | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Board Presentation Plan | Pete W. | 2015-09-30 | No | Build long term Board Presentation Plan (including Entities) | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role | Updated charters for BERC, ERMC, EMC and MRMC | Pete W. | 2015-08-31 | No | Updates to charters drafted | 2015-08-31 | Reviewed and finalized BERC, ERMC, EMC and MRMC committee charters with updates to strengthen MRM oversight and roles and responsibilities | 2015-08-31 | [6 empty] | High | High | Yes
Model Risk Management |  | Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role | Charter Approval (Board Minute) | Pete W. | 2015-09-30 | No | Revised charters approved | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Develop model risk workstream (CART) reporting, governance, controls | Requirements for model risk workstream (CART) reporting, governance, controls | Greg T. | 2015-07-31 | No | Requirements for enhanced model risk remediation reporting, governance and control drafted | 2015-06-30 | Requirements for enhanced model risk remediation reporting, governance and control reviewed and approved | 2015-07-31 | [6 empty] | Medium | Medium | No
Model Risk Management |  | Develop model risk workstream (CART) reporting, governance, controls | Reporting templates, communication plan and calendar(cadence) | Greg T. | 2015-07-31 | No | Reporting templates, communication plan and calendar(cadence) drafted | 2015-07-31 | [8 empty] | Medium | Low | No
Model Risk Management |  | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | Requirements for enhanced model risk BAU reporting | Pete W. | 2015-08-31 | No | Requirements for enhanced model risk BAU reporting drafted (MRMC, Model Risk to BERC/ERMC, etc.) | 2015-07-31 | Requirements for enhanced model risk BAU reporting approved | 2015-08-31 | [6 empty] | Medium | Medium | No
Model Risk Management |  | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | BAU Reporting templates, Frequency(Cadence) , Communication Plan (Who gets what level of detail) | Pete W. | 2015-08-31 | No | Reporting templates, communication plan and calendar(cadence) drafted | 2015-08-31 | Reporting templates, communication plan and calendar(cadence) approved | 2015-08-31 | [6 empty] | Medium | Medium | Yes
Model Risk Management |  | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | MRMC Committee deck, BERC/ERMC submission | Pete W. | 2015-09-30 | No | Implemented Enhanced reporting | 2015-09-30 | [8 empty] | Medium | Medium | Yes
Model Risk Management |  | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Long term Model inventory and reporting system requirement | Pete W. | 2015-09-30 | Yes | Requirements for long term Model inventory and reporting system drafted | 2015-09-30 | Requirements for long term Model inventory and reporting system approved | 2015-09-30 | [6 empty] | High | High | Yes
Model Risk Management |  | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Vendor selection criteria and approach | Pete W. | 2015-10-31 | No | Vendor selection criteria and process drafted/approved | 2015-10-31 | [8 empty] | Low | Low | No
Model Risk Management |  | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Vendor SOW; documented Minutes of decision (per VRM committee) | Pete W. | 2015-11-30 | No | Vendor selection complete | 2015-11-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Hire for known staffing requirements based on volume of validation req'd | Staffing Report | Rafic F. | 2015-12-31 | No | Approval for supplemental FTE headcount | 2015-06-30 | Approval for supplemental consultant/advisory headcount | 2015-06-30 | Onboarding of consulting resources | 2015-07-31 | Hiring of approved incremental FTEs and existing gaps | 2015-12-31 |  |  | Medium | Medium | No
Model Risk Management |  | Define Target Operating model (including org structure) | Operating Model | Edward S. | 2015-07-31 | No | Articulation of 3LoD principles (May) | 2015-05-29 | Formalization of Risk reporting lines at the C-Suite (May) | 2015-05-29 | Risk roles and responsibilities of SHUSA vs. subsidiaries (across each line of defense) | 2015-07-31 | Design of org. structure for each risk type / entity / line of defense | 2015-07-31 | Operating model approved | 2015-07-31 | Medium | Medium | Yes
Model Risk Management |  | Conduct talent and staffing assessment for MRMG | Talent and staffing assessment result/report | Rafic F. | 2015-09-30 | No | Assessment of FTE needs (activity based analysis) | 2015-09-30 | Definition of capabilities needed | 2015-09-30 | Assessment of capabilities of existing staff | 2015-09-30 | Identification of training / upskilling / hiring needs | 2015-09-30 | Talent and staffing assessment complete | 2015-09-30 | Medium | Medium | Yes
Model Risk Management |  | Conduct First Line and auxiliary functions (IT, etc.) staffing assessment (Dependency on Model Development) | Talent and staffing assessment result/report | TBD | 2015-09-30 | Yes | Assessment of FTE needs (activity based analysis) | 2015-09-30 | Definition of capabilities needed | 2015-09-30 | Assessment of capabilities of existing staff | 2015-09-30 | Identification of training / upskilling / hiring needs | 2015-09-30 | First line and auxiliary functions staffing assessment complete | 2015-09-30 | Medium | Medium | Yes
Model Risk Management |  | Develop staffing/hiring strategy (including external resources) and plan based on assessment, backlogs, and workloads | Staffing/Hiring Strategy | TBD | 2015-09-30 | No | All relevant inputs to define staffing/hiring strategy is in place | 2015-09-30 | Staffing/Hiring strategy drafted | 2015-09-30 | Staffing/Hiring strategy approved | 2015-09-30 |  |  |  | 2015-12-31 | Medium | Medium | Yes
Model Risk Management |  | Commence hiring strategy/plan in partnership with the First Line/Model Development | Hiring execution touchpoint cadence | TBD | 2015-12-31 | No | Regular checkpoint on hiring strategy execution drafted | 2015-12-31 | Regular checkpoint on hiring strategy execution reviewed and published | 2015-12-31 | [6 empty] | Low | High | Yes
Model Risk Management |  | Include MRMG specialist in SCUSA pricing governance | Updated SCUSA pricing governance charter | TBD | 2015-07-31 | No | MRMG specialist designated to participate in SCUSA pricing governance | 2015-07-31 | SCUSA pricing governance charter updated to include MRMG specialist | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates | SCUSA retail finance product oversight requirements | TBD | 2015-07-31 | No | Requirements for oversight drafted | 2015-07-31 | Requirements for oversight approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates | Updated relevant charters | TBD | 2015-07-31 | No | List of charters to be updated defined | 2015-07-31 | Relevant charters updates drafted | 2015-07-31 | Relevant charters updates approved | 2015-07-31 |  |  |  |  | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Enhance SCUSA pricing policies and procedures | Updated SCUSA pricing policy | TBD | 2015-07-31 | No | SCUSA pricing policy updates drafted | 2015-07-31 | SCUSA pricing policy updates approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Enhance SCUSA pricing policies and procedures | Updated SCUSA pricing procedures | TBD | 2015-07-31 | No | SCUSA pricing procedures updates drafted | 2015-07-31 | SCUSA pricing procedures updates approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Develop Framework - enhance decision making authority & roles and responsibilities for approving models and model changes (including model retirement) | MRM Framework | Pete W. | 2015-08-31 | No | Framework Drafted | 2015-07-31 | Framework Approved | 2015-08-31 | [6 empty] | High | High | Yes
Model Risk Management |  | Enhance Provisional Approval (PA) process, clarify roles and responsibilities | PA process enhancement requirements | Pete W. | 2015-07-31 | No | Requirements for enhancement for PA process drafted | 2015-07-31 | Requirements for enhancement for PA process approved | 2015-07-31 | [6 empty] | High | Low | No
Model Risk Management |  | Enhance Provisional Approval (PA) process, clarify roles and responsibilities | Updated PA process | Pete W. | 2015-08-31 | No | PA process updates drafted | 2015-08-31 | PA process updates approved | 2015-08-31 | [6 empty] | Medium | Low | No
Model Risk Management |  | Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology | Model Risk rating methodology enhancement requirements | Pete W. | 2015-08-31 | No | Requirements for Model risk rating methodology drafted | 2015-08-31 | Requirements for Model risk rating methodology approved | 2015-08-31 | [6 empty] | High | Low | No
Model Risk Management |  | Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology | Updated model risk rating methodology | Pete W. | 2015-08-31 | No | Enhancement of Model risk rating methodology drafted | 2015-08-31 | Enhancement of Model risk rating methodology approved | 2015-08-31 | [6 empty] | High | Low | No
Model Risk Management |  | Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology | Model tiering methodology enhancement requirements | Pete W. | 2015-07-31 | No | Requirements for Model tiering methodology drafted | 2015-07-31 | Requirements for Model tiering methodology approved | 2015-07-31 | [6 empty] | High | Low | No
Model Risk Management |  | Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology | Updated model tiering methodology | Pete W. | 2015-07-31 | No | Enhancement of Model tiering methodology drafted | 2015-07-31 | Enhancement of Model tiering methodology approved | 2015-07-31 | [6 empty] | High | Low | No
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | SR 11-7 gap analysis | Pete W. | 2015-07-31 | No | SR 11-7 Gap analysis complete | 2015-07-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Updated MRM Policy | Pete W. | 2015-08-31 | No | Policy update based on SR 11-7 gap analysis drafted | 2015-08-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Minutes from MRMC / BERC/ERMC | Pete W. | 2015-09-30 | No | Obtain approval on MRM policy | 2015-09-30 | [8 empty] | High | Medium | No
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | MRM Procedure inventory | Pete W. | 2015-08-31 | No | Updated inventory of procedures based on SR11-7 | 2015-08-31 | [8 empty] | Low | High | Yes
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Updated MRM procedures | Pete W. | 2015-09-30 | No | Obtained MRMC approval of procedures | 2015-09-30 | [8 empty] | High | High | Yes
Model Risk Management |  | Train MRMG staff on the new validation procedures | Training materials approved by CMRO | Pete W. | 2015-09-30 | No | Prepare MRMG materials | 2015-09-30 | [8 empty] | High | Low | No
Model Risk Management |  | Train MRMG staff on the new validation procedures | Record of attendees / signatures | Pete W. | 2015-09-30 | No | Deliver MRMG training | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Enhance training based on updated Policy, Procedures, and Development Standards | Updated training materials | Pete W. | 2015-12-31 | No | Training material for all stakeholders drafted | 2015-12-31 | Training material for all stakeholders approved by CMRO | 2015-12-31 | [6 empty] | High | Medium | Yes
Model Risk Management |  | Enhance training based on updated Policy, Procedures, and Development Standards | Training schedule/cadence | Pete W. | 2015-12-31 | No | Training schedule/cadence drafted | 2015-12-31 | Training schedule/cadence reviewed and published | 2015-12-31 | [6 empty] | Low | Low | No
Model Risk Management |  | Implement Policy and Procedures/Standards | TBD | Pete W. | TBD | No | Collection of compliance report complete | TBD | [8 empty] | High | High | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Prioritized list of Legacy models | Paul M. | 2015-07-31 | No | Legacy models prioritized for validation | 2015-07-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Gap assessment result | Paul M. | 2015-10-31 | No | Tier 1 Models gap assessment complete | 2015-10-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Remediation plan | Paul M. | 2015-10-31 | No | Tier 1 Models remediation plan complete | 2015-10-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Validation results | Paul M. | 2015-10-31 | No | Initial validation findings – including interim compensating controls and other risk mitigants | 2015-10-31 | [8 empty] | High | High | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | List of validation ready models | Paul M. | 2015-12-31 | No | Commence work on models identified as being ready for validation | 2015-12-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | CCAR model validation | Validation Schedule | Paul M. | 2015-06-30 | No | Definition of validation schedule with Model Development complete | 2015-06-30 | [8 empty] | High | Medium | Yes
Model Risk Management |  | CCAR model validation | CCAR Model Validation Result | Paul M. | 2015-12-31 | No | CCAR models validated | 2015-12-31 | [8 empty] | High | High | Yes
Model Risk Management |  | Define model data validation data and reporting requirements aligned to model risk management framework and validation standards | Model data validation data requirements | TBD | TBD | Yes | Requirements for Model Data validation data drafted | TBD | Requirements for Model Data validation data approved | TBD | [6 empty] | High | Low | No
Model Risk Management |  | Define model data validation data and reporting requirements aligned to model risk management framework and validation standards | Model data validation reporting requirements | TBD | TBD | Yes | Requirements for Model Data validation Report drafted | TBD | Requirements for Model Data validation Report approved | TBD | [6 empty] | High | Medium | No
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SHUSA Aggregrated IT Risk Assessment Document (Phase 1 - partial completion expected) | Frank Cignarella | December 31 2015 | Yes | IT Risk Assessment Methodology Document Published | June 1 2015 | IT Risk Aggregregation Model Developed and Approved by IT, ORM and ERM | July 1 2015 | iGRC SHUSA Instance with Business Hierarchy loaded | Aug 1 2015 | iGRC Data populated for SHUSA and related entitied (SBNA, SCUSA, other (SIS) | December 15 2015 | SHUSA Risk Aggregration report from iGRC Data generated for management | December 31 2015 | Medium | High | Yes | SHUSA iGRC Instance and SBNA methodology and groundwork available today to leverage; contract in place with vendor to support
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SBNA IT Risk Assessment Document (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 10 2015 | Yes | SBNA IT Risk Register | May 25 2015 | SBNA IT Applicability Matrix | June 1 2015 | SBNA IT Control Plans and Controls Modeled inside iGRC | June 15 2015 | SBNA IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | SBNA Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | SBNA iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SCUSA IT Risk Assessment Document (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 15 2015 | Yes | SCUSA IT Risk Register | May 25 2015 | SCUSA IT Applicability Matrix | June 15 2015 | SCUSA IT Control Plans and Controls Modeled inside iGRC | June 20 2015 | SCUSA IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | SCUSA Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | SCUSA iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | Other SHUSA Entity IT Risk Assessment Document (e.g., SIS, etc.) (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 20 2015 | Yes | Other IT Risk Register | May 25 2015 | Other IT Applicability Matrix | June 20 2015 | Other IT Control Plans and Controls Modeled inside iGRC | June 25 2015 | "Other" IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | "Other" Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | "Other" iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
Data & IT |  | Finding and Remediation Management Capability and Governance (including 2014 IT SOX Finding Remediations) | Monthly report of Technology Findings and Remediation Plans, assigned to owners with business alignment (T&O, Retail, Auto, etc.) generated and delivered to EMC members | Frank Cignarella | December 1 2015 | Yes | Business Owners for Applications (SOX Covered) Identified | June 1 2015 | Findings for Business Applications assigned to Business Owners (e.g., T&O, Retail, Auto, etc.) | June 15 2015 | Findings and Remediation Plan Governance Model Documented (expected behavior and timing) | July 1 2015 | SHUSA and related entities Findings to be loaded into iGRC SHUSA Instance and related iGRC instances for entities (SBNA, SCUSA, etc.) with minimum necessary fields populated | Oct 1 2015 | "Governance" Report generated from iGRC and communicated to EMC members and the finding and remediation plan owners for ongoing management and maintenance | Nov 20 2015 | High | High | Yes | IGRC instances and SBNA OpRisk Issue Management documentation available to leverage; heavy lifting will be getting ownership, fields populated and active management of the findings and remediations in place and under governance whereby violations (non participation) are escalated and remedied.
Data & IT |  | Governance: Policy, Standards, Roles and Responsibilities Development (EPAP, RTS) | IT Governance document in EPAP Compliant format for SHUSA the holding company approved and published | Frank Cignarella | December 31 2015 | Yes | IT Policies Drafted | Nov 1 2015 | IT Policies Approved | Dec 1 2015 | IT Standards Drafted | Dec 1 2015 | IT Standards Approved | Dec 15 2015 | IT Guidelines, Acceptable form, and select IT Processes Drafted | Dec 31 2015 | High | Medium | Yes | Contracted for delivery of the draft documents with vendor in place, leveraging same vendor we had success developing SBNA governance documents with and will 'uplifting' SBNA documents to the extent practical.
Data & IT |  | Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA Access Attestation & Certification Solution - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for Access Attestation and Certification | Oct 1 2015 | Define SHUSA Access Attestation and Certification - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA Access Attestation & Certification Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA Access Attestation and Certification Solution | Dec 15 2015 | Production Release -SHUSA Access Attestation & Certification Solutoin Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) and initial campaign initiated | Dec 31 2015 | High | High | Yes | Contracted for delivery of the Attestation and Certification with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Data & IT |  | Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA User Access Request Portal - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for User Access Request Portal | Oct 1 2015 | Define SHUSA User Access Request Portal - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA User Access Request Portal Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA User Access Request Portal Solution | Dec 15 2015 | Production Release - SHUSA User Access Request Portal - Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) (3-5 Applications and related roles can be requested and workflow for management pre-approval and then sent to human provisioners) | Dec 31 2015 | High | High | Yes | Contracted for delivery of the User Access Request Portal with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Data & IT |  | Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA Access Termination Workflow - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for Access Termination Workflow | Oct 1 2015 | Define SHUSA Access Termination Workflow - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA Access Termination Workflow Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA Access Termination Workflow Solution | Dec 15 2015 | Production Release - SHUSA Access Termination Workflow - Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) | Dec 31 2015 | High | High | Yes | Contracted for delivery of the Access Termination Workflow Solution with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Data & IT |  | Data Flow Control from Upstream Feeders into Golden Sources and from Golden Sources to Downstream Reporting Systems | Data Flow Control Document detailing the data flows and specific controls (e.g., accuracy and completeness) in place for the data elements | Frank Cignarella | December 31 2015 | Yes | Data Elements identified and documented | July 1 2015 | Data Sources (Upstream feeders, golden sources, downstream reporting systems) identified and documented (including owners) | Aug 1 2015 | Data flow modeled (flow chart) from source to source (upstream, golden, downstream) | Oct 1 2015 | Control Points and Control Techniques documented | Nov 1 2015 | Potential gaps in control points and control techniques documented in SHUSA iGRC as Findings with corresponding remediation plans | Dec 31 2015 | High | High | Yes | This is a core deliverable and requires support from the Architecture, RDA and CDO teams
Data & IT |  | Establish Key Data Elements (KDEs) for prioritized CCAR data (including models and schedules), including documenting data dictionary and lineage, measuring and remediating data quality, deploying data controls. | KDEs defined for each domain in SHUSA, with lineage information, data quality rules, and initial metrics (KPIs) | Peter Flanagan | 2015-12-31 | Yes
Data & IT |  | Implement a Data Quality Center of Excellence to improve the quality of the company’s data (SHUSA and all the related US entities) by centralizing the collection of data defects, analyzing and assigning the issues causing the defects, and ensuring remediation activities are completed. | DQ COE staffed and operational | Peter Flanagan | 2015-12-21 | Yes
Data & IT |  | Conduct a data industry maturity model assessment for SBNA, SCUSA and SHUSA to identify capability gaps that require further remediation. | Data Maturity Model (DMM) assessment for each of SHUSA, SBNA and SCUSA | Peter Flanagan | 2015-08-30 | No
Data & IT |  | Establish strict governance on KDEs to assess, ensure and report on compliance with data policies and standards. | Establishment of working group including business data stewards | Peter Flanagan | 2015-12-31 | No
Data & IT |  | Create the structure and organization of the CDO for SHUSA | Staffed CDO Target Operating Model | Peter Flanagan | 2015-12-21 | No
Data & IT |  | Clearly define roles, responsibilities and ownership for data collection, quality, maintenance (Data Manager, Data Owner, Data Steward, DQ Admin, Tech Data Owner,……) as well as a list of Data Domains. | Agreed list of Data Domain definition documents, with assignment of key roles | Peter Flanagan | 2015-07-31 | No
Data & IT |  | Organize data management roles along the three lines of defense model (Business, Chief Data Officer and Independent Audit) | Approval of data management roles definitions | Peter Flanagan | 2015-07-15 | No
Data & IT |  | Socialize data management program and implementation plan with key stakeholders. | Education and communication plan for SHUSA CDO | Peter Flanagan | 2015-07-15 | No
Data & IT |  | Define domain scope and boundaries | Data Domain definition documents | Peter Flanagan | 2015-11-30 | No
Data & IT |  | Launch a SHUSA Data Governance Council attended by Data Manager, Data Owners, Data Stewards and CDO. | Data Governance council charter approved by first meeting of DG Council members | Peter Flanagan | 2015-06-30 | No
Data & IT |  | Assess and ensure compliance of SHSUA, SBNA and SCUSA practices against the Data Management Policy and Standards | Compliance review worksheet completed for each CDO team within SHUSA, SBNA and SCUSA | Peter Flanagan | 2015-12-31 | No
Data & IT |  | Define a comprehensive data control framework, and apply it for critical CCAR and EPS / ELS related processes | Data Dictionary, Lineage, Data Quality Dashboard Reports | Peter Flanagan | 2015-12-31 | Yes
Data & IT |  | Conduct data industry maturity model assessment for SHUSA, SBNA and SCUSA on an annual basis | Completed Maturity Model | Peter Flanagan | 2015-11-30 | No
CCAR | Scenario generation | Improve linkages between scenario generation and upstream / downstream processes | Capital Management team included in the Risk ID process to ensure appropriate collaboration between teams and support the identification of quantitative and qualitative risks | John Barris | 2015-10-31 | No | Identify Capital Management-Risk ID liaison | 2015-06-30 | Define roles, responsibilities governing involvement and collaboration (if any) | 2015-07-31 | Review ed aggregation of SHUSA-level Inventory with Top-Down Analysis | 2015-10-31 |  |  |  |  | Medium | Medium | No | Heavy reliance on Risk ID to meet their deadlines, which are reflected here as Milestones.
CCAR | Scenario generation | Development of multiple, robust scenarios for selection and testing | Enhanced set of scenarios aligned to the refreshed scenario design methodology | John Barris | 2015-12-18 | No | Receive SHUSA-level Risk ID Inventory & Assessment | 2015-10-31 | Capital Management presents and recommends initial set of Idiosyncratic Narratives to Ex&Agg | 2015-11-13 | Capital Management recommends Idiosyncratic Narratives to Management CC | 2015-12-18 | Capital Management recommends Idiosyncratic Narratives to Board CC | 2015-12-01 | Capital Management works with BU and Risk stakeholder to paramterize suite of multiple scenarios | 2015-12-18 | High | Medium | No
CCAR | Scenario generation | Development of multiple, robust scenarios for selection and testing | Updated policies and procedures that govern the scenario-design and scenario-selection processes | John Barris | 2015-10-31 | No | First Draft of Policy & Procedure Documentation reviewed by CCAR Director | 2015-08-30 | Policy & Procedure Documentation reviewed by Ex&Agg | 2015-08-15 | Policy & Procedure Documentation reviewed by Management CC | 2015-09-15 | Policy & Procedure Documentation reviewed by Board CC | 2015-10-31 | Policy & Procedure Documentation updated to reflect actual CCAR 2016 process | 2016-01-31 | Medium | Low | No
CCAR | Scenario generation | Development of multiple, robust scenarios for selection and testing | BHC scenarios actual macroeconomic data aligned across all scenarios | John Barris | 2016-01-31 | No | Presentation of a suite of scenarios to Management and Board Capital Committees for formal selection and approval of the scenarios to be used in CCAR/DFAST | 2015-12-31 | Receive FRB Scenarios from FRB | 2015-01-22 | Align BHC Scenario Actuals with FRB Scenarios | 2015-01-31 |  |  |  |  | Low | Low | No
CCAR | Capital assessment | Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Defined quantification approach and methodology | Imad Kordab | TBD | No | Drafted quantification approach and methodology |  | Syndicated with relevant experts and stakeholders |  | Approved by [X] committee
CCAR | Capital assessment | Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Developed model to translate uncertainty to a capital buffer | Imad Kordab | TBD | Yes | Staffed modeling team |  | Developed multiple model options for governance committee consideration |  | Finalized modeling approach
CCAR | Capital assessment | Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Quantification/estimate of uncertainty resulting from capital planning and process weaknesses at a process or model level | Imad Kordab | TBD | Yes | Assessed current and past process weakness to develop estimate of uncertainty |  | Developed estimates related to assumptions, limitations and weaknesses |  | Quantification approved by [X] committee
CCAR | Capital assessment | Measure and account for inherent uncertainty due to model limitations | Developed quantification approach and standards | Imad Kordab | TBD | No | Drafted quantification approach and standards |  | Approved by [X] committee
CCAR | Capital assessment | Measure and account for inherent uncertainty due to model limitations | Disseminated the approach to stakeholders to syndicate | Imad Kordab | TBD | No | Developed approach to stakeholders |  | Implemented approach
CCAR | Capital assessment | Measure and account for inherent uncertainty due to model limitations | Quantified inherent model uncertainty and incorporated results into stressed capital buffer | Imad Kordab | TBD | No | Develop intial quantification of model uncertainty |  | Syndicated results of uncertainty measurement with model risk management and model validation |  | Approved by [X] committee
CCAR | Capital assessment | Developed economic capital model to evaluate impact on capital of stressful scenarios | Rigorous process developed beyond enterprise-wide scenario analysis, to assess the aggregate impact on capital from stressful conditions | Imad Kordab | TBD | Yes | Brainstormed and determined necessary actions to constititute process steps |  | Mapped process based on determined steps
CCAR | Capital assessment | Formalized management overlays process | Developed overlay standards and templates | Imad Kordab | TBD | No | Determined and consulted with correct stakeholders |  | Determined correct standards/templates based on stakeholder interactions |  | Incorporated feedback and expert opinions
CCAR | Capital assessment | Formalized management overlays process | Disseminated model overlay approach to governance committees and model owners | Imad Kordab | TBD | No | Disseminated approach to stakeholders |  | Implemented approach |  | Implemented standards of documentation for overlays
CCAR | Capital assessment | Formalized management overlays process | Aggregated of overlays across CCAR process steps | Imad Kordab | TBD | No | Developed and implemented process for centralzing collection of overlay documentation |  | Aggregated overlay results across CCAR process steps
CCAR | Governance and effective challenge | Improved weakness indentification and management process | Updated weakness indentification policy and procedures | Jon Watson | TBD | No | Draft updated policy and procedures |  | Draft sent to committee #1 |  | Draft sent to committee #2 | [5 empty] | Medium | Low
CCAR | Governance and effective challenge | Improved weakness indentification and management process | Finalized weakness inventory with owners and action items | Jon Watson | TBD | No | Weakness inventory structure updated to comply with new weakness ID procedures |  | Weakness ID process communicated to CCAR participants |  | Completed inventory | [5 empty] | Medium | High
CCAR | Governance and effective challenge | Refreshed and implemented review and challenge framework | Review and enhance current review and challenge framework | Jon Watson | TBD | No | Assessment and update of current framework completed |  | Draft sent to committee #1 |  | Draft sent to committee #2 |  | New review and challenge communicated to all relevant governance committees |  |  |  | Medium | Low
CCAR | Governance and effective challenge | Refreshed and implemented review and challenge framework | Review and challenge calendar aligned to framework | Jon Watson | TBD | No | Calendars and high-level drafted |  | Calendar approved by committee #1 |  | Detailed calendar based on revamped end-to-end process | [5 empty] | Medium | Low
CCAR | Governance and effective challenge | Updated CCAR governance structure | Re-designed CCAR governance structure and landscape | Jon Watson | TBD | No | Current state governance structure and flows assessed |  | New CCAR governance structure determined (e.g., charters, membership) |  |  |  | Approval of governance structure by committee #1 |  |  |  | Medium | Low
CCAR | Governance and effective challenge | Updated CCAR governance structure | Governance landscape implemented | Jon Watson | TBD | No | Governance structure approved |  | Initial meeting of committee with new membership/composition held | [7 empty] | High | High
CCAR | Governance and effective challenge | Extensive board engagement and input into CCAR process | Board training materials and schedule | Jon Watson | TBD | No | Developed overall board training schedule and agenda |  | Delivered training #1 |  | Delivered training #2 | [5 empty] | High | Medium
CCAR | Governance and effective challenge | Extensive board engagement and input into CCAR process | Board key capital planning decision calendar and schedule | Jon Watson | TBD | No | Deveoped overall board interaction schedule and model |  | Approved by [X] committee | [7 empty] | Medium | Medium
CCAR | Documentation | Develop common documentation standards and templates | Developed document landscape consisting of key document categories | Jon Watson | TBD | No | Identified the universe of document categories (e.g., capital planning and policy) |  | Collaborated with process/category owners to define the document types per category |  | Syndicated completeness of document landscape (across processes and within process steps / events) with process owners and overarching CCAR central team | [5 empty] | Medium | Low
CCAR | Documentation | Develop common documentation standards and templates | Documentation standards, procedures and templates across the documentation landscape | Jon Watson | TBD | No | For each document in the landscape, defined level of document granularity, type of descriptions required ((e.g., actions, processes, events), and type of explanation (e.g., analysis, decision-making / rationale) |  | Syndicate documentation standards with CCAR central team to ensure documentation standards are aligned with FRB expectations |  | Syndicated / disseminated document standards with process owners witin workstreams |  | Adapted models and processes to ensure capture of documents to the established standards (e.g., altered granularity of models to ensure documentation granularity) |  |  |  | Medium | Low
CCAR | Documentation | Develop common documentation standards and templates | Developed a centralized inventory for documents, with clear organization scheme and owners attached | Jon Watson | TBD | Yes | Identified central storage warehouse for documents |  | Defined organization scheme for documents (e.g., by Y 14A line item, v. legal entity) |  | Defined ownership for each document in each category |  | Defined owner roles and responsibilities |  | Trained owners on orgnization scheme and inventory access |  | Medium | Medium
CCAR | Documentation | Create centralized documentation aggregation and review process | Detailed documentation hand-off process including calendar of hand-offs and dates | Jon Watson | TBD | No | Developed calendar of review and challenge sessions in line with |  | Defined steps in review process for incorporating feedback, correctionsm and controls to ensure evidence of review is incorporated |  | Mapped out detailed documentation hand-off process, including calendar of hand-offs and R&C session, with dates for submission | [5 empty] | Medium | Low
CCAR | Documentation | Create centralized documentation aggregation and review process | Established central oversight to own document aggregation | Jon Watson | TBD | No | Defined ownership of and accountability for dcoumentation process |  | Assigned central team documentation liaisons in each core documentation area | [7 empty] | Medium | Medium
CCAR | E2E process and controls | Redesign and centralization of the CCAR end-to-end process | Developed spreadsheet inventory and standardized controls | Jon Watson | TBD | No | Compiled list of all spreadsheets used in each CCAR process |  | Defined organization scheme for spreadsheets (e.g., by Y 14A line item, v. legal entity) |  | Assessed criticality of each spreadsheet for classification and prioritization |  | Identified, implemented and documented all required control points |  | Defined a minimum set of spreadsheet controls (e.g., password protection) and applied to all spreadsheets |  | High | High
CCAR | E2E process and controls | Restructure CCAR organization and improve staffing | Centralized oversight and execution of CCAR cycle run process within CCAR workstream | Jon Watson | TBD | No | Established oversight governance, i.e., CCAR leadership / oversight, decision-making, reporting lines, and escalation process |  | Defined responsibilities of oversight team (e.g., process design, change management and issue tracking) | [7 empty] | High | High
CCAR | E2E process and controls | Restructure CCAR organization and improve staffing | Implemented change management process led by dedicated team | Jon Watson | TBD | No | Defined change management team responsibilities: identification and documentation of changes and required controls |  | Defined process for managing changes and internal controls |  | Established ownership / leadership of change management process | [5 empty] | High | High
CCAR | E2E process and controls | Develop new internal controls framework and testing procedures | Developed an enhanced internal controls framework and testing plan | Jon Watson | TBD | No | Defined CCAR requirements for internal controls |  | Defined critical control points across CCAR cycle run process |  | Developed materiality assessment for internal control points |  | Created a governance mechanism to ensure that all control points used in the capital planning process are graded for materiality |  | Ensured robust design and testing of controls within material spreadsheets |  | Medium | Low
CCAR | E2E process and controls | Develop new internal controls framework and testing procedures | Implemented internal controls across critical control points | Jon Watson | TBD | Yes | All material controls implemented |  | All remaining controls implemented | [5 empty] | Engaged external advisors to supplement internal teams in oversight and execution |  | High | High
CCAR | E2E process and controls | Develop new internal controls framework and testing procedures | Designed and enforced governance structure to ensure consistent implementation of controls mechanisms | Jon Watson | TBD | No | Defined clear ownership of controls and review and challenge processes |  | Developed hand-off calendar with sign-off for audit and review tasks | [7 empty] | Medium | High
CCAR | E2E process and controls | Effective process for aggreagating estimates of loss revenue | Updated IT infrastructure for generation and aggregation of loss estimates | Jon Watson | TBD | Yes | Developed customized SAS aggreation tool for loss and PPNR forecasts |  | Reconciled as of data set |  | Partially implemented Moody's Scenario Analyzer |  | Increased granularily of forecasts (e.g., by business line / unit) in SAS |  |  |  | High | High
Model Development |  | In partnership with MRMG, promulgate an Enterprise Model Policy that includes standards for: Data, Model development, Documentation, Testing and implementation, Validations, Monitoring, Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services | Develop an Enterprise Model Policy | Alex Silloway and Rafic Fahs | Thu 7/2/2015 | No | Enterprise Model Policy COMPLETE and APPROVED at CART Leadership (to include Standards, Roles & Responsibilities, and a gap analysis against SR Letter 11-7) | Thu 7/16/2015 | Communication of the Enterprise Model Policy DISTRIBUTED company wide and train Model Owners, Model Developers, Model Validators and Model User | Thu 9/3/2015 | Draft procedures re: Enterprise Model Policy COMPLETE and APPROVED at Working Group (to reinforce the application of the Enterprise Model Policy for Model Developers) | Thu 9/3/2015 |  |  |  |  | Low | Low | Yes | Resources required: consulting company to do benchmark analysis and gap assessment versus SR Letter 11-7
Model Development |  | Review, and modify if needed, working group charters | Working group charters | Alex Silloway | Thu 7/2/2015 | No | Existing governance MAPPED and APPROVED (to include the following topics: Alignment on Data for Model Development, Documentation, Testing and implementation, Validations, Monitoring, Model Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services) | Fri 6/19/2015 | Charters UPDATED and COMPLETE and APPROVED at CART Leadership | Thu 7/2/2015 | Implement new charters within all working groups | Thu 7/2/2015 |  |  |  |  | Low | Low | No | 0
Model Development |  | Ensure model performance monitoring reports are being regularly generated for all tier 1 models | Model Performance Monitoring report for all tier 1 models | Alex Silloway | Thu 7/2/2015 | No | Receive from MRM final inventory of all tier 1 models | Mon 6/1/2015 | All tier 1 models not included on the model performance monitoring report prioritized & ADDED | Fri 6/19/2015 | Procedures COMPLETE establishing routines to ensure model performance monitoring reports are being regularly generated for all tier 1 models | Thu 7/2/2015 |  |  |  |  | Medium | Medium | No | 0
Model Development |  | Define a Model Development organizational structure that establishes clear lines of control between SHUSA and LOBs | Model Development Organizational Structure | Alex Silloway | Thu 7/2/2015 | No | Scope and roles & responsibilities for SHUSA Model Development group (with detailed lines of control btwn SHUSA & LOBs) COMPLETE | Thu 7/2/2015 | Model Dev Organizational Structure COMPLETE and APPROVED at CART Leadership | Thu 7/2/2015 | [6 empty] | Low | Low | Yes | Model Development resources pending Organizational Structure design
Model Development |  | Standardized skills assessments for senior analysts and managers | Standardized job descriptions across SHUSA | Alex Silloway | Thu 7/2/2015 | No | Existing job descriptions for Model Development across SHUSA MAPPED | Mon 6/8/2015 | Organization and HR job descriptions for Model Development across SHUSA reviewed with HR and APPROVED | Thu 7/2/2015 | New job descriptions for existing Model Development employess COMMUNICATED / SOCIALIZED across SHUSA | Thu 7/2/2015 |  |  |  |  | Low | Low | Yes | Resouces: Pending revised grade and comp for new Job Descriptions
Model Development |  | Assess recruiting needs and begin recruiting of qualified FTEs | New and existing resource requirement and recruitment plan | Alex Silloway | Fri 7/31/2015 | No | Comprehensive staffing assessment conducted and COMPLETE (determines skills, capabilities and areas of expertise) | Fri 6/19/2015 | Gap analysis between staffing assessment and model landscape COMPLETE | Thu 6/25/2015 | New hiring plan defined and APPROVED at CART Leadership | Thu 6/25/2015 |  |  |  |  | Low | Low | Yes | Resouces: Pending idetification of resource needs outside of Model Development group (resource of Model Development group already identified together with the definition of the new Organization Structure)
Model Development |  | Introduce Professional Qualification Standards (PQS) at the SHUSA level | Professional Qualification Standards (PQS) at the SHUSA level | Alex Silloway | Thu 10/29/2015 | No | PQS at SHUSA COMPLETE and APPROVED | Thu 10/29/2015 | Training and Implementation plan COMPLETE and APPROVED | Thu 10/29/2015 | [6 empty] | Medium | Medium | Yes | May need assistance with systems support
Model Development |  | Model Reference Library: - Establish a Model Reference Library of modeling procedures, standardized reporting templates, best practices, and other support materials to assist in the management of mathematical models - Populate the Model Reference Library with at least one “Gold Standard” document | Model Reference Library | Alex Silloway | Thu 10/29/2015 | No | Model Reference Library DEFINED (to include modeling procedures, standardized reporting templates, best practices, and other support materials to assist in the management of models) | Thu 10/29/2015 | Model Reference Library POPULATED (includes X "Gold Standard” documents) | Thu 10/29/2015 | Model Reference Library SHARED company-wide | Thu 10/29/2015 | Training Plan COMPLETE, APPROVED and IMPLEMENTED | Thu 10/29/2015 |  |  | Low | Low | Yes | Vendor may be needed to develop training plan and assist with inventory
Model Development |  | Model Landascape: - Confirm Model inventory - Assign model risk tiers (in alignment with new tiering system) - Assess model performance - Identify non-existent BAU models - Prioritize - Validate or redevelop as necessary | 2015 & 2016 Model Landascape | Alex Silloway and Rafic Fahs | Fri 7/31/2015 | Yes | Model Inventory CONFIRMED | Mon 6/8/2015 | Model Risk Tiers ASSIGNED / COMPLETE | Mon 6/15/2015 | Model development Prioritization COMPLETE | Mon 6/15/2015 | Go-forward Model Development Strategy COMPLETE (outlining the Development, validation or redevelopment of models wherever necessary) | Fri 6/26/2015 | Model Development procedures COMPLETE and APPROVED (procedures will allow MD to continue this process moving forward) | Fri 7/31/2015 | High | High | Yes | 0
Model Development |  | CCAR Models: - Strong coordination between PPNR and CCAR Credit Losses, with unified project plan - Follow approved approach, including unified decision making, to prioritize and execute CCAR Model Landscape for 2016 - Ensure alignment and appropriateness of segmentation and selection of Risk Factors - Create procedures for 70% of all CCAR modeling processes | CCAR Model Landascape for 2016 CCAR Submission | Alex Silloway | Tue 9/1/2015 | Yes | Unified project plan for PPNR and CCAR Credit Loss model development COMPLETE | Thu 7/2/2015 | Approach to prioritize the CCAR Model Development landscape for 2016 DEFINED | Mon 8/3/2015 | Procedures COMPLETE implementing recurring model performance monitoring | Tue 9/1/2015 | Procedures for 70% of all CCAR modeling processes COMPLETE and APPROVED | Tue 9/1/2015 |  |  | High | High | Yes | 0
Formulas:
Proposed Date = Table2[[#This Row],[Proposed Date]]
Proposed Date2 = Table2[[#This Row],[Proposed Date2]]
Proposed Date3 = Table2[[#This Row],[Proposed Date3]]
Proposed Date4 = Table2[[#This Row],[Proposed Date4]]
Proposed Date5 = Table2[[#This Row],[Proposed Date5]]
Proposed Date6 = Table2[[#This Row],[Proposed Date6]]
Milestone 3 (If applicable) = Table2[[#This Row],[Milestone 3 (If applicable)]]
Milestone 4 (If applicable) = Table2[[#This Row],[Milestone 4 (If applicable)]]
Milestone 2 (If applicable) = Table2[[#This Row],[Milestone 2 (If applicable)]]
Milestone 1 = Table2[[#This Row],[Milestone 1]]
Milestone 5 (If applicable) = Table2[[#This Row],[Milestone 5 (If applicable)]]
CART- Master Program Level Deliverable Inventory

## Finance Transformation
|  | Yes | [12 empty] | High
|  | No | [12 empty] | Medium
Low
Initiative | Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Milestone 6 | Proposed Date7 | Milestone 7 | Propsoed Date8 | Milestone 8 | Proposed Date9 | Milestone 9 | Proposed Date10 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Workstream Interdependency | Comment | Workstream Interdependency 2 | Comment 2
Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | Enhanced SOX Internal Control framework and methodology | M. Munoz | 2015-12-31 | No | [18 empty] | Medium | High | Yes | Resources need to be approved, identified, and hired
Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | SOX based CCAR Internal Control framework and methodology | M. Munoz | 2015-12-31 | No | Conduct gap assessment against SOX framework | 2015-06-30 | Enhance framework to align with CCAR internal controls requirements | 2015-09-30 | Benchmark framework against industry standard/regulatory expectations | 2015-12-31 | [12 empty] | Medium | Medium | Yes |  | Model Development | CCAR Models | Model Risk Management | CCAR Models
Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | EUA Internal Conttrol Framework and Methodology | M. Munoz | 2015-12-31 | No | [18 empty] | Medium | Medium | No
Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | BSI SOX/COSO Internal Control program | M. Munoz | 2015-12-31 | yes | Approve and hire resources for open SOX positions across SHUSA | 2015-07-31 | Acquire tool (Archer) to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-06-30 | Configure (Archer) tool to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-07-31 | Source clean data into the tool to enable adherence with enhanced SOX methodology | 2015-11-30 | Complete testing and certification for SOX | 2015-12-31 | [8 empty] | High | Medium | No
Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | BSI/PR SOX based CCAR Internal Control Program | M. Munoz | 2015-12-31 | yes | Approve and hire resources for open SOX positions across SHUSA | 2015-07-31 | Leverage tool used for SOX compliance to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-11-30 | Conduct gap assessment against existing CCAR controls and documentation | 2015-09-30 | Develop and execute on remediation plan based on gap findings | 2015-09-30 | Complete testing and certification for CCAR | 2015-12-31 | [8 empty] | Medium | Medium | No |  | Model Development | CCAR Models | Model Risk Management | CCAR Models
Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | SHUSA (All IHC Entities) EUA Internal Control Program | M. Munoz | 2015-12-31 | No | Operationalize existing tool across all new SHUSA subsidiaries to remediate existing MRIA on spreadsheet risk management | 2015-06-30 | Execute active identification and management of critical spreadsheets | 2015-12-31 | [14 empty] | Medium | High | Yes | Need to approve, identify, and hire resources (also tool needs to be installed)
Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | 2015 Strategic Plan Timeline (Planning Calendar) | D. Budington | 2015-06-15 | No | Draft of the 2015 Strategic Plan Timeline framework has been developed and reviewed with stakeholders | 2015-06-05 | Revisions are incorporated and the 2015 Strategic Plan Timeline has been finalized | 2015-06-15 | [14 empty] | Medium | Medium | Yes | Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | FP&A Policy Documentation and Implementation | D. Budington | 2015-07-30 | No | Governance Model Design has been reviewed and approved by SHUSA and subsidiary EMCs | 2015-06-30 | Planning process design has been reviewed and approved (same approvars) | 2015-06-30 | Data flow map and reconciliation points has been review and approved | 2015-07-30 | Planning Guide Framework has been reviewed and approved | 2015-07-30 | [10 empty] | Medium | Medium | Yes | Delivery Risk: Requires executive approval and entity buy-in on process design and roles/responsibilities
Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | 2015 Strategic Planning Forecasting Process Design and Implementation | D. Budington | 2015-11-15 | No | Design contributor file system and reporting requirements for Strategic Planning process to integrate into SAS forecasting engine | 2015-06-30 | Develop, Test and Implement Strategic Planning forecasting process | 2015-09-30 | Execute forecasting process for P-18 strategic plan | 2015-11-15 | [12 empty] | High | High | Yes | SAS dependency; Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | Critical positions within strategic planning and PPNR teams are staffed to execute 2015 FP&A activities | D. Budington | 2015-07-30 | Yes | All positions posted and recuriters engaged | ongoing | Develop skills assessment gaps and remediation and training plans | ongoing | Identify and manage succession and operational risks | [13 empty] | High | High | Yes | SAS, Moody's as data repository for contract level information and RWA.
Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | Board approved and well documented Strategic Plan (SP18) | D. Budington | 2015-12-31 | No | High-level 3 year strategic priorities has been completed | 2015-06-30 | Investor Day Presentation has been delivered | 2015-09-15 | Final Board Approval for Strategic Plan has been received | 2015-12-31 | [12 empty] | Medium | Medium | Yes | Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Planning and Analysis | Establish and implement foundational strategic planning and forecasting functions and ensure consistency in the governance and forecast process used for SHUSA's P-18 strategic plan and the capital planning process used for CCAR. | 2016 Budget | D. Budington | 2015-12-31 | No | Mapping process of Budget to Strategic Plan has been completed | 2015-09-15 | Entity submission has been completed | 2015-11-01 | Review & challenge process has been completed | 2015-12-01 | Final submission has occurred | 2015-12-15 | Final Board approval has been received | 2015-12-31 | [8 empty] | Medium | Medium | Yes | Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Planning and Analysis | Establish and implement foundational SHUSA Management Reporting function | Team is identified and hired | D. Budington | 2015-08-30 | No | Organization chart, roles, responsibilities and job descriptions are defined | 2015-07-01 | Candidates interviewed and offers have been extended and accepted | 2015-08-30 | [14 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Planning and Analysis | Establish and implement foundational SHUSA Management Reporting function | Reporting Package Templates (Board package, Profitability reporting, Entity business review) | D. Budington | 2015-06-30 | No | Reporting Package methodology and framework have been designed | 2015-06-15 | Reporting Package draft templates have been built and reviewed with stakeholders | 2015-06-15 | Revisions have been made and the Reporting Package templates have been approved and finalized | 2015-06-30 | [12 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Planning and Analysis | Establish and implement foundational SHUSA Management Reporting function | Systemic production of monthly reporting packages | D. Budington | 2015-10-30 | No | [18 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Planning and Analysis | Incorporate cost of Contingent Liquidity across all SHUSA | Methodology and Interim Solution for Contingent Liquidity | D. Budington | 2015-12-31 | No | Finalize and Approve Contingent Liquidity methodology | 2015-08-31 | Interim Solution for Contingent Liquidity reviewed and approved with stakeholders | 2015-10-31 | Implement Interim Solution for Contingent Liquidity | 2015-12-31 | [12 empty] | Medium | Medium | Yes | Delivery Risk: Resource availability to review and approve requirement documents, Treasury dependency
Finance Planning and Analysis | Develop cost allocation policies and implementation plan to support organizational and product profitability analysis used in strategic planning and performance management | Cost allocation policies and implementation plan | D. Budington | 2015-12-31 | No | Cost allocation methodology and framework have been designed | 2015-08-31 | Cost allocation methodology, policies and implementation plan have been built and reviewed with stakeholders | 2015-10-31 | Feedback has been included and the cost allocation policies and implementation plan have been approved and finalized | 2015-12-31 | [12 empty] | Medium | Medium | Yes | Delivery Risk: Resource availability to review and approve requirement documents, Treasury dependency
Finance Planning and Analysis | Develop FP&A's Target Operating Model requirements and implementation plan | Detailed FP&A TOM (end state) implementation plan | D. Budington | 2015-12-31 | Yes | FP&A TOM "end state" business requirements | 2015-07-10 | High level technology assessment on strategic solution supporting FP&A TOM | 2015-10-30 | Detailed implementation plan | 2015-12-31 | [12 empty] | Medium | Medium | Yes | Delivery Risk: Resource availability to review and approve requirement documents
Treasury | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions | Established policies, procedures and MIS per regulatory requirements and enhanced internal practices | Manuel Aya | 2015-10-20 | No | Fulfill all open Treasury positions | 2015-09-30 | Target Operating Model Implemented | 2015-06-30 | Enhanced Internal practices identified and distributed for implementation | 2015-09-30 | [12 empty] | Medium | Medium | No |  | Model Development | LST Scenario Validation | Model Risk Management | LST Scenario Validation
Treasury | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions | Independent Review of LRM adequacy and effectiveness | Manuel Aya | 2015-10-20 | No | Establish policies and procedures to facilitate the independent review of the LRM policies, procedures and generation of analytics | 2015-10-20 | [16 empty] | Medium | Low | No
Treasury | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate | Established Policies and Procedures to Consolidate Intraday Liquidity Management | Manuel Aya | 2015-09-30 | No | Intraday Liquidity Management consolidation policies and procedures developed | 2015-09-30 | Intraday Liquidity Management consolidation policies and procedures approved by all applicable management committees | 2015-09-30 | [14 empty] | High | Medium | Yes |  | Operational Risk | Overight of integration into BAU
Treasury | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate | Established Policies and Procedures to Consolidate Intraday Collateral Management | Manuel Aya / Ed Cipullo | 2015-09-30 | Yes | Intraday Collateral Management consolidation policies and procedures developed | 2015-09-30 | Intraday Collateral Management consolidation policies and procedures approved by all applicable management committees | 2015-09-30 | Bank of New York (BONY Collateral Management System implemented | 2015-09-30 | [12 empty] | High | Medium | Yes |  | Risk Transformation | Market Risk Review and Chllenge
Treasury | Incorporate intraday procedures in SHUSA’s Cash Management and Funding policy and procedures | Incorporated intraday procedures and intraday metrics into SHUSA’s Liquidity Management and Funding policy and procedures | Manuel Aya, Bill Brundige, Andy Withers | 2015-12-31 | Yes | Intraday Liquidity Management consolidation policies and procedures implemented | 2015-12-31 | Intraday Collateral Management consolidation policies and procedures implemented | 2015-12-31 | Consolidated Intraday Liquidity Management information available for use by SHUSA | 2015-12-31 | Consolidated Intraday Collateral Management information available for use by SHUSA | 2015-12-31 | [10 empty] | High | High | Yes |  | Non CART Workstream | Argus Data Aggregation
Treasury | Develop first version of Board-approved Enterprise and Operating policies, procedure and charter for Interest Rate Risk | Produced Board approved Enterprise Operating Liquidity Risk Management Policy (OLRPM) and associated procedure(s) | Victor Morillo | 2015-12-31 | No | Enterprise Operating Liquidity Risk Management Policies (OLRMP) developed | 2015-06-30 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) approved by all applicable management committees | 2015-06-30 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) implemented for SHUSA, SCUSA, SBNA | 2015-09-23 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) implemented for all IHC entities | 2015-12-31 | [10 empty] | Medium | Medium | No |  | Non CART Workstream | Argus Data Aggregation
Treasury | Enhance QRM operating environment including prudent mix of Chart of Accounts and dimensions, access controls and optimization of processes | Analyzed and Revised QRM environment including Chart of Accounts, dimensions, controls and optimization of processes | Niraj Biswas | 2015-12-31 | Yes | QRM Chart of Accounts and Dimensions analyzed, reviewed and enhanced | 2015-09-30 | QRM access control and information distribution / sharing analyzed, reviewed and enhanced | 2015-09-30 | QRM processes reviewed and enhanced to provide improved availability of QRM information and implementation of "best practices" | 2015-12-31 | [12 empty] | High | High | Yes | Need RCRD resources; Delivery Risk: Data Quality and Data Sourcing |  | Finance - CCAR
Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Cash Flow Projections Completed | Manuel Aya | 2015-12-31 | Yes | Baseline Cashflow Projections | 2015-06-01 | Cash Flow Projection tool / reporting developed and deployed | 2015-12-31 | [14 empty] | High | Medium | No | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity SBNA and Fast Close
Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Model Validation Completed | MRM | 2015-12-31 | Yes | Conduct formal Model Validation on Stress testing Scenarios | 2015-12-31 | [16 empty] | High | Medium | No | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity SCUSA
Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | First round of stress testing completed and documented | Manuel Aya | 2015-05-29 | Yes | Stress Testing Tool developed and available | 2015-05-04 | First round of stress test generating scenarios and assumptions approved by all applicable management committees | 2015-05-29 | First round of stress test scenarios executed and complete results generated | 2015-05-29 | First round of stress test results fully documented and analyzed | 2015-05-29 | First round of stress test results published to all applicable management parties | 2015-05-29 | [8 empty] | High | Medium | No | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity BSI
Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Enhanced stress testing process with additional "framework" scenarios | Manuel Aya | 2015-12-31 | Yes | First round of enhanced stress test generating scenarios and assumptions approved by all applicable management committees | 2015-12-31 | Enhanced first round of stress test scenarios executed and complete results generated | 2015-12-31 | Enhanced first round of stress test results fully documented and analyzed | 2015-12-31 | Enhanced first round of stress test results published to all applicable management parties | 2015-12-31 | [10 empty] | High | Medium | No | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity PR
Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Enhanced stress testing process | Manuel Aya | 2016-04-18 | No | Conduct regression analysis of stress testing scenarios and assumptions for applicability, accuracy, and adjustment | 2016-04-18 | Revalidate, via formal Model Risk Management process, proposed adjustments to stress testing scenarios and / or assumptions | 2016-04-18 | Revised (if applicable) stress testing scenarios and assumptions approved by all applicable management committees | 2016-04-18 | [12 empty] | High | Medium | No | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity SIS
Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Operationalization of stress testing completed and documented | Manuel Aya | 2016-04-18 | Yes | Second round of stress test generating scenarios and assumptions approved by all applicable management committees | 2016-04-18 | Second round of stress test scenarios executed and complete results generated | 2016-04-18 | Second round of stress test results fully documented and analyzed | 2016-04-18 | Second round of stress test results published to all applicable management parties | 2016-04-18 | [10 empty] | High | Medium | No | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entities - Other IHC
Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Updated Liquidity Buffer | Manuel Aya | 2015-09-30 | No | Evaluate results of second round of stress testing to identify required adjustments to the Liquidity Buffer | 2015-06-30 | Proposed changes to the Liquidity Buffer approved by all applicable management committees | 2015-06-30 | Implement adjustments to the Liquidity Buffer via established procedures | 2015-09-30 | [12 empty] | Medium | Medium | No | May need additional resources. Delivery Risk: Willingness to comply with new change management process & controls |  | Finance - All SHUSA Entities Finance
Treasury | Develop capability to submit 2052a reports by 1/1/16 | Developed solution for data acquisition and storage to support 2052A regulatory reporting | Manuel Aya | 2015-12-31 | Yes | All required source data identified and availability/ location confirmed and documented | 2015-12-31 | All required source data extracted from identified source(s) and available for testing | 2015-12-31 | 2052A reporting solution developed and available for testing | 2015-12-31 | Quality Assurance testing for 2052A Reporting solution complete | 2015-12-31 | 2052A Reporting solution tested and deployed. | 2015-12-31 | [8 empty] | High | High | No | May need additional resources. Delivery Risk: Willingness to comply with new change management process & controls |  | Finance - All SHUSA Entities Finance
Treasury | U.S. LCR reporting (though not currently required, is expected to be produced as a result of the granularity of 2052a reporting) | Developed reporting solution to generate Liquidity Coverage Ratio (LCR) reporting based upon data submitted via 2052A | Manuel Aya | 2015-12-31 | Yes | Liquidity Coverage Ratio (LCR) reporting solution developed and available for testing | 2015-12-31 | Quality Assurance testing for Liquidity Coverage Ratio (LCR) reporting solution complete | 2015-12-31 | [14 empty] | High | High | No | Delivery Risk: Willingness to comply with new change management process & controls |  | Finance - All SHUSA Entities Finance
Accounting, Tax, & Reporting | Establish a set of reconciled and clean current and historical financial data (internal sources where possible) to use for reporting and to support forecasting capabilities (CCAR and Strategic Planning) | Historical reporting requirements (from CCAR/Strategic Plan perspective) | Eric Ratican | 2015-12-31 | No | [18 empty] | High | High | Yes | Need RCRD resources; Delivery Risk: Data Quality and Data Sourcing |  | Finance - CCAR
Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation implemented at SBNA | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SBNA to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SBNA GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SBNA to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from SBNA to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at SBNA | 2015-05-22 | HFM: Complete Design Phase for SBNA | 2015-05-22 | HFM: Complete Construct Phase for SBNA | 2015-09-03 | HFM: Complete Implement Phase for SBNA | 2015-10-01 | HFM: Complete Operate & Review Phase for SBNA | 2015-11-06 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity SBNA and Fast Close
Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation implemented at SCUSA | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SCUSA to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SCUSA GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SCUSA to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from SCUSA to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at SCUSA | 2015-05-22 | HFM: Complete Design Phase for SCUSA | 2015-05-22 | HFM: Complete Construct Phase for SCUSA | 2015-09-03 | HFM: Complete Implement Phase for SCUSA | 2015-10-01 | HFM: Complete Operate & Review Phase for SCUSA | 2015-11-06 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity SCUSA
Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation Implemented at BSI | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map BSI to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in BSI GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from BSI to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from BSI to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at BSI | 2015-05-22 | HFM: Complete Design Phase for BSI | 2015-05-22 | HFM: Complete Construct Phase for BSI | 2015-09-03 | HFM: Complete Implement Phase for BSI | 2015-10-01 | HFM: Complete Operate & Review Phase for BSI | 2015-11-06 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity BSI
Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidations Implemented at PR | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map PR to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in PR GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from PR to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from PR to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at PR | 2015-05-22 | HFM: Complete Design Phase for PR | 2015-05-22 | HFM: Complete Construct Phase for PR | 2015-09-03 | HFM: Complete Implement Phase for PR | 2015-10-01 | HFM: Complete Operate & Review Phase for PR | 2015-11-06 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity PR
Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidations Implemented at SIS | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SIS to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SIS GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SIS to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from SIS to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at SIS | 2015-05-22 | HFM: Complete Design Phase for SIS | 2015-05-22 | HFM: Complete Construct Phase for SIS | 2015-09-03 | HFM: Complete Implement Phase for SIS | 2015-10-01 | HFM: Complete Operate & Review Phase for SIS | 2015-11-06 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entity SIS
Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Hyperion Consolidation Implemented at other IHC entities | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map IHC-Other to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in IHC-Other GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from IHC-Other to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from IHC-Other to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at IHC-Other | 2015-05-22 | HFM: Complete Design Phase for IHC-Other | 2015-05-22 | HFM: Complete Construct Phase for IHC-Other | 2015-09-03 | HFM: Complete Implement Phase for IHC-Other | 2015-10-01 | HFM: Complete Operate & Review Phase for IHC-Other | 2015-11-06 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support. | Risk Transformation | Entities - Other IHC
Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Hyperion DRG Implemented | John Moore | 2015-11-12 | Yes | DRG: Complete Assess Phase | 2015-06-24 | DRG: Complete Design Phase | 2015-07-23 | DRG: Complete Construct Phase | 2015-08-28 | DRG: Complete Implement Phase | 2015-09-24 | DRG: Complete Operate & Review Phase | 2015-11-12 | [8 empty] | High | High | Yes | May need additional resources. Delivery Risk: Willingness to comply with new change management process & controls |  | All SHUSA Entities Finance
Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Hyperion DRM Implemented | John Moore | 2015-11-12 | Yes | DRM: Complete Assess Phase | 2015-05-08 | DRM: Complete Design Phase | 2015-06-24 | DRM: Complete Construct Phase | 2015-08-11 | DRM: Complete Implement Phase | 2015-10-02 | DRM: Complete Operate & Review Phase | 2015-11-12 | [8 empty] | High | High | Yes | May need additional resources. Delivery Risk: Willingness to comply with new change management process & controls |  | All SHUSA Entities Finance
Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Formal Governance over CoA/Hierarchies | John Moore | 2015-12-31 | No | Define roles/responsibilities for managing CoA | 2015-06-24 | Obtain acknowledgement from entities of understanding of Governance process | 2015-06-24 | Implement formal governance | 2015-12-31 | [12 empty] | High | Medium | No | Delivery Risk: Willingness to comply with new change management process & controls |  | All SHUSA Entities Finance
Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | FRS fed from HFM | Sean Mulcahy | 2015-12-31 | Yes | Map expected HFM capability to FRS reporting requirements | 2015-12-31 | Identify gaps in HFM/FRS mapping | 2015-12-31 | Develop plan for remediation of HFM/FRS mapping gaps | 2015-12-31 | Remediate HFM/FRS mapping gaps | 2015-12-31 | Design HFM/FRS integration | 2015-12-31 | Code HFM/FRS integration | 2015-12-31 | Test HFM/FRS integration | 2015-12-31 | Implement HFM/FRS integration | 2015-12-31 |  |  | High | High | Yes | IT may need additional resources. Delivery Risk: SHUSA SME Bandwidth for completing breadth of work |  | None
Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | Moody's fed from HFM | Eric Ratican | 2015-12-31 | Yes | Map expected HFM capability to Moody's reporting requirements | 2015-12-31 | Identify gaps in HFM/Moody's mapping | 2015-12-31 | Develop plan for remediation of HFM/Moody's mapping gaps | 2015-12-31 | Remediate HFM/Moody's mapping gaps | 2015-12-31 | Design HFM/Moody's integration | 2015-12-31 | Code HFM/Moody's integration | 2015-12-31 | Test HFM/Moody's integration | 2015-12-31 | Implement HFM/Moody's integration | 2015-12-31 |  |  | High | High | Yes | IT may need additional resources. Delivery Risk: SHUSA SME Bandwidth for completing breadth of work | Risk Transformation | Risk Data | Operational Risk | Op Risk Data
Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | Workiva fed from HFM | Kerry Marshall | 2016-02-29 | Yes | Map expected HFM capability to Workiva reporting requirements | 2016-02-29 | Identify gaps in HFM/Workiva mapping | 2016-02-29 | Develop plan for remediation of HFM/Workiva mapping gaps | 2016-02-29 | Remediate HFM/Workiva mapping gaps | 2016-02-29 | Design HFM/Workiva integration | 2016-02-29 | Code HFM/Workiva integration | 2016-02-29 | Test HFM/Workiva integration | 2016-02-29 | Implement HFM/Workiva integration | 2016-02-29 |  |  | High | High | Yes | IT may need additional resources. Delivery Risk: SHUSA SME Bandwidth for completing breadth of work |  | None
Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Fully functional CoA with hierarchy dimensionality | Nancy Reinhard | 2015-09-30 | Yes | Complete HFM implementation (dependency placeholder) | 2015-11-06 | [16 empty] | High | High | Yes | Same resources as above to deliver HFM.Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation |  | None
Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Reconciliation process In place between GL's and Hyperion | Nancy Reinhard | 2015-09-30 | Yes | Establish reconciliation process for SHUSA | 2015-09-30 | Establish reconciliation process for SBNA | 2015-09-30 | Establish reconciliation process for SCUSA | 2015-09-30 | Establish reconciliation process for BSI | 2015-09-30 | Establish reconciliation process for PR | 2015-09-30 | Establish reconciliation process for SIS | 2015-09-30 | Establish reconciliation process for Other Entities | 2015-09-30 |  |  |  |  | Medium | Medium | No | Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation |  | All SHUSA Entities Finance and Finance - Internal Control
Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Reconciliation process In place between Hyperion and Financial/regulatory reporting tools | Nancy Reinhard | 2015-09-30 | Yes | Establish reconciliation process for FRS | 2015-09-30 | Establish reconciliation process for Moody's | 2015-09-30 | Establish reconciliation process for Workiva | 2015-09-30 | [12 empty] | High | High | Yes | Need consultants to design process. Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation |  | All SHUSA Entities Finance and Finance - Internal Control
Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Reconciliatio process between reporting tools in place. | Nancy Reinhard | 2015-09-30 | Yes | Identify common elements between reporting | 2015-09-30 | Complete 4-way recon between Hyperion-FRS-Moody's-Workiva | 2015-09-30 | [14 empty] | High | High | Yes | Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation |  | Finance - Internal Control
Accounting, Tax, & Reporting | Comprehensive documentation of controls over reporting process (centralized and distributed components) | SOX level control documentation approved | Manuel Munoz | 2015-09-30 | No | Revise process for tax reporting | 2015-09-30 | Revise process for parent reporting | 2015-09-30 | Revise process for reg reporting | 2015-09-30 | Revise process for CCAR reg reporting | 2015-09-30 | Revise process for SEC reporting | 2015-09-30 | [8 empty] | Medium | Medium | Yes | Need consultants to develop documentation. Delivery Risk: Comprehensive cross-functional participation, expertise in documentation |  | Finance-Internal Control
Accounting, Tax, & Reporting | Comprehensive documentation of controls over reporting process (centralized and distributed components) | Change management process for SOX level control documentation in place. | Manuel Munoz | 2015-09-30 | No | Coordinate with internal controls (dependency) | 2015-09-30 | [16 empty] | Medium | Medium | No | Delivery Risk: Comprehensive cross-functional participation, expertise in documentation |  | Finance-Internal Control
Accounting, Tax, & Reporting | Improve efficiency of Regulatory Report production (Incorporate all legacy systems not completed as part of the original FRS implementation). | FRS source data optimization | Sean Mulcahy | 2015-12-31 | Yes | Enhance FRS: Complete Analysis | Completed | Enhance FRS: Complete Design | 2015-06-30 | Enhance FRS: Complete Development | 2015-09-30 | Enhance FRS: Complete Testing | 2015-10-31 | Enhance FRS: Complete UAT | 2015-12-31 | [8 empty] | High | High | Yes | Need internal or consulting resources. Delivery Risk: IT Execution |  | SBNA Operations - Chris Winter
Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | Inventory of SHUSA (SBNA/SCUSA) critical EUA's | John Moore | 2015-06-30 | Yes | [18 empty] | High | High | No | Delivery Risk: Bandwidth for completing large breadth of work |  | Finance - Internal Control
Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | Risk Rating of of SHUSA (SBNA/SCIUSA) critical EUA's and prioritized plan for compliance | John Moore | 2015-07-31 | Yes | [18 empty] | High | High | No | Delivery Risk: Bandwidth for completing large breadth of work |  | Finance-Internal Control
Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | SHUSA (SBNA/SCUSA) critical EUA's remediated | John Moore | 2015-12-31 | Yes | [18 empty] | High | High | No | Delivery Risk: Bandwidth for completing large breadth of work |  | Finance-Internal Control
Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Current State Assessment | Mike Boyle | Completed | No | Develop Data Flows (of pain points) from source to report | Completed | [16 empty] | Medium | Medium | No | completed |  | N/A - Deloiverable Completed
Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Conduct Quality Gap Assessment | Mike Boyle | Completed | No | Document areas of deficiency | Completed | [16 empty] | Medium | Medium | No | completed |  | N/A - Deloiverable Completed
Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Develop Recommendations | Mike Boyle | Completed | No | Develop recommendations to address areas of deficiency | Completed | [16 empty] | Medium | Medium | No | completed |  | N/A - Deloiverable Completed
Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Prioritize Data Areas | Mike Boyle | Completed | No | Prioritize remediation of deficiencies | Completed | [16 empty] | Medium | Medium | No | completed |  | N/A - Deloiverable Completed
Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Roadmap for remediation of Group reporting processes. | Mike Boyle | 2015-06-12 | No | Develop schedule for remediation | 2015-06-12 | [16 empty] | Medium | Medium | Yes | Need risk resources | Risk Transformation
Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Revised approach for remediation of data sources for Group reporting processes | Mike Boyle | 2015-09-30 | Yes | Revised approach to data sourcing | 2015-09-30 | [16 empty] | Medium | Medium | Yes | Need IT and risk resources | Risk Transformation
Accounting, Tax, & Reporting | Improve the quality of information in the general ledger needed to complete the chart of accounts and execute reporting | Remediate gaps in feeds from entity GL's | Nancy Reinhard | 2015-11-06 | Yes | [22 empty] | Risk Transformation | All SHUSA Entities
Accounting, Tax, & Reporting | Improve the amount of general ledger information available from direct system feeds rather than manual processes | Hyperion fed from RDA | Ignacio Garijo Garde | 2015-12-31 | Yes | Inventory Manual Processes (SBNA) | TBD | Prioritize Processes Changes | TBD | Develop Schedule to Remediate | 2015-05-31 | Develop System Feeds | 2015-12-31 | [14 empty] | Risk Transformation
Accounting, Tax, & Reporting | Deployment of a uniform reconciliation tool (SHUSA and subsidiaries) | Unifrom Automated reconciliation | John Moore | 2015-12-31 | Yes | Evaluate and select the appropriate reconciliation tool | 2015-08-31 | Develop schedule and plan for SBNA deployment | 2015-08-31 | Install tool for SBNA | 2015-12-31 | Develop schedule and plan for other entity deployments | 2015-12-31 | [15 empty] | SBNA Operations - Chris Winter
Accounting, Tax, & Reporting | Finalize the implementation of Target Operating Model | Target Operating Model | Ken Goldman | 2015-12-31 | No | Complete Definition of Target Operating Model | 2015-12-31 | [16 empty] | Low | Low | No |  |  | None
Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SHUSA adherence to revised accounting policies | Jessie Velazquez | 2015-12-31 | No | Procedures revised at SHUSA | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SHUSA | 2015-11-30 | [12 empty] | Medium | Medium | Yes | May need resources to review and revise policies. |  | All SHUSA Entities
Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SBNA adherence to revised accounting policies | M Ballenger | 2015-12-31 | No | Procedures revised at SBNA | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SBNA | 2015-11-30 | [12 empty] | Medium | Medium | Yes | May need resources to review and revise policies. |  | Entity SBNA
Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SCUSA adherence to revised accounting policies | J Kulas | 2015-12-31 | No | Procedures revised at SCUSA | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SCUSA | 2015-11-30 | [12 empty] | Medium | Medium | Yes | May need resources to review and revise policies. |  | Entity SCUSA
Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | BSI adherence to revised accounting policies | E Franco Espinosa | 2015-12-31 | No | Procedures revised at BSOI | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at BSI | 2015-11-30 | [12 empty] | Medium | Medium | Yes | May need resources to review and revise policies. |  | Entity BSI
Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | PR adherence to revised accounting policies | A. Guzman | 2015-12-31 | No | Procedures revised at PR | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at PR | 2015-11-30 | [12 empty] | Medium | Medium | Yes | May need resources to review and revise policies. |  | Entity PR
Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | SIS adherence to revised accounting policies | F. Sempre | 2015-12-31 | No | Procedures revised at SIS | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SIS | 2015-11-30 | [12 empty] | Medium | Medium | Yes | May need resources to review and revise policies. |  | Entity SIS
Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Other IHC entities adherence to revised accounting policies | Jessie Velazquez | 2015-12-31 | No | Procedures revised at Other Entities | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at Other Entities | 2015-11-30 | [12 empty] | Medium | Medium | Yes | May need resources to review and revise policies. |  | Entities - Other IHC
Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Enhance SHUSA Capital policy | Bart Simon | 2015-12-31 | No | Governance: -Enhance the roles and responsibilities of the Board members, senior management and auxiliary functions -Prescribe more specific governance including approval hierarchy and committees for subsidiary capital decisions -Policy Board approval, including all milestones for this deliverable | 2015-12-31 | Capital goals and targets methodology : - At sub level ID and quant critical stakeholder requirements in stress - Enhance study of experience in stress - Determine capital goals at each sub & analysis impact of changes at subs on SHUSA -Include analysis for each entity and document the associated loss absorbency at the subsidiary and the consolidated capital position. A key focus of the analysis will include management’s evaluation of the SCUSA minority interest within consolidated capital - Improve alignment between the risk identification process and target setting --Develop analysis to demonstrate how the post-stress minimum will support the target debt rating in stress and allow each entity to maintain funding plans and actions -Consider liquidity risk management strategies and metrics in identifying capital goals -Document impact of modifications to strategies or metrics on changes to capital goals on a dynamic basis -Analyse the impact on the consolidated capital position if all subsidiaries operating at their post-stress minimum -Set capital goals such that the capital required to access capital markets is differentiated from requirements to remain a going concern. -Complete analysis of capital required to absorb stress at a subsidiary level and demonstrate how those directly build to the consolidated stress absorption buffer -Include procedures to consider changes to the composition and inherent risks on the balance sheet to update capital targets on a dynamic basis | 2015-09-05 | Capital assessment methodology: - Enhance doc of process & responsibilities & deliverables - ID specific analysis (ratios, changes in biz profile, strategic initiatives, risk tolerance metrics, etc.) required for assessment - Develop draft of capital assessment report (companion to current deck) -Present capital assessment and deployment report each quarter at operating entities -Clarify the linkage between the capital assessment and the capital ratio forecasts under different scenarios as well as time horizons | 2015-09-05 | Dividend and capital action methodology: -Develop analytical approaches for capital distribution to design quantitative triggers for baseline and stress scenarios -Incorporate the key indicators (e.g. earnings, balance sheet growth, macroeconomic factors driving SHUSA’s operations) that influence the size, timing and form of capital distributions - Compile data required for analysis of indicators that could drive changes to capital actions - Assign specific responsibilities to individuals across entities for preparing supporting analysis and recommending capital actions to appropriate committees - Develop a governance structure to allow for coordinated senior management overview and consistency with the capital policy, and determine communication expectations -Integrate capital distribution procedures which include timing and approval hierarchy for subsidiary capital action decisions into policy -Set forth specific requirements for deliverables and supporting analysis provided to senior management and board committees to substantiate capital distribution decisions -Document the comprehensive plan thoroughly and clearly present key factors and underlying assumptions that will support the distribution amount and how modifications to those factors and assumptions could influence changes in the future- -Clearly articulate events and circumstances that require a reevaluation of capital distributions within the capital policy -Align the analysis with contingency plans and incorporate capital targets, expected capital position, projected earnings levels, planned balance sheet growth and parent company liquidity management | TBD | Incorporate all new methodology / enhancements into Policy Admin reviewed Capital Policy | 2015-12-30 | Enhance Capital Policy for CCAR 2017: 1. Develop methodology for evaluating changes to risk tolerance metrics and capital targets, with more explicit quantitative linkages 2. Capital target settings to: -Originate capital target settings at each entity based on the risk identification process -Link targets directly to each identified risk with documentation of models that were used to quantify that risk or qualitative judgment used for estimation -Organize information by business line and identified risks to facilitate review and challenge sessions | 2016-12-31 | [6 empty] | Medium | Low | No
Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Enhance SHUSA Capital contingency policy | Bart Simon | 2015-12-05 | No | Incorporate FRS and IA feedback into existing draft policy - Align capital contingency process with updated capital policy methodology documents - Include 'capital triggers' analysis | 2015-11-30 | Develop appropriate governance over capital contingency process across entities. | 2015-12-02 | Deliver contingency policy to policy admin | 2015-11-30 | Complete policy and approval governance process | 2015-12-05 | [10 empty] | Medium | Low | No |  | Risk Transformation
Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Capital Policies for subs (SBNA, SCUSA and IHCs) commensurate with size / complexity | Bart Simon | 2015-12-31 | No | Establish capital management governance structure at each entity | TBD | Capital goals and targets methodology document - ID and quant critical stakeholder requirements in stress - Enhance study of experience in stress - Risk Inventory from Risk ID w/ quant source - Roles & Responsibilities | 2015-09-05 | Dividend and capital action methodology document - ID all metrics and analysis required to develop 'capital triggers' - Compile data required for analysis of indicators that could drive changes to capital actions - Determine roles & responsibilities for analysis - Determine governance/communication expectations | TBD | Develop early warning indicators | 2015-05-15 | Define individual entity roles & responsibilities | TBD | [8 empty] | Medium | Medium | Yes
Capital Management | Operationalize processes for escalation to board, potential suspension of capital actions, and implementation of contingency plans (improve analysis and documentation of contingency actions) | Enhance/Update Contingent Capital Plan | Bart Simon | 2016-04-05 | No | Re-define process for which contingent actions are identified, quantified and assessed | 2015-10-15 | Update inventory of potential contingent capital actions | 2015-10-30 | Align potential contingent capital actions with liquidity, strategic planning, & resolution planning (dependencies…) | 2015-10-15 | Quantify potential contingent capital actions | 2016-03-20 | Board Approval of contingent capital plan | 2016-04-05 | [8 empty] | Medium | Low | No
Capital Management | Enhance capital adequacy and capital planning governance | Improved quality of information presented | Simon / Watson | 2015-09-30 | No | Establish team for template creation and population | TBD | Create common templates | TBD | Develop process for review of content prior to presentation | TBD | [12 empty] | High | High | Yes
Capital Management | Enhance capital adequacy and capital planning governance | Improve completeness of info presented | Simon / Watson | 2015-12-31 | No | Review final structures to determine 'new' reporting expectations and locations | TBD | Develop full inventory of models and processes for review | TBD | Develop full inventory of results for review | TBD | Schedule and track review of inventories at appropriate level of governance body | TBD | [10 empty] | Low | Medium | No |  | Non CART Workstream | Finance
Capital Management | Enhance capital adequacy and capital planning governance | Add clarity to material provided for consideration of dividend | Bart Simon | 2015-12-31 | No | See SHUSA Capital Policy for details | TBD
Capital Management | Enhance capital adequacy and capital planning governance | Enhance Board and Snr. Management Training | Simon / Watson | 2015-12-31 | No | Outline required training at Board and Senior Management | TBD | Schedule training | TBD | Determine training provider (internal / external) | TBD | [12 empty] | Low | Low | Yes
Capital Management | Enhance capital adequacy and capital planning governance | Detailed Procedures for E2E processes | Bart Simon | 2015-12-31 | No | Determine review governance / review process for E2E procedures | TBD | Confirm E2E process map owners and responsibilities for procedures | TBD | First draft of procedures for all E2E process steps | TBD | Central review of draft procedures | TBD | [10 empty] | High | Medium | Yes
Capital Management | Enhance capital adequacy and capital planning governance | Establish clear accountabilities | TBD-McKinsey to provide dates | TBD | No | This needs to be part of the 'bigger' Governance discussion. | TBD | [19 empty] | completed, | Non CART Workstream | RCRD
Capital Management | Establish staffing and conduct adequate training across the end-to-end CCAR review cycle | Establish Staffing & Conduct Training - TBD | TBD-J. Watson to provide dates | TBD | No | [22 empty] | Non CART Workstream | Internal Audit
Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Establish set of reconciled as-of and clean historical data | IT/IMAD | TBD | Yes | Complete gap assessment against data quality | TBD | Develop remediation plan to close prioritized gaps | TBD | Execute remediation plan to close prioritized gaps | TBD | Operationalize source system(s) for 2016 CCAR Run | TBD | [14 empty] | Model Development | Model Validation
Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Develop end-to-end stress-testing platform | TBD | TBD | Yes | Develop BHC specific Scenarios that are clearly linked to the RISK ID process and that are BHC specific | TBD | Develop model execution platform (for PPNR, Credit Loss, etc.) | TBD | Develop SAS balance-walk engine | TBD | Develop integration of IHC data | TBD | Develop ability to consolidate SHUSA IHC information | TBD | Develop RWA / capital engine | TBD | Populate Y14A report / XML | TBD | [8 empty] | Non CART Workstream
Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Base and stress forecasts for each IHC entity | TBD | TBD | No | Communicate modeling strategy | TBD | Develop forecasting processes for non-modeled line-items (PPNR) | TBD | Develop forecasting processes for non-modeled line-items (Credit) | TBD | Develop supporting documentation | TBD | Internal Control review of process (IC, IA, MRM, etc.) | TBD | IHC 'Capital Plan' | TBD | [10 empty] | Non CART Workstream | Finance - Internal Controls
Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Detailed E2E processes maps | Bart Simon | 2015-12-31 | No | Build team for compilation of E2E process maps | TBD | Process owners deliver individual maps | TBD | Aggregation and review of full process maps | TBD | Approval of full process maps / full process | TBD | [10 empty] | High | Medium | Yes
Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Comprehensive Assessment from Internal Audit | Vik Soni | 2016-03-31 | No | [22 empty] | Non CART Workstream | Finance - Strategic Planning
Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Comprehensive Assessment from Internal Controls | M. Munoz | 2015-12-31 | No | [22 empty] | Non CART Workstream | Finance - Strategic Planning
Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Model Validation / MRM | TBD | TBD | No | [22 empty] | Non CART Workstream | Finance - Strategic Planning
Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Increase the granularity of forecasting of on and off balance sheet product level information. This process will be extended to include all material IHCs for CCAR 2016 inclusion | John Barris | 2015-11-30 | No | Management Control/Strategic Planning build out SAS forecasting models | 2015-09-30 | SAS Models validated | 2015-12-31 | GAP level of forecasts with RWA needed levels | 2015-10-30 | Develop any methodologies or assumptions for gaps and obtain governance approvals | 2015-12-31 | [10 empty] | Medium | Low | No
Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Finalization of the Basel III methodology that is approved and fully documented and Forecasting methodology that is consistent with the final approved SHUSA Basel III methodology | John Barris | 2015-07-06 | No | RCRD/Accounting to produce final Basel III methodology for numerator and denominator | 2015-04-01 | CPG to incorporate final Basel III methodology into forecasting | 2015-07-06 | Update forecasting documentation obtain final approval | 2015-07-06 | [12 empty] | Medium | Medium | No
Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Internal Audit to review the RWA methodology for both actuals and forecasts for CCAR 2016 | John Barris | 2015-12-31 | No | Review of Actual methodology for RWA | 2015-06-01 | Review of forecasting methodology for Forecasting | 2015-12-31 | [14 empty] | Low | Low | No | completed | Non CART Workstream | RCRD
Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | RWA methodology will be well documented and all assumptions will be approved by the appropriate governance committees prior to use, including validated SSFA methodology developed and run by 3rd party external vendor | John Barris | 2015-12-31 | No | Obtain approval for SSFA 3rd Party Vendor | 2015-07-31 | Vendor to develop methodology with CPG | 2015-09-30 | MRM to validate SSFA models | 2015-12-31 | Provide Cusips and produce results | 2016-03-01 | [10 empty] | High | High | Yes |  | Non CART Workstream | Finance - Strategic Planning
Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Implement a framework for RWA sensitivity analysis and back testing for CCAR 2016 that is well documented | John Barris | 2016-04-04 | No | Develop necessary analysis and back testing needs | 2015-09-30 | Gap needs to abilities | 2015-10-30 | Develop plan for analysis and back testing for CCAR 2016 | 2015-12-31 | Document results of analysis and back testing | 2015-04-04 | [10 empty] | High | High | No |  | Non CART Workstream | Finance - Strategic Planning
Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | RWA process will be reviewed and tested by internal controls for CCAR 2016 | John Barris | 2016-03-31 | No | Work with IC to produce necessary RWA control framework | 2015-07-30 | Add controls into the RWA process as outlined | 2015-12-31 | Produce RWA for CCAR 2016 | 2016-04-04 | IC to conduct control test | 2016-05-30 | [10 empty] | Low | Low | No
Capital Management | Improve financial analysis at consolidated and legal entity view | Review of Previous Capital Plan with comments on areas for improvement | Bart Simon | 2015-06-01 | No | Comments delivered to Capital Plan contributors | TBD | [16 empty] | Low | Low | No
Capital Management | Improve financial analysis at consolidated and legal entity view | Consolidated and legal entity historical results in Planning Tree delivered | TBD | TBD | Yes
Capital Management | Improve financial analysis at consolidated and legal entity view | Strategic plan at consolidated and legal entity in Planning Tree | D. Budington | TBD | Yes | [22 empty] | Non CART Workstream | Finance - Strategic Planning
Capital Management | Improve financial analysis at consolidated and legal entity view | Baseline and Stress at consolidated and legal entity in Planning Tree | John Barris | TBD | Yes | [18 empty] | High | High | Yes
Capital Management | Improve financial analysis at consolidated and legal entity view | Financial analysis in Capital Plan | John Barris | TBD | Yes | Determine roles and review expectations | TBD | Establish "team" for review | TBD | Preplan all charts graphs | TBD | Reviewed analysis in Capital Plan | TBD | [10 empty] | Medium | Medium | Yes
Capital Management | Establish enhanced monthly capital reporting / tracking | Develop / Enhance Monthly Report | John Barris | TBD | No | Gap Current Report to Management Needs | TBD | Develop remediation plan for executions | TBD | Develop draft report for approval | TBD
Capital Management | Establish enhanced monthly capital reporting / tracking | Align to GL and RCRD | John Barris | TBD | Yes | Integrate Proforma forecast for monthly cycle | 2015-04-01 | Align to GL through Essbase | TBD
Capital Management | Establish enhanced monthly capital reporting / tracking | Enhance with Current Capital LOB Allocations | John Barris | TBD | No | Integrate LOB allocations into report | TBD
Capital Management | Establish enhanced monthly capital reporting / tracking | Develop forecasting ability with Stress overlays | John Barris | TBD | No | Develop process to use monthly actuals to true up forecast | TBD | Develop methodology to overlay CCAR/Mid Cycle stress impacts | TBD | Finalize Reporting format and governance approval | TBD
Capital Management | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements | Quarterly Decks for MCC | Bart Simon | 2016-04-06 | No | Q1 Deck | 2015-06-25 | Q2 Deck | 2015-09-25 | Q3 Deck | 2015-12-25 | Q4 Deck = 2016 Capital Plan | 2016-04-06 | [10 empty] | Low | Low | No
Capital Management | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements | Quarterly Report for Board | Bart Simon | 2016-04-06 | No | Define report structure, details and delivery mechanism | TBD | Define roles and responsibilities for compilation | TBD | Report included in quarterly Board Package | TBD | [12 empty] | Medium | High | No
Capital Management | Enhance Capital Plan for 2016 | Review 2014 Capital Plan | Bart Simon | 2015-06-01 | No | CMG Review of Previous Capital Plan | 2015-06-01 | Incorporate FRS Feedback of Previous Capital Plan | 2015-06-01 | [14 empty] | High | Low | No
Capital Management | Enhance Capital Plan for 2016 | Align results & methodology presentation with 'new' segmentation | Bart Simon | 2015-09-30 | Yes | Define revised presentation tables | 2015-09-30 | [16 empty] | High | High | No
Capital Management | Enhance Capital Plan for 2016 | IHC Capital Plan | Bart Simon | 2016-04-04 | No | Create Project Plan for each entity: SBNA, SCUSA, Miami, NY, Puerto Rico | 2015-07-31 | [16 empty] | High | High | Yes
Capital Management | Enhance Capital Plan for 2016 | Methodology Appendix for Capital Plan | Contributors | 2015-12-31 | No | Contributors Draft/Revise Methodology Sections | 2015-08-01 | Improve existing summary documentation in Capital Plan in workiva per ROPE | 2015-08-01 | Review Team - Capital Management, Working Groups, Peer Review | 2015-12-31 | [12 empty] | High | Low | No
Capital Management | Enhance Capital Plan for 2016 | Results for CCAR Run | Contributors | 2016-03-20 | No | Contributors Draft/Update Results for CCAR Run | 2016-03-10 | Improve existing summary documentation in Capital Plan in workiva per ROPE | 2016-03-10 | Review Team - Capital Management, Working Groups, Peer Review | 2016-03-30 | [12 empty] | High | Medium | Yes
Capital Management | Enhance Capital Plan for 2016 | Enhance Capital Plan Documentation | Bart Simon | 2016-03-20 | No | Improve automation / linkage to wDesk | 2016-03-20 | Improve summary documentation in Capital Plan in workiva per ROPE | 2016-03-20 | Update definition of available capital: -Develop a comprehensive process to evaluate capital requirements under varying circumstances -Consider rating agency requirements the credit rating of the bank in stress based on both capital levels and risk position as part of the comprehensive process. -Update the target setting process and evaluation of how the current stress test results impact capital targets with information and analytical requirements listed in the capital policy | 2015-12-31 | Update criteria for making decisions related to all capital actions: -Improve the analysis required to support capital distribution decisions -Include required documentation of the analysis contemplated in the previous response in the capital plan -Support the sizing of any capital distributions, as well as key factors that will be monitored to ensure continued appropriateness of both the distribution and its size | 2015-12-31 | Criteria for making decisions related to capital actions: -Include additional analysis in the capital plan to support other capital actions including the repurchase of capital instruments. This analysis shall support the sizing of any additional capital actions as well as key factors to be monitored to ensure continued appropriateness of the repurchase -Update criteria related to events, circumstances and key indicators that could result in reevaluation of the capital repurchase that could lead to a reduced size or elimination | 2016-04-04 | [8 empty] | High | Medium | Yes
Capital Management | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board | Procedures for developing and review of alternative capital actions | Bart Simon | 2015-12-31 | No | Determine Roles & Responsibilities | TBD | Determine Governance | TBD | [14 empty] | Low | Low | No
Capital Management | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board | Alternative Capital Actions | Bart Simon | 2016-04-04 | No | Execute process to develop alternative capital actions | TBD | Review alternative actions w/ appropriate governance bodies | TBD | Include alternative actions in 2016 Capital Plan | TBD | [12 empty] | Low | Low | No
Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Develop, document and test customized SAS forecast and aggregation tool | D. Budington | 2015-10-09 | Yes | Define preliminary data requirements for forecast execution (based on 2015 CCAR process) | 2015-04-15 | Design customized SAS forecast and aggregation tool, including detailed specification of capabilities and hand-offs | 2015-05-15 | Build customized SAS forecast solution, including initial testing and sign-off of capabilities and design | 2015-06-30 | Test forecast and aggregation tool | 2015-10-09 | Document forecast and aggregation tool | 2015-10-09
CART- Finance Transformation Deliverable Inventory

## Risk Transformation
|  | Yes | [12 empty] | High
|  | No | [12 empty] | Medium
Low
Sub-workstream | Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Workstream Interdependency | Inter-dependency Comment | Workstream Interdependency2 | Inter-dependency Comment2 | Workstream Interdependency3 | Inter-dependency Comment3 | Workstream Interdependency4 | Inter-dependency Comment4 | Workstream Interdependency5 | Inter-dependency Comment5
Re-design and embed Risk Appetite Statement | Re-design SHUSA RAS | SHUSA RAS reporting and breach escalation processes | Edward Smith | 2015-08-10 | No | Draft RAS |  | Final RAS |  | Draft process |  | Final process |  |  |  | High | Low | Yes
Re-design and embed Risk Appetite Statement | Re-design SHUSA RAS | SHUSA-level RAS | Edward Smith | 2015-08-10 | Yes | Delivery of training | [9 empty] | Medium | Low | Yes
Re-design and embed Risk Appetite Statement | Re-design SHUSA RAS | Board approval for SHUSA RAS | Edward Smith | 2015-09-07 | No | Board approval | [9 empty] | Low | Low | Yes |  | Non CART Workstream | Ensure integration into Board agenda
Re-design and embed Risk Appetite Statement | Re-design SHUSA RAS | RAS business and data requirements | Edward Smith | 2015-09-25 | Yes | Draft of materials |  | Final materials and delivery of communication | [7 empty] | Medium | Low | Yes
Re-design and embed Risk Appetite Statement | Re-design SHUSA RAS | Board-level RAS communications | Edward Smith | 2015-09-25 | No | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Low | No |  | Non CART Workstream | Ensure integration into Board agenda
Re-design and embed Risk Appetite Statement | Cascade RAS to priority subsidiaries | RAS for priority subsidiaries (SBNA & SCUSA) | Edward Smith | 2015-11-06 | Yes | Draft approach |  | Final approach | [7 empty] | Medium | Low | Yes
Re-design and embed Risk Appetite Statement | Cascade RAS to priority subsidiaries | Delivery of enterprise-level RAS comms. & socialization materials | Edward Smith | 2015-12-28 | No | Draft RAS for priority subs and list of metrics |  | Input from subs |  | Final RAS for priority subs and list of metrics | [5 empty] | High | Low | Yes |  | Non CART Workstream | Enterprise wide comms need to be co-ordinated
Re-design and embed Risk Appetite Statement | Initialize embedding of RAS in material processes | Updated process maps for key processes with explicit RAS links | Edward Smith | 2015-11-27 | No | Draft process |  | Final process | [7 empty] | Medium | Low | Yes |  | Non CART Workstream | Need to coordinate with process owners
Strengthen Board and Management oversight | Board risk committee training | Board risk training curriculum and schedule | Edward Smith | 2015-07-27 | No | Board approval | [9 empty] | Low | Low | Yes
Strengthen Board and Management oversight | Board risk committee training | Board risk training sessions delivered - e.g. RAS | Edward Smith | 2015-09-28 | No | Draft of training materials, including training schedule |  | Final training materials, including training schedule |  | Delivery of two training sessions | [5 empty] | Medium | Low | Yes |  | Non CART Workstream | Ensure integration into Board agenda
Strengthen Board and Management oversight | Board risk committee training | Board risk training sessions delivered - e.g. CCAR Governance | Edward Smith | 2015-11-30 | No | Key stakeholder engagement |  | Draft governance and coordination mechanisms |  | Final governance and coordination mechanisms | [5 empty] | High | Medium | Yes |  | Non CART Workstream | Ensure integration into Board agenda
Strengthen Board and Management oversight | Strengthen SHUSA Board / Mgt. Committee guidance | Diagnostic of Risk Mgt. Committee (includes relationship with parent) | John Hennessey | 2015-06-29 | No | Board approval | [9 empty] | Low | Low | Yes
Strengthen Board and Management oversight | Strengthen SHUSA Board / Mgt. Committee guidance | Definition of composition / mandates / charters for priority committees | John Hennessey | 2015-09-28 | No | Group approval | [9 empty] | Medium | Medium | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Strengthen Board and Management oversight | Strengthen SHUSA Board / Mgt. Committee guidance | Board approval for high priority committee changes | John Hennessey | 2015-09-28 | No | Draft of diagnostic materials |  | Final materials and delivery of diagnostic | [7 empty] | Medium | Low | Yes |  | Non CART Workstream | Ensure integration into Board agenda
Strengthen Board and Management oversight | Strengthen SHUSA Board / Mgt. Committee guidance | Definition of composition / mandates / charters for remaining committees | John Hennessey | 2015-12-28 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Strengthen Board and Management oversight | Strengthen SHUSA Board / Mgt. Committee guidance | Board approval for low priority committee changes | John Hennessey | 2015-12-28 | No | Board approval | [9 empty] | Low | Low | Yes |  | Non CART Workstream | Ensure integration into Board agenda
Re-design operating model and talent mgmt | Change & enforce Risk Leadership reporting lines | Updated Risk leadership reporting lines | John Hennessey | 2015-06-15 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Re-design operating model and talent mgmt | Change & enforce Risk Leadership reporting lines | Board-approved Risk leadership organization | John Hennessey | 2015-06-29 | No | Board approval | [9 empty] | Low | Low | Yes
Re-design operating model and talent mgmt | Articulate 3 LoD across SHUSA-subsidiary relationships | Board-approved SHUSA frameworks | John Hennessey | 2015-07-27 | No | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No |  | Non CART Workstream | Ensure integration into Board agenda
Re-design operating model and talent mgmt | Articulate 3 LoD across SHUSA-subsidiary relationships | Cascaded SHUSA frameworks to subsidiaries | John Hennessey | 2015-09-28 | Yes | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No |  | Operational Risk |  | Model Development |  | Model Risk Management
Re-design operating model and talent mgmt | Articulate 3 LoD across SHUSA-subsidiary relationships | Standardized policies and procedures, aligned to new frameworks for key risk types | John Hennessey | 2015-12-28 | No | Draft 3LoD principles |  | Final 3LoD principles | [7 empty] | Low | Low | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Re-design operating model and talent mgmt | Design Risk management organizational structures & staffing | Operating model design including headcount analysis | John Hennessey | 2015-08-03 | No | Draft reporting lines |  | Key stakeholder engagement |  | Final (formalization of) reporting lines | [5 empty] | Low | Low | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Re-design operating model and talent mgmt | Design Risk management organizational structures & staffing | Recruitment of senior Risk and other high priority staff | Kerrie Maitland | 2015-11-30 | No | Board approval | [9 empty] | Medium | Low | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Re-design operating model and talent mgmt | Detail interactions between risk groups for critical processes | Interaction definition | John Hennessey | 2015-10-03 | No | Draft of operating model |  | Final operating model | [7 empty] | High | Medium | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Re-design operating model and talent mgmt | Detail interactions between risk groups for critical processes | Critical processes updated | John Hennessey | 2015-09-14 | No | Draft headcount |  | Delivery of skills / staffing assessment |  | Hiring / redeployment strategy | [5 empty] | High | Medium | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management
Re-design operating model and talent mgmt | Talaent management | Perform a talent review and assessment of key risk staff and develop a strategy to address gaps (e.g. hiring, training, leadership programs, etc.) and begin rolling out hiring strategy to fill staffing gaps | John Hennessey | TBC | No | Draft of communication and training materials for enterprise-wide communication |  | Delivery of final communication and training materials for enterprise-wide communication |  | Development of job descriptions |  | Delivery of enterprise-wide training |  |  |  | High | Medium | Yes |  | Operational Risk |  | Model Development |  | Model Risk Management |  | Model Risk Management
Re-design operating model and talent mgmt | Talaent management | Articulation of a strong and desired risk culture and creation of risk communication forums (e.g. intranet, Risk Town Halls, etc.) | John Hennessey | TBC | No | Validation of updated frameworks | [9 empty] | Low | Low | No
Risk Measurement-Create effective risk ID and assessment process | Enhance Risk ID and Assessment process | Documentation of top-down risk aggregation | Edward Smith / Diane Allaire | 2015-06-29 | No | Board approval | [9 empty] | Low | Low | No |  | Non CART Workstream | Data & IT
Risk Measurement-Create effective risk ID and assessment process | Enhance Risk ID and Assessment process | Framework to identify material risks, including tools, templates, risk taxonomy, guidance, policies and procedures | Edward Smith / Diane Allaire | 2015-07-27 | No | Draft of assessment |  | Delivery of assessment |  | Prioritization of enhancements |  | Final plan for enhancements, given stakeholder input |  | Standardization of all policies / procedures |  | Medium | Low | No
Risk Measurement-Create effective risk ID and assessment process | Enhance Risk ID and Assessment process | Definition of risk ID foundational elements, multi-year enhancement goals | Edward Smith / Diane Allaire | 2015-09-07 | No | Draft definition of risk ID/assessment process and plan for execution |  | Final definition of risk ID/assessment process and plan for execution |  | Communication to key stakeholders | [5 empty] | Low | Medium | No |  | Operational Risk
Risk Measurement-Create effective risk ID and assessment process | Enhance Risk ID and Assessment process | Clear linkages established between Risk ID output to capital planning scenario generation process | Edward Smith / Diane Allaire | 2015-11-01 | No | Board approval | [9 empty] | Low | Low | No |  | Non CART Workstream | CCAR
Risk Measurement-Create effective risk ID and assessment process | Enhance Risk ID and Assessment process | Risk ID / Assess. business and data requirements, drawing upon process to create risk register | Edward Smith / Diane Allaire | 2015-11-01 | Yes | Conduct bottom-up risk identification |  | Aggregate, review & challenge |  | Conduct top-down risk identification |  | Draft of risk register |  | Final risk register |  | High | High | Yes
Risk Measurement-Create effective risk ID and assessment process | Enhance Risk ID and Assessment process | Risk register for modeled and non-modeled risk with reporting to Board and Snr mgt. | Edward Smith / Diane Allaire | 2015-11-01 | Yes | Draft policy and procedures for risk ID and assessment cycle |  | Final policy and procedures for risk ID and assessment cycle |  | Communication of policies/procedures to key stakeholders | [5 empty] | Medium | Low | No
Financial Risk Mgmt-Design and operationalize | Conduct high level of credit risk management | High level wholesale credit process review incl. limits / controls and DoA at SCUSA and SBNA | TBD | 2015-11-15 | No | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Medium | No
Financial Risk Mgmt-Design and operationalize | Conduct liquidity risk gap analysis | Definition of target liq. risk capabilities, current state review and remediation plan | TBD | 2015-12-14 | No | Proposed recommendations |  | Approved recommendations |  | Updated Credit Policy | [5 empty] | Medium | Medium | Yes
Update internal reporting | Enhance internal reporting | Assessment of current reporting landscape with quick win enhancements | Edward Smith | 2015-06-29 | No | Draft framework |  | Final framework | [7 empty] | Medium | Medium | Yes
Update internal reporting | Enhance internal reporting | Definition of target risk reporting landscape | Edward Smith | 2015-08-10 | Yes | Definition of liquidity risk capabilities |  | Current state vs. capabilities |  | Remediation plan | [5 empty] | Medium | Medium | Yes |  | Non CART Workstream | Data & IT
Update internal reporting | Enhance internal reporting | Template reports and socialization of high priority reports | Edward Smith | 2015-09-21 | No | Initial review of risks |  | Scenario and impact analysis |  | Remediation plan |  | Business and data requirements |  |  |  | TBD | TBD | Yes
Update internal reporting | Enhance internal reporting | Operationalization of high priority reports e.g. allocate reporting resources | Edward Smith | 2015-11-15 | Yes | Initial review of framework |  | Process and associated tools |  | Documented decision authority |  | Business and data requirements |  |  |  | TBD | TBD | Yes |  | Non CART Workstream | Data & IT
Update internal reporting | Enhance internal reporting | Template reports and socialization of low priority reports | Edward Smith | 2015-12-28 | No | Risk reporting landscape outline | [9 empty] | Low | Low | Yes
CART- Risk Transformation Deliverable Inventory

## Operational Risk
|  | Yes | [12 empty] | High
|  | No | [12 empty] | Medium
Low
Initiative | Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | CCAR | IHC | ELS | Comments | Workstream Interdependency | Inter-dependency Comment | Workstream Interdependency2 | Inter-dependency Comment2 | Workstream Interdependency3 | Inter-dependency Comment3 | Workstream Interdependency4 | Inter-dependency Comment4 | Workstream Interdependency5 | Inter-dependency Comment5
Risk Appetite | Simplify SHUSA Operational Risk Tolerance Statement Limits | Enhanced SHUSA operational risk limits implemented, monitored and reported | Sean O'Malley | 2015-09-30 | No | A documented set of recommended enhanced operational risk limits with clear rationale, definitions and thresholds |  | SHUSA Board-approved enhanced operational risk limits and thresholds. |  | Implemented processes to effectively monitor and report on enhanced operational risk limits. | [5 empty] | High | Medium | No | No | Yes | No |  | Risk Transformation | ERM, owner of Risk Transformation, will drive risk appetite activities including methodology, timing, etc | Non CART Workstream | SHUSA subsidiaries/future subsidiaries - data input to operational risk tolerance limits | Non CART Workstream | Board schedule, as Board approval may be required
Risk Appetite | Align with Capital Measures described in the Basel Consultative document (Total Potential OR Losses as a % of Gross Income, Single OR Loss Event > $10MM) | Enhanced SHUSA operational risk limits implemented, monitored and reported | Sean O'Malley | 2015-09-30 | No | A documented set of recommended enhanced operational risk limits with clear rationale, definitions and thresholds |  | SHUSA Board-approved enhanced operational risk limits and thresholds. |  | Implemented processes to effectively monitor and report on enhanced operational risk limits. | [5 empty] | High | Medium | No | No | Yes | No |  | Risk Transformation | ERM, owner of Risk Transformation, will drive risk appetite activities including methodology, timing, etc | Non CART Workstream | Board schedule, as Board approval may be required
Governance & Organization | Determine OR organizational structure between SHUSA and Subsidiaries | Approved short term (year 1) operational risk management operating model for SHUSA and it subsidiaries | Steve Bhatti | 2015-11-30 | No | A documented, recommended short term (year 1) operational risk management operating model for SHUSA and it subsidiaries including roles and responsibilities clearly defined using the RACI method | [9 empty] | High | Low | No | No | Yes | No |  | Risk Transformation | Organizational Structure - 3 Lines of Defense and Parent-Subsidiary Relationship
Governance & Organization | Determine OR organizational structure between SHUSA and Subsidiaries | Approved medium term (years 2/3) operational risk management operating model for SHUSA and its subsidiaries | Steve Bhatti | 2015-11-30 | No | A documented, recommended medium term (years2/3) operational risk management operating model for SHUSA and its subsidiaries including roles and responsibilities clearly defined using the RACI method | [9 empty] | High | Low | No | No | Yes | No |  | Risk Transformation | Organizational Structure - 3 Lines of Defense and Parent-Subsidiary Relationship
Governance & Organization | Determine and select short-term / medium-term resource requirements (internal and external) to deliver Year 1/2/3 priorities | Approved operational risk management staffing assessment for both the short term (year 1) and medium term (years 2/3) operating models | Steve Bhatti | 2015-11-30 | No | Documented results from an operational risk management staffing assessment for both the short term (year 1) and medium term (years 2/3) operating models | [9 empty] | High | Low | No | No | Yes | No |  | Risk Transformation | Organizational Structure - 3 Lines of Defense and Parent-Subsidiary Relationship
Governance & Organization | Recruit and onboard necessary talent | Active recruitment of SHUSA ORM staff for short term (year 1) operating model | Steve Bhatti | 2015-11-30 | No | Initial recruitment for SHUSA ORM based on the short term (year 1) operating model | [9 empty] | High | Low | No | No | Yes | No |  | Risk Transformation | Organizational Structure - 3 Lines of Defense and Parent-Subsidiary Relationship | Non CART Workstream | The recuriting, hiring, and onboarding will be reliant on Human Resources
Governance & Organization | Recruit and onboard necessary talent | Active recruitment of SHUSA subsidiaries ORM staff for both 1st and 2nd lines of defense for short term (year 1) operating model | Steve Bhatti | 2015-11-30 | No | Initial recruitment for all SHUSA subsidiares ORM 1st and 2nd lines of defense based on the short term (year 1) operating model | [9 empty] | High | Low | No | No | Yes | No |  | Risk Transformation | Organizational Structure - 3 Lines of Defense and Parent-Subsidiary Relationship | Non CART Workstream | The recuriting, hiring, and onboarding will be reliant on Human Resources
Governance & Organization | Establish a SHUSA Operational Risk Management Framework (Develop ORM principles, 3 LoD roles and responsibilities, SHUSA ORM organizational structure, ORM ERM methodology) | SHUSA Operational Risk Framework approved by SHUSA BERC | Brian McVane | 2015-07-31 | No | A draft SHUSA Operational Risk Management Framework |  | Socialized Framework with obtained acknowledgement by CRO's and 1st line of defense with acknowledgement of roles and responsibilities |  | Obtained approval from SHUSA BERC | [5 empty] | High | Low | No | Yes | Yes | No |  | Non CART Workstream | SHUSA subsidiaries acknowledgement of Framework roles & responsbilities | Non CART Workstream | BERC schedule - BERC approval will be required | Risk Transformation | Organizational Structure - 3 Lines of Defense and Parent-Subsidiary Relationship
Governance & Organization | Perform gap analysis of policy inventory in line with regulatory guidance supporting SHUSA policy requirements | Completed mapping of all operational risk management enterprise policies and regulatory requirements in a tool | Brian McVane | 2015-07-31 | Yes | Tool selected |  | Tool implemented |  | Obtained authoritative sources for regulatory requirements |  | Uploaded regulatory and policy requirements into tool |  |  |  | High | Medium | No | Yes | Yes | No |  | Non CART Workstream | External support required (authoritative sources)
Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Operational Risk Management Policy | Brian McVane | 2105-10-31 | No | Updated operational risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for operational risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No | Yes | Yes | No |  | Non CART Workstream | Board schedule, as Board approval is required
Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Information Risk Management Policy | Brian McVane | 2015-10-31 | No | Updated information risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Information Risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No | Yes | Yes | No |  | Non CART Workstream | Board schedule, as Board approval is required
Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Third Party Risk Managment Policy | Brian McVane | 2015-10-31 | No | Updated Third Party risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Third Party Risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No | Yes | Yes | No |  | Non CART Workstream | Board schedule, as Board approval is required
Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Business Continuity & Disaster Recovery Policy | Brian McVane | 2015-10-31 | No | Updated Business Continuity & Disaster Recovery risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Business Continuity & Disaster Recovery enterprise policies and communication strategies | [7 empty] | High | Medium | No | Yes | Yes | No |  | Non CART Workstream | Board schedule, as Board approval is required
Governance & Organization | Gap analysis to identify training needs for staff of SHUSA and Subsidiaries with respect to SHUSA enterprise Ops Risk policies and standards | Documented operational risk management knowledge/skill assessment to inform initial training requirements | Brian McVane | 2015-11-30 | No | Developed centralized, criterion based operational risk management knowledge/skill assessment for SHUSA and its subsidiary 2nd LoD |  | Completed operational risk management knowledge/skill assessment | [7 empty] | Medium | High | Yes | No | Yes | No |  | Non CART Workstream | External support may be needed for assessment | Non CART Workstream | Human Resources may need to provide input into the training requirements
Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved operational risk management standards and communication strategy | Brian McVane | 2015-12-31 | No | Creation of operational risk management Standards Inventory |  | Drafted operational risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes | Yes | Yes | No
Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved information risk management standards and communication strategy | Brian McVane | 2015-12-31 | No | Creation of information risk management Standards Inventory |  | Drafted information risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes | Yes | Yes | No
Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved third party risk management standards and communication strategy | Brian McVane | 2015-12-31 | No | Creation of third party risk management Standards Inventory |  | Drafted third party risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes | Yes | Yes | No
Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved business continuity and disaster recovery standards and communication strategy | Brian McVane | 2015-12-31 | No | Creation of business continuity & disaster recovery Standards Inventory |  | Drafted business continuity & disaster recovery standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes | Yes | Yes | No
Risk Identification & Measurement | Establish the process to enforce and improve the identification and management of open issue and remediation efforts | SHUSA known issues are reflected in an issues management tool enhancing issue governance and management. | Sean O'Malley | 2015-08-31 | No | Enterprise issue management process ownership and oversight centralized within SHUSA Operational Risk |  | A documented process/standard to improve the centralization of issue management. | [7 empty] | High | High | Yes | No | Yes | No | 3rd Party
Risk Identification & Measurement | Implement the issue management tool for the identification, capture and management of issues | SHUSA known issues are reflected in an issues management tool enhancing issue governance and management. | Sean O'Malley | 2015-10-31 | Yes | Issue management tool selected |  | Issue management tool implemented |  | Completed data migration of all known issues into an issue management tool | [5 empty] | High | High | Yes | No | Yes | No | 3rd Party | Non CART Workstream | SHUSA subsidiaries/future subsidiaries - data input from various sources
Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Documented analysis of material event thresholds for peer institutions (primarily SBNA peers) | Sean O'Malley | 2015-10-31 | No | Completed peer review of event escalation thresholds with results and recommendations for threshold modifications (if applicable) documented | [9 empty] | Low | Low | Yes | No | Yes | No | 3rd Party
Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Document of strategic mitigation program to be completed in collaboration with 1st Line of Defense | Sean O'Malley | 2015-11-15 | No | Documented strategic mitigation program designed to address material operational risk event root causes | [9 empty] | Low | Low | Yes | No | Yes | No | 3rd Party
Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Documented analysis of material event back-testing | Sean O'Malley | 2015-12-15 | No | A documented plan for back testing related to material operational risk events to ensure data is complete, accurate and timely. | [9 empty] | Low | Low | Yes | No | Yes | No | 3rd Party
Risk Identification & Measurement | Review, evaluate and select RCSA methodology based on industry standards | RCSA Methodology document | Sean O'Malley | 2015-09-30 | No | Develop an RCSA methodology |  | Approved RCSA methodology (through appropriate governance) | [7 empty] | Medium | Medium | Yes | No | Yes | No | Internal | Non CART Workstream | This may require significant input from non-OR stakeholders across the risk organization, above and beyond what the other priorities may require
Risk Identification & Measurement | Review, evaluate and select RCSA methodology based on industry standards | Documented approval (ORC meeting minutes) for RCSA methodology | Sean O'Malley | 2015-11-30 | No | Develop an RCSA methodology |  | Approved RCSA methodology (through appropriate governance) | [7 empty] | Medium | Medium | Yes | No | Yes | No | Internal
Risk Identification & Measurement | Evaluate Scenario Analysis Tools and Processes | Documentation of discussion points raised in Scenario Analysis workshops and loss estimates based on subjective results (SHUSA and Subsidiaries) | Sean O'Malley | 2015-12-15 | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries | [9 empty] | Medium | Medium | Yes | Yes | Yes | No | Internal
Risk Identification & Measurement | Evaluate Scenario Analysis Tools and Processes | Scenario analysis Methodology document | Sean O'Malley | 2015-12-15 | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries | [9 empty] | Medium | Medium | Yes | Yes | Yes | No | Internal | Risk Transformation | The Operational Risk scenario analysis methodology should align with the broader framework for Risk Identification developed as part of the Risk Transformation workstream
Risk Identification & Measurement | Complete scenario analysis program for SHUSA and Subsidiaries | Scenario analysis Methodology document | Sean O'Malley | 2015-12-15 | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries |  | Provide documented methodology of scenario analysis in line with regulatory standards | [7 empty] | Medium | Medium | Yes | Yes | Yes | No | Internal | Non CART Workstream | SHUSA subsidiaries/future subsidiaries - participation in scenario analysis process
Risk Identification & Measurement | Complete CCAR OR Loss Estimates | ORM Loss Estimation Methodology document | Sean O'Malley | 2015-10-31 | No | Provide documented methodology of ORM Loss Forecasting in line with regulatory standards | [9 empty] | High | High | Yes | Yes | Yes | No | 3rd Party & Internal | Model Risk Management | Methodology must be reviewed and approved for use by Model Risk Management | Model Development | Model development resources may be required to develop an Operational Risk loss forecasting model
Risk Identification & Measurement | Refine operational risk loss forecasting model - Internal/External Loss Data Tools and Processes | Complete Y14A submission for CCAR 2016 | Sean O'Malley | 2015-12-31 | Yes | A completed submission of operational risk loss estimates for CCAR (Y14A) | [9 empty] | High | High | Yes | Yes | Yes | No | 3rd Party & Internal
Risk Identification & Measurement | Improve manual processes for OR Loss Event/Incident identification and collection | Documentation for OR Loss Event/Incident identification and capture across SHUSA and Subsidiaries (working with 1st Line of Defense) | Sean O'Malley | 2015-11-15 | Yes | Produce documented changes to OR Loss Event/Incident identification and collection process that increase the level of automation | [9 empty] | High | High | Yes | Yes | Yes | No | 3rd Party & Internal | Finance Transformation | OR Loss Event/Incident capture uses the General Ledger process to collect loss event records
Risk Identification & Measurement | Refine methodology to focus on emerging threats and vulnerabilities | IRM Gap analysis | Geoffrey Hauge | 2015-11-30 | No | Created IRM Risk Assessment cross entity working group |  | Kickoff IRM Risk Assessment gap analysis across regulatory guidance and industry standards |  | Completed Analysis for the IRM Risk Assessment | [5 empty] | High | High | Yes | No | Yes | No | 3rd Party
Risk Identification & Measurement | Refine Third Party Inherent Risk Classification methodology to determine scope and frequency of third party reviews | Documented methodology for third party inherent risk classification | Gregory Hamilton | 2015-07-01 | Yes | A documented Third Party Inherent Risk Classification methodology |  | Rollout for the Third Party Inherent Risk Classification methodology completed for SHUSA entities | [7 empty] | High | High | Yes | No | Yes | No | 3rd Party
Risk Identification & Measurement | Complete the new Inherent Risk Classification questionnaire for critical third party services | Updated inherent risk classifications for all critical third party services | Gregory Hamilton | 2015-08-30 | Yes | Inherent risk classifications completed for all critical third party services of SHUSA entities | [9 empty] | High | High | Yes | No | Yes | No | 3rd Party | Non CART Workstream | Dependency on 1st Line of Defense "Vendor Relationship Owners" completeing the inherent risk assemsnts for the critical vendor they own.
Risk Identification & Measurement | Perform onsite reviews for all critical third parties (scope/frequency will be driven by inherent risk questionnaire) | Onsite schedule for critical third parties. Critical third party assessment final reports. | Gregory Hamilton | 2015-12-31 | Yes | Completed onsite reviews for a selection of critical third parties based on results of inherent risk classifications | [9 empty] | High | High | Yes | No | Yes | No | 3rd Party | Non CART Workstream | Dependency on 1st Line of Defense "Vendor Relationship Owners" working the Third Party Risk Team and or Consultancy team to execute the onsite reviews for Critical population.
Risk Identification & Measurement | Review for program changes as a result of regulatory and SHUSA Policy changes | Business Continuity Management Policy -- review and enhance existing policy; Working individually with each subsidiary: | Danny Phillips | 2015-09-30 | No | Finalized BCM policy for submission through approval process and distribute to all subsidiaries (see Enhance Ops Risk Policies for governance); | [9 empty] | High | High | Yes | No | Yes | No | 3rd party & internal | Non CART Workstream | Dependant on the policy approval process in place | Non CART Workstream | Will need the cooperation from each subsidiary in rollout the approved SHUSA BCM policy
Risk Identification & Measurement | Review and refine existing Business Impact Analysis (BIA) of SBNA and SCUSA | Complete review of existing SBNA and SCUSA BIAs supporting SHUSA and subsidiary teammates: -- identify critical processes; -- to investigate and update in existing BIAs where applicable; | Danny Phillips | 2015-10-31 | Yes | Completed review of existing BIAs and current dependencies for SBNA and SCUSA entities | [9 empty] | High | High | Yes | No | Yes | No | 3rd party & internal | Non CART Workstream | Requiring subsidiary BCM 2nd Line of Defense input | Risk Transformation | Ensure ERM is aligned with the new Risk and Business analysis pricess executed within the SHUSA and subsidiaries BCM area
Risk Identification & Measurement | Identify gaps from current BIAs for SBNA and SCUSA critical processes, applications and testing | - Review 2014 - 2015 SBNA and SCUSA BCM (BR and DR) testing reports: -- identify issues and remediations completed and pending: -- identify responsible teams for issues and remediations; | Danny Phillips | 2015-12-31 | Yes | Conducted BCM (BR and DR) of testing reports from 2014 to 2015 to identify all existing/pending, closed issues and remediation for SBNA and SCUSA | [9 empty] | High | High | Yes | No | Yes | No | 3rd party & internal | Non CART Workstream | Requiring subsidiary BCM 2nd Line of Defense input
Risk Identification & Measurement | Review existing exercise results for each SBNA and SCUSA | Consolidate gap analysis report for SBNA and SCUSA of critical processes, -- critical applications, and testing for all subsidiaries: -- identify potential Risks; | Danny Phillips | 2015-12-31 | Yes | Completed and consolidated a gap analysis against critical processes, critical applications and testing results for SBNA and SCUSA | [9 empty] | High | High | Yes | No | Yes | No | 3rd party & internal | Non CART Workstream | Requiring subsidiary BCM 2nd LoD input
Risk Management | Strengthen aggregated operational risk reporting to allow the SAN US/SHUSA Operational Risk Committee to better fulfill its obligation to oversee and manage the identification and monitoring of operational risks as well as to escalate risks/issues that need ERMC/BERC/Board transparency. (Establish baseline operational risk management reporting and dashboards for SHUSA and its subsidiaries including (1) a standard set up summary risk data such as RTS limits, risk profile, top risks, emerging risks, material events and program updates, (2) a standard set of risk data specific to operational risk, information risk, third party risk and business continuity) | Established operational risk dashboards, including risk data for ORM, IRM, TPRM and BCM, for SHUSA and its subsidiaries are included in monthly governance reporting. | Brian McVane | 2015-12-31 | No | SHUSA operational risk management reporting framework is communicated to all subsidiaries |  | SHUSA defined processes and tools are utilized to support monthly operational risk reporting |  | SHUSA subsidiaries are producing operational risk reporting in line with SHUSA operational risk management requirements | [5 empty] | Medium | Medium | Yes | No | Yes | No |  | Non CART Workstream | SHUSA subsidiaries/future subsidiaries - data input | Risk Transformation | The Operational Risk reporting should align to the broader internal risk reporting framework being developed as part of the Risk Transformation workstream
Risk Monitoring | Develop timely reporting mechanisms and processes to satisfy OR Y-14Q reporting requirements | Completed automation of data collection for initial phase | Sean O'Malley | 2015-12-31 | Yes | "Golden Source" repository populated with data for initial phase | [9 empty] | High | High | Yes | Yes | No | No | 3rd party & internal
CART- Operational Risk Deliverable Inventory

## Model Development
| Yes | [12 empty] | High
| No | [12 empty] | Medium
Low
Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Finance Transformation
In partnership with MRMG, promulgate an Enterprise Model Policy that includes standards for: Data, Model development, Documentation, Testing and implementation, Validations, Monitoring, Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services | Develop an Enterprise Model Policy | Alex Silloway and Rafic Fahs | Thu 7/2/2015 | No | Enterprise Model Policy COMPLETE and APPROVED at CART Leadership (to include Standards, Roles & Responsibilities, and a gap analysis against SR Letter 11-7) | Thu 7/16/2015 | Communication of the Enterprise Model Policy DISTRIBUTED company wide and train Model Owners, Model Developers, Model Validators and Model User | Thu 9/3/2015 | Draft procedures re: Enterprise Model Policy COMPLETE and APPROVED at Working Group (to reinforce the application of the Enterprise Model Policy for Model Developers) | Thu 9/3/2015 |  |  |  |  | Low | Low | Yes | Resources required: consulting company to do benchmark analysis and gap assessment versus SR Letter 11-7
Review, and modify if needed, working group charters | Working group charters | Alex Silloway | Thu 7/2/2015 | No | Existing governance MAPPED and APPROVED (to include the following topics: Alignment on Data for Model Development, Documentation, Testing and implementation, Validations, Monitoring, Model Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services) | Fri 6/19/2015 | Charters UPDATED and COMPLETE and APPROVED at CART Leadership | Thu 7/2/2015 | Implement new charters within all working groups | Thu 7/2/2015 |  |  |  |  | Low | Low | No
Ensure model performance monitoring reports are being regularly generated for all tier 1 models | Model Performance Monitoring report for all tier 1 models | Alex Silloway | Thu 7/2/2015 | No | Receive from MRM final inventory of all tier 1 models | Mon 6/1/2015 | All tier 1 models not included on the model performance monitoring report prioritized & ADDED | Fri 6/19/2015 | Procedures COMPLETE establishing routines to ensure model performance monitoring reports are being regularly generated for all tier 1 models | Thu 7/2/2015 |  |  |  |  | Medium | Medium | No
Define a Model Development organizational structure that establishes clear lines of control between SHUSA and LOBs | Model Development Organizational Structure | Alex Silloway | Thu 7/2/2015 | No | Scope and roles & responsibilities for SHUSA Model Development group (with detailed lines of control btwn SHUSA & LOBs) COMPLETE | Thu 7/2/2015 | Model Dev Organizational Structure COMPLETE and APPROVED at CART Leadership | Thu 7/2/2015 | [6 empty] | Low | Low | Yes | Model Development resources pending Organizational Structure design
Standardized skills assessments for senior analysts and managers | Standardized job descriptions across SHUSA | Alex Silloway | Thu 7/2/2015 | No | Existing job descriptions for Model Development across SHUSA MAPPED | Mon 6/8/2015 | Organization and HR job descriptions for Model Development across SHUSA reviewed with HR and APPROVED | Thu 7/2/2015 | New job descriptions for existing Model Development employess COMMUNICATED / SOCIALIZED across SHUSA | Thu 7/2/2015 |  |  |  |  | Low | Low | Yes | Resouces: Pending revised grade and comp for new Job Descriptions
Assess recruiting needs and begin recruiting of qualified FTEs | New and existing resource requirement and recruitment plan | Alex Silloway | Fri 7/31/2015 | No | Comprehensive staffing assessment conducted and COMPLETE (determines skills, capabilities and areas of expertise) | Fri 6/19/2015 | Gap analysis between staffing assessment and model landscape COMPLETE | Thu 6/25/2015 | New hiring plan defined and APPROVED at CART Leadership | Thu 6/25/2015 |  |  |  |  | Low | Low | Yes | Resouces: Pending idetification of resource needs outside of Model Development group (resource of Model Development group already identified together with the definition of the new Organization Structure)
Introduce Professional Qualification Standards (PQS) at the SHUSA level | Professional Qualification Standards (PQS) at the SHUSA level | Alex Silloway | Thu 10/29/2015 | No | PQS at SHUSA COMPLETE and APPROVED | Thu 10/29/2015 | Training and Implementation plan COMPLETE and APPROVED | Thu 10/29/2015 | [6 empty] | Medium | Medium | Yes | May need assistance with systems support
Model Reference Library: - Establish a Model Reference Library of modeling procedures, standardized reporting templates, best practices, and other support materials to assist in the management of mathematical models - Populate the Model Reference Library with at least one “Gold Standard” document | Model Reference Library | Alex Silloway | Thu 10/29/2015 | No | Model Reference Library DEFINED (to include modeling procedures, standardized reporting templates, best practices, and other support materials to assist in the management of models) | Thu 10/29/2015 | Model Reference Library POPULATED (includes X "Gold Standard” documents) | Thu 10/29/2015 | Model Reference Library SHARED company-wide | Thu 10/29/2015 | Training Plan COMPLETE, APPROVED and IMPLEMENTED | Thu 10/29/2015 |  |  | Low | Low | Yes | Vendor may be needed to develop training plan and assist with inventory
Model Landascape: - Confirm Model inventory - Assign model risk tiers (in alignment with new tiering system) - Assess model performance - Identify non-existent BAU models - Prioritize - Validate or redevelop as necessary | 2015 & 2016 Model Landascape | Alex Silloway and Rafic Fahs | Fri 7/31/2015 | Yes | Model Inventory CONFIRMED | Mon 6/8/2015 | Model Risk Tiers ASSIGNED / COMPLETE | Mon 6/15/2015 | Model development Prioritization COMPLETE | Mon 6/15/2015 | Go-forward Model Development Strategy COMPLETE (outlining the Development, validation or redevelopment of models wherever necessary) | Fri 6/26/2015 | Model Development procedures COMPLETE and APPROVED (procedures will allow MD to continue this process moving forward) | Fri 7/31/2015 | High | High | Yes
CCAR Models: - Strong coordination between PPNR and CCAR Credit Losses, with unified project plan - Follow approved approach, including unified decision making, to prioritize and execute CCAR Model Landscape for 2016 - Ensure alignment and appropriateness of segmentation and selection of Risk Factors - Create procedures for 70% of all CCAR modeling processes | CCAR Model Landascape for 2016 CCAR Submission | Alex Silloway | Tue 9/1/2015 | Yes | Unified project plan for PPNR and CCAR Credit Loss model development COMPLETE | Thu 7/2/2015 | Approach to prioritize the CCAR Model Development landscape for 2016 DEFINED | Mon 8/3/2015 | Procedures COMPLETE implementing recurring model performance monitoring | Tue 9/1/2015 | Procedures for 70% of all CCAR modeling processes COMPLETE and APPROVED | Tue 9/1/2015 |  |  | High | High | Yes
CART- Model Development Deliverable Inventory

## Model Risk Management
| Yes | [12 empty] | High
| No | [12 empty] | Medium
Low
Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Workstream Interdependency | Inter-dependency Comment | Workstream Interdependency2 | Inter-dependency Comment2 | Workstream Interdependency3 | Inter-dependency Comment3 | Workstream Interdependency4 | Inter-dependency Comment4 | Workstream Interdependency5 | Inter-dependency Comment5
Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Material | Pete W. | 2015-08-31 | No | Presentation material drafted | 2015-08-31 | Presentation material reviewed and approved | 2015-08-31 | [6 empty] | High | Low | Yes |  | Non CART Workstream | Legal
Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Schedule (if beyond SHUSA) | Pete W. | 2015-08-31 | No | Presentation schedule drafted | 2015-08-31 | Presentation schedule reviewed | 2015-08-31 | Presentation Schedule published | 2015-08-31 |  |  |  |  | Low | Low | No |  | Non CART Workstream | Legal
Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Confirmation (Board Minute) | Pete W. | 2015-09-30 | No | Conduct Initial SHUSA Board Presentation | 2015-09-30 | [8 empty] | Low | Low | No |  | Non CART Workstream | Legal
Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Board Presentation Plan | Pete W. | 2015-09-30 | No | Build long term Board Presentation Plan (including Entities) | 2015-09-30 | [8 empty] | Low | Low | No |  | Non CART Workstream | Legal
Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role | Updated charters for BERC, ERMC, EMC and MRMC | Pete W. | 2015-08-31 | No | Updates to charters drafted | 2015-08-31 | Reviewed and finalized BERC, ERMC, EMC and MRMC committee charters with updates to strengthen MRM oversight and roles and responsibilities | 2015-08-31 | [6 empty] | High | High | Yes |  | Risk Transformation | BERC, ERMC, EMC charter updates to flow through Risk Transformation | Non CART Workstream | Legal
Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role | Charter Approval (Board Minute) | Pete W. | 2015-09-30 | No | Revised charters approved | 2015-09-30 | [8 empty] | Low | Low | No |  | Risk Transformation | BERC, ERMC, EMC charter updates to flow through Risk Transformation | Non CART Workstream | Legal
Develop model risk workstream (CART) reporting, governance, controls | Requirements for model risk workstream (CART) reporting, governance, controls | Greg T. | 2015-07-31 | No | Requirements for enhanced model risk remediation reporting, governance and control drafted | 2015-06-30 | Requirements for enhanced model risk remediation reporting, governance and control reviewed and approved | 2015-07-31 | [6 empty] | Medium | Medium | No |  | Non CART Workstream | Central CART team - standards, guidance
Develop model risk workstream (CART) reporting, governance, controls | Reporting templates, communication plan and calendar(cadence) | Greg T. | 2015-07-31 | No | Reporting templates, communication plan and calendar(cadence) drafted | 2015-07-31 | [8 empty] | Medium | Low | No |  | Non CART Workstream | Central CART team - standards, guidance
Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | Requirements for enhanced model risk BAU reporting | Pete W. | 2015-08-31 | No | Requirements for enhanced model risk BAU reporting drafted (MRMC, Model Risk to BERC/ERMC, etc.) | 2015-07-31 | Requirements for enhanced model risk BAU reporting approved | 2015-08-31 | [6 empty] | Medium | Medium | No |  | Model Development | Get relevant data points for reporting | Risk Transformation | Include reporting requirements from RTY team
Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | BAU Reporting templates, Frequency(Cadence) , Communication Plan (Who gets what level of detail) | Pete W. | 2015-08-31 | No | Reporting templates, communication plan and calendar(cadence) drafted | 2015-08-31 | Reporting templates, communication plan and calendar(cadence) approved | 2015-08-31 | [6 empty] | Medium | Medium | Yes |  | Risk Transformation | Standards, guidance to ensure alignment/consistency across risk reporting
Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | MRMC Committee deck, BERC/ERMC submission | Pete W. | 2015-09-30 | No | Implemented Enhanced reporting | 2015-09-30 | [8 empty] | Medium | Medium | Yes |  | Risk Transformation | Standards, guidance to ensure alignment/consistency across risk reporting
Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Long term Model inventory and reporting system requirement | Pete W. | 2015-09-30 | Yes | Requirements for long term Model inventory and reporting system drafted | 2015-09-30 | Requirements for long term Model inventory and reporting system approved | 2015-09-30 | [6 empty] | High | High | Yes |  | Model Development | Supplement requirements
Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Vendor selection criteria and approach | Pete W. | 2015-10-31 | No | Vendor selection criteria and process drafted/approved | 2015-10-31 | [8 empty] | Low | Low | No |  | Model Development | Supplement requirements
Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Vendor SOW; documented Minutes of decision (per VRM committee) | Pete W. | 2015-11-30 | No | Vendor selection complete | 2015-11-30 | [8 empty] | Low | Low | No
Hire for known staffing requirements based on volume of validation req'd | Staffing Report | Rafic F. | 2015-12-31 | No | Approval for supplemental FTE headcount | 2015-06-30 | Approval for supplemental consultant/advisory headcount | 2015-06-30 | Onboarding of consulting resources | 2015-07-31 | Hiring of approved incremental FTEs and existing gaps | 2015-12-31 |  |  | Medium | Medium | No |  | Non CART Workstream | HR
Define Target Operating model (including org structure) | Operating Model | Edward S. | 2015-07-31 | No | Articulation of 3LoD principles (May) | 2015-05-29 | Formalization of Risk reporting lines at the C-Suite (May) | 2015-05-29 | Risk roles and responsibilities of SHUSA vs. subsidiaries (across each line of defense) | 2015-07-31 | Design of org. structure for each risk type / entity / line of defense | 2015-07-31 | Operating model approved | 2015-07-31 | Medium | Medium | Yes |  | Risk Transformation | Oliver Wyman proposed effort | Model Development | Participation in definition/confirmation/dissemination
Conduct talent and staffing assessment for MRMG | Talent and staffing assessment result/report | Rafic F. | 2015-09-30 | No | Assessment of FTE needs (activity based analysis) | 2015-09-30 | Definition of capabilities needed | 2015-09-30 | Assessment of capabilities of existing staff | 2015-09-30 | Identification of training / upskilling / hiring needs | 2015-09-30 | Talent and staffing assessment complete | 2015-09-30 | Medium | Medium | Yes |  | Risk Transformation | Oliver Wyman proposed effort | Model Development | Participation in definition/confirmation/dissemination
Conduct First Line and auxiliary functions (IT, etc.) staffing assessment (Dependency on Model Development) | Talent and staffing assessment result/report | TBD | 2015-09-30 | Yes | Assessment of FTE needs (activity based analysis) | 2015-09-30 | Definition of capabilities needed | 2015-09-30 | Assessment of capabilities of existing staff | 2015-09-30 | Identification of training / upskilling / hiring needs | 2015-09-30 | First line and auxiliary functions staffing assessment complete | 2015-09-30 | Medium | Medium | Yes |  | Risk Transformation | Oliver Wyman proposed effort
Develop staffing/hiring strategy (including external resources) and plan based on assessment, backlogs, and workloads | Staffing/Hiring Strategy | TBD | 2015-09-30 | No | All relevant inputs to define staffing/hiring strategy is in place | 2015-09-30 | Staffing/Hiring strategy drafted | 2015-09-30 | Staffing/Hiring strategy approved | 2015-09-30 |  |  |  | 2015-12-31 | Medium | Medium | Yes |  | Risk Transformation | Oliver Wyman proposed effort | Non CART Workstream | HR
Commence hiring strategy/plan in partnership with the First Line/Model Development | Hiring execution touchpoint cadence | TBD | 2015-12-31 | No | Regular checkpoint on hiring strategy execution drafted | 2015-12-31 | Regular checkpoint on hiring strategy execution reviewed and published | 2015-12-31 | [6 empty] | Low | High | Yes |  | Non CART Workstream | HR
Include MRMG specialist in SCUSA pricing governance | Updated SCUSA pricing governance charter | TBD | 2015-07-31 | No | MRMG specialist designated to participate in SCUSA pricing governance | 2015-07-31 | SCUSA pricing governance charter updated to include MRMG specialist | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed | Non CART Workstream | SCUSA
Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates | SCUSA retail finance product oversight requirements | TBD | 2015-07-31 | No | Requirements for oversight drafted | 2015-07-31 | Requirements for oversight approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed | Non CART Workstream | SCUSA
Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates | Updated relevant charters | TBD | 2015-07-31 | No | List of charters to be updated defined | 2015-07-31 | Relevant charters updates drafted | 2015-07-31 | Relevant charters updates approved | 2015-07-31 |  |  |  |  | High | Medium |  | Actual status of this item is pending. May be closed | Non CART Workstream | SCUSA
Enhance SCUSA pricing policies and procedures | Updated SCUSA pricing policy | TBD | 2015-07-31 | No | SCUSA pricing policy updates drafted | 2015-07-31 | SCUSA pricing policy updates approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed | Non CART Workstream | SCUSA
Enhance SCUSA pricing policies and procedures | Updated SCUSA pricing procedures | TBD | 2015-07-31 | No | SCUSA pricing procedures updates drafted | 2015-07-31 | SCUSA pricing procedures updates approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed | Non CART Workstream | SCUSA
Develop Framework - enhance decision making authority & roles and responsibilities for approving models and model changes (including model retirement) | MRM Framework | Pete W. | 2015-08-31 | No | Framework Drafted | 2015-07-31 | Framework Approved | 2015-08-31 | [6 empty] | High | High | Yes
Enhance Provisional Approval (PA) process, clarify roles and responsibilities | PA process enhancement requirements | Pete W. | 2015-07-31 | No | Requirements for enhancement for PA process drafted | 2015-07-31 | Requirements for enhancement for PA process approved | 2015-07-31 | [6 empty] | High | Low | No
Enhance Provisional Approval (PA) process, clarify roles and responsibilities | Updated PA process | Pete W. | 2015-08-31 | No | PA process updates drafted | 2015-08-31 | PA process updates approved | 2015-08-31 | [6 empty] | Medium | Low | No
Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology | Model Risk rating methodology enhancement requirements | Pete W. | 2015-08-31 | No | Requirements for Model risk rating methodology drafted | 2015-08-31 | Requirements for Model risk rating methodology approved | 2015-08-31 | [6 empty] | High | Low | No
Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology | Updated model risk rating methodology | Pete W. | 2015-08-31 | No | Enhancement of Model risk rating methodology drafted | 2015-08-31 | Enhancement of Model risk rating methodology approved | 2015-08-31 | [6 empty] | High | Low | No
Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology | Model tiering methodology enhancement requirements | Pete W. | 2015-07-31 | No | Requirements for Model tiering methodology drafted | 2015-07-31 | Requirements for Model tiering methodology approved | 2015-07-31 | [6 empty] | High | Low | No
Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology | Updated model tiering methodology | Pete W. | 2015-07-31 | No | Enhancement of Model tiering methodology drafted | 2015-07-31 | Enhancement of Model tiering methodology approved | 2015-07-31 | [6 empty] | High | Low | No
Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | SR 11-7 gap analysis | Pete W. | 2015-07-31 | No | SR 11-7 Gap analysis complete | 2015-07-31 | [8 empty] | High | Medium | Yes
Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Updated MRM Policy | Pete W. | 2015-08-31 | No | Policy update based on SR 11-7 gap analysis drafted | 2015-08-31 | [8 empty] | High | Medium | Yes |  | Non CART Workstream | Legal - Board Review, get on agenda, etc. | Non CART Workstream | EPA - pre-board policy review, feedback, etc
Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Minutes from MRMC / BERC/ERMC | Pete W. | 2015-09-30 | No | Obtain approval on MRM policy | 2015-09-30 | [8 empty] | High | Medium | No |  | Non CART Workstream | Minutes
Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | MRM Procedure inventory | Pete W. | 2015-08-31 | No | Updated inventory of procedures based on SR11-7 | 2015-08-31 | [8 empty] | Low | High | Yes
Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Updated MRM procedures | Pete W. | 2015-09-30 | No | Obtained MRMC approval of procedures | 2015-09-30 | [8 empty] | High | High | Yes
Train MRMG staff on the new validation procedures | Training materials approved by CMRO | Pete W. | 2015-09-30 | No | Prepare MRMG materials | 2015-09-30 | [8 empty] | High | Low | No
Train MRMG staff on the new validation procedures | Record of attendees / signatures | Pete W. | 2015-09-30 | No | Deliver MRMG training | 2015-09-30 | [8 empty] | Low | Low | No
Enhance training based on updated Policy, Procedures, and Development Standards | Updated training materials | Pete W. | 2015-12-31 | No | Training material for all stakeholders drafted | 2015-12-31 | Training material for all stakeholders approved by CMRO | 2015-12-31 | [6 empty] | High | Medium | Yes
Enhance training based on updated Policy, Procedures, and Development Standards | Training schedule/cadence | Pete W. | 2015-12-31 | No | Training schedule/cadence drafted | 2015-12-31 | Training schedule/cadence reviewed and published | 2015-12-31 | [6 empty] | Low | Low | No
Implement Policy and Procedures/Standards | TBD | Pete W. | TBD | No | Collection of compliance report complete | TBD | [8 empty] | High | High | Yes
Address Legacy Model Validation Backlog | Prioritized list of Legacy models | Paul M. | 2015-07-31 | No | Legacy models prioritized for validation | 2015-07-31 | [8 empty] | High | Medium | Yes |  | Model Development | List of models to be received from MD
Address Legacy Model Validation Backlog | Gap assessment result | Paul M. | 2015-10-31 | No | Tier 1 Models gap assessment complete | 2015-10-31 | [8 empty] | High | Medium | Yes
Address Legacy Model Validation Backlog | Remediation plan | Paul M. | 2015-10-31 | No | Tier 1 Models remediation plan complete | 2015-10-31 | [8 empty] | High | Medium | Yes
Address Legacy Model Validation Backlog | Validation results | Paul M. | 2015-10-31 | No | Initial validation findings – including interim compensating controls and other risk mitigants | 2015-10-31 | [8 empty] | High | High | Yes
Address Legacy Model Validation Backlog | List of validation ready models | Paul M. | 2015-12-31 | No | Commence work on models identified as being ready for validation | 2015-12-31 | [8 empty] | High | Medium | Yes
CCAR model validation | Validation Schedule | Paul M. | 2015-06-30 | No | Definition of validation schedule with Model Development complete | 2015-06-30 | [8 empty] | High | Medium | Yes |  | Model Development | Validation schedule to be developed in coordination with MD
CCAR model validation | CCAR Model Validation Result | Paul M. | 2015-12-31 | No | CCAR models validated | 2015-12-31 | [8 empty] | High | High | Yes
Define model data validation data and reporting requirements aligned to model risk management framework and validation standards | Model data validation data requirements | TBD | TBD | Yes | Requirements for Model Data validation data drafted | TBD | Requirements for Model Data validation data approved | TBD | [6 empty] | High | Low | No
Define model data validation data and reporting requirements aligned to model risk management framework and validation standards | Model data validation reporting requirements | TBD | TBD | Yes | Requirements for Model Data validation Report drafted | TBD | Requirements for Model Data validation Report approved | TBD | [6 empty] | High | Medium | No
CART- Model Risk Management Deliverable Inventory

## Data & IT
| Yes | [12 empty] | High
| No | [12 empty] | Medium
Low
Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Finance Transformation
IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SHUSA Aggregrated IT Risk Assessment Document (Phase 1 - partial completion expected) | Frank Cignarella | December 31 2015 | Yes | IT Risk Assessment Methodology Document Published | June 1 2015 | IT Risk Aggregregation Model Developed and Approved by IT, ORM and ERM | July 1 2015 | iGRC SHUSA Instance with Business Hierarchy loaded | Aug 1 2015 | iGRC Data populated for SHUSA and related entitied (SBNA, SCUSA, other (SIS) | December 15 2015 | SHUSA Risk Aggregration report from iGRC Data generated for management | December 31 2015 | Medium | High | Yes | SHUSA iGRC Instance and SBNA methodology and groundwork available today to leverage; contract in place with vendor to support
IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SBNA IT Risk Assessment Document (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 10 2015 | Yes | SBNA IT Risk Register | May 25 2015 | SBNA IT Applicability Matrix | June 1 2015 | SBNA IT Control Plans and Controls Modeled inside iGRC | June 15 2015 | SBNA IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | SBNA Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | SBNA iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SCUSA IT Risk Assessment Document (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 15 2015 | Yes | SCUSA IT Risk Register | May 25 2015 | SCUSA IT Applicability Matrix | June 15 2015 | SCUSA IT Control Plans and Controls Modeled inside iGRC | June 20 2015 | SCUSA IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | SCUSA Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | SCUSA iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | Other SHUSA Entity IT Risk Assessment Document (e.g., SIS, etc.) (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 20 2015 | Yes | Other IT Risk Register | May 25 2015 | Other IT Applicability Matrix | June 20 2015 | Other IT Control Plans and Controls Modeled inside iGRC | June 25 2015 | "Other" IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | "Other" Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | "Other" iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
Finding and Remediation Management Capability and Governance (including 2014 IT SOX Finding Remediations) | Monthly report of Technology Findings and Remediation Plans, assigned to owners with business alignment (T&O, Retail, Auto, etc.) generated and delivered to EMC members | Frank Cignarella | December 1 2015 | Yes | Business Owners for Applications (SOX Covered) Identified | June 1 2015 | Findings for Business Applications assigned to Business Owners (e.g., T&O, Retail, Auto, etc.) | June 15 2015 | Findings and Remediation Plan Governance Model Documented (expected behavior and timing) | July 1 2015 | SHUSA and related entities Findings to be loaded into iGRC SHUSA Instance and related iGRC instances for entities (SBNA, SCUSA, etc.) with minimum necessary fields populated | Oct 1 2015 | "Governance" Report generated from iGRC and communicated to EMC members and the finding and remediation plan owners for ongoing management and maintenance | Nov 20 2015 | High | High | Yes | IGRC instances and SBNA OpRisk Issue Management documentation available to leverage; heavy lifting will be getting ownership, fields populated and active management of the findings and remediations in place and under governance whereby violations (non participation) are escalated and remedied.
Governance: Policy, Standards, Roles and Responsibilities Development (EPAP, RTS) | IT Governance document in EPAP Compliant format for SHUSA the holding company approved and published | Frank Cignarella | December 31 2015 | Yes | IT Policies Drafted | Nov 1 2015 | IT Policies Approved | Dec 1 2015 | IT Standards Drafted | Dec 1 2015 | IT Standards Approved | Dec 15 2015 | IT Guidelines, Acceptable form, and select IT Processes Drafted | Dec 31 2015 | High | Medium | Yes | Contracted for delivery of the draft documents with vendor in place, leveraging same vendor we had success developing SBNA governance documents with and will 'uplifting' SBNA documents to the extent practical.
Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA Access Attestation & Certification Solution - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for Access Attestation and Certification | Oct 1 2015 | Define SHUSA Access Attestation and Certification - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA Access Attestation & Certification Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA Access Attestation and Certification Solution | Dec 15 2015 | Production Release -SHUSA Access Attestation & Certification Solutoin Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) and initial campaign initiated | Dec 31 2015 | High | High | Yes | Contracted for delivery of the Attestation and Certification with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA User Access Request Portal - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for User Access Request Portal | Oct 1 2015 | Define SHUSA User Access Request Portal - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA User Access Request Portal Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA User Access Request Portal Solution | Dec 15 2015 | Production Release - SHUSA User Access Request Portal - Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) (3-5 Applications and related roles can be requested and workflow for management pre-approval and then sent to human provisioners) | Dec 31 2015 | High | High | Yes | Contracted for delivery of the User Access Request Portal with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA Access Termination Workflow - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for Access Termination Workflow | Oct 1 2015 | Define SHUSA Access Termination Workflow - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA Access Termination Workflow Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA Access Termination Workflow Solution | Dec 15 2015 | Production Release - SHUSA Access Termination Workflow - Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) | Dec 31 2015 | High | High | Yes | Contracted for delivery of the Access Termination Workflow Solution with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Data Flow Control from Upstream Feeders into Golden Sources and from Golden Sources to Downstream Reporting Systems | Data Flow Control Document detailing the data flows and specific controls (e.g., accuracy and completeness) in place for the data elements | Frank Cignarella | December 31 2015 | Yes | Data Elements identified and documented | July 1 2015 | Data Sources (Upstream feeders, golden sources, downstream reporting systems) identified and documented (including owners) | Aug 1 2015 | Data flow modeled (flow chart) from source to source (upstream, golden, downstream) | Oct 1 2015 | Control Points and Control Techniques documented | Nov 1 2015 | Potential gaps in control points and control techniques documented in SHUSA iGRC as Findings with corresponding remediation plans | Dec 31 2015 | High | High | Yes | This is a core deliverable and requires support from the Architecture, RDA and CDO teams
Establish Key Data Elements (KDEs) for prioritized CCAR data (including models and schedules), including documenting data dictionary and lineage, measuring and remediating data quality, deploying data controls. | KDEs defined for each domain in SHUSA, with lineage information, data quality rules, and initial metrics (KPIs) | Peter Flanagan | 2015-12-31 | Yes
Implement a Data Quality Center of Excellence to improve the quality of the company’s data (SHUSA and all the related US entities) by centralizing the collection of data defects, analyzing and assigning the issues causing the defects, and ensuring remediation activities are completed. | DQ COE staffed and operational | Peter Flanagan | 2015-12-21 | Yes
Conduct a data industry maturity model assessment for SBNA, SCUSA and SHUSA to identify capability gaps that require further remediation. | Data Maturity Model (DMM) assessment for each of SHUSA, SBNA and SCUSA | Peter Flanagan | 2015-08-30 | No
Establish strict governance on KDEs to assess, ensure and report on compliance with data policies and standards. | Establishment of working group including business data stewards | Peter Flanagan | 2015-12-31 | No
Create the structure and organization of the CDO for SHUSA | Staffed CDO Target Operating Model | Peter Flanagan | 2015-12-21 | No
Clearly define roles, responsibilities and ownership for data collection, quality, maintenance (Data Manager, Data Owner, Data Steward, DQ Admin, Tech Data Owner,……) as well as a list of Data Domains. | Agreed list of Data Domain definition documents, with assignment of key roles | Peter Flanagan | 2015-07-31 | No
Organize data management roles along the three lines of defense model (Business, Chief Data Officer and Independent Audit) | Approval of data management roles definitions | Peter Flanagan | 2015-07-15 | No
Socialize data management program and implementation plan with key stakeholders. | Education and communication plan for SHUSA CDO | Peter Flanagan | 2015-07-15 | No
Define domain scope and boundaries | Data Domain definition documents | Peter Flanagan | 2015-11-30 | No
Launch a SHUSA Data Governance Council attended by Data Manager, Data Owners, Data Stewards and CDO. | Data Governance council charter approved by first meeting of DG Council members | Peter Flanagan | 2015-06-30 | No
Assess and ensure compliance of SHSUA, SBNA and SCUSA practices against the Data Management Policy and Standards | Compliance review worksheet completed for each CDO team within SHUSA, SBNA and SCUSA | Peter Flanagan | 2015-12-31 | No
Define a comprehensive data control framework, and apply it for critical CCAR and EPS / ELS related processes | Data Dictionary, Lineage, Data Quality Dashboard Reports | Peter Flanagan | 2015-12-31 | Yes
Conduct data industry maturity model assessment for SHUSA, SBNA and SCUSA on an annual basis | Completed Maturity Model | Peter Flanagan | 2015-11-30 | No
CART- Data & IT Deliverable Inventory
Expected By 5/15/15

## CCAR Vertical Unique
| Yes | [13 empty] | High
| No | [13 empty] | Medium
Low
Priority | Deliverable | Workstream | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Finance Transformation
Improve linkages between scenario generation and upstream / downstream processes | Capital Management team included in the Risk ID process to ensure appropriate collaboration between teams and support the identification of quantitative and qualitative risks | Scenario generation | John Barris | 2015-10-31 | No | Identify Capital Management-Risk ID liaison | 2015-06-30 | Define roles, responsibilities governing involvement and collaboration (if any) | 2015-07-31 | Review ed aggregation of SHUSA-level Inventory with Top-Down Analysis | 2015-10-31 |  |  |  |  | Medium | Medium | No | Heavy reliance on Risk ID to meet their deadlines, which are reflected here as Milestones.
Development of multiple, robust scenarios for selection and testing | Enhanced set of scenarios aligned to the refreshed scenario design methodology | Scenario generation | John Barris | 2015-12-18 | No | Receive SHUSA-level Risk ID Inventory & Assessment | 2015-10-31 | Capital Management presents and recommends initial set of Idiosyncratic Narratives to Ex&Agg | 2015-11-13 | Capital Management recommends Idiosyncratic Narratives to Management CC | 2015-12-18 | Capital Management recommends Idiosyncratic Narratives to Board CC | 2015-12-01 | Capital Management works with BU and Risk stakeholder to paramterize suite of multiple scenarios | 2015-12-18 | High | Medium | No
Development of multiple, robust scenarios for selection and testing | Updated policies and procedures that govern the scenario-design and scenario-selection processes | Scenario generation | John Barris | 2015-10-31 | No | First Draft of Policy & Procedure Documentation reviewed by CCAR Director | 2015-08-30 | Policy & Procedure Documentation reviewed by Ex&Agg | 2015-08-15 | Policy & Procedure Documentation reviewed by Management CC | 2015-09-15 | Policy & Procedure Documentation reviewed by Board CC | 2015-10-31 | Policy & Procedure Documentation updated to reflect actual CCAR 2016 process | 2016-01-31 | Medium | Low | No
Development of multiple, robust scenarios for selection and testing | BHC scenarios actual macroeconomic data aligned across all scenarios | Scenario generation | John Barris | 2016-01-31 | No | Presentation of a suite of scenarios to Management and Board Capital Committees for formal selection and approval of the scenarios to be used in CCAR/DFAST | 2015-12-31 | Receive FRB Scenarios from FRB | 2015-01-22 | Align BHC Scenario Actuals with FRB Scenarios | 2015-01-31 |  |  |  |  | Low | Low | No
Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Defined quantification approach and methodology | Capital assessment | Imad Kordab |  | No | Drafted quantification approach and methodology |  | Syndicated with relevant experts and stakeholders |  | Approved by [X] committee
Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Developed model to translate uncertainty to a capital buffer | Capital assessment | Imad Kordab |  | Yes | Staffed modeling team |  | Developed multiple model options for governance committee consideration |  | Finalized modeling approach
Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Quantification/estimate of uncertainty resulting from capital planning and process weaknesses at a process or model level | Capital assessment | Imad Kordab |  | Yes | Assessed current and past process weakness to develop estimate of uncertainty |  | Developed estimates related to assumptions, limitations and weaknesses |  | Quantification approved by [X] committee
Measure and account for inherent uncertainty due to model limitations | Developed quantification approach and standards | Capital assessment | Imad Kordab |  | No | Drafted quantification approach and standards |  | Approved by [X] committee
Measure and account for inherent uncertainty due to model limitations | Disseminated the approach to stakeholders to syndicate | Capital assessment | Imad Kordab |  | No | Developed approach to stakeholders |  | Implemented approach
Measure and account for inherent uncertainty due to model limitations | Quantified inherent model uncertainty and incorporated results into stressed capital buffer | Capital assessment | Imad Kordab |  | No | Develop intial quantification of model uncertainty |  | Syndicated results of uncertainty measurement with model risk management and model validation |  | Approved by [X] committee
Developed economic capital model to evaluate impact on capital of stressful scenarios | Rigorous process developed beyond enterprise-wide scenario analysis, to assess the aggregate impact on capital from stressful conditions | Capital assessment | Imad Kordab |  | Yes | Brainstormed and determined necessary actions to constititute process steps |  | Mapped process based on determined steps
Formalized management overlays process | Developed overlay standards and templates | Capital assessment | Imad Kordab |  | No | Determined and consulted with correct stakeholders |  | Determined correct standards/templates based on stakeholder interactions |  | Incorporated feedback and expert opinions
Formalized management overlays process | Disseminated model overlay approach to governance committees and model owners | Capital assessment | Imad Kordab |  | No | Disseminated approach to stakeholders |  | Implemented approach |  | Implemented standards of documentation for overlays
Formalized management overlays process | Aggregated of overlays across CCAR process steps | Capital assessment | Imad Kordab |  | No | Developed and implemented process for centralzing collection of overlay documentation |  | Aggregated overlay results across CCAR process steps
Improved weakness indentification and management process | Updated weakness indentification policy and procedures | Governance and effective challenge | Jon Watson |  | No | Draft updated policy and procedures |  | Draft sent to committee #1 |  | Draft sent to committee #2 | [5 empty] | Medium | Low
Improved weakness indentification and management process | Finalized weakness inventory with owners and action items | Governance and effective challenge | Jon Watson |  | No | Weakness inventory structure updated to comply with new weakness ID procedures |  | Weakness ID process communicated to CCAR participants |  | Completed inventory | [5 empty] | Medium | High
Refreshed and implemented review and challenge framework | Review and enhance current review and challenge framework | Governance and effective challenge | Jon Watson |  | No | Assessment and update of current framework completed |  | Draft sent to committee #1 |  | Draft sent to committee #2 |  | New review and challenge communicated to all relevant governance committees |  |  |  | Medium | Low
Refreshed and implemented review and challenge framework | Review and challenge calendar aligned to framework | Governance and effective challenge | Jon Watson |  | No | Calendars and high-level drafted |  | Calendar approved by committee #1 |  | Detailed calendar based on revamped end-to-end process | [5 empty] | Medium | Low
Updated CCAR governance structure | Re-designed CCAR governance structure and landscape | Governance and effective challenge | Jon Watson |  | No | Current state governance structure and flows assessed |  | New CCAR governance structure determined (e.g., charters, membership) |  |  |  | Approval of governance structure by committee #1 |  |  |  | Medium | Low
Updated CCAR governance structure | Governance landscape implemented | Governance and effective challenge | Jon Watson |  | No | Governance structure approved |  | Initial meeting of committee with new membership/composition held | [7 empty] | High | High
Extensive board engagement and input into CCAR process | Board training materials and schedule | Governance and effective challenge | Jon Watson |  | No | Developed overall board training schedule and agenda |  | Delivered training #1 |  | Delivered training #2 | [5 empty] | High | Medium
Extensive board engagement and input into CCAR process | Board key capital planning decision calendar and schedule | Governance and effective challenge | Jon Watson |  | No | Deveoped overall board interaction schedule and model |  | Approved by [X] committee | [7 empty] | Medium | Medium
Develop common documentation standards and templates | Developed document landscape consisting of key document categories | Documentation | Jon Watson |  | No | Identified the universe of document categories (e.g., capital planning and policy) |  | Collaborated with process/category owners to define the document types per category |  | Syndicated completeness of document landscape (across processes and within process steps / events) with process owners and overarching CCAR central team | [5 empty] | Medium | Low
Develop common documentation standards and templates | Documentation standards, procedures and templates across the documentation landscape | Documentation | Jon Watson |  | No | For each document in the landscape, defined level of document granularity, type of descriptions required ((e.g., actions, processes, events), and type of explanation (e.g., analysis, decision-making / rationale) |  | Syndicate documentation standards with CCAR central team to ensure documentation standards are aligned with FRB expectations |  | Syndicated / disseminated document standards with process owners witin workstreams |  | Adapted models and processes to ensure capture of documents to the established standards (e.g., altered granularity of models to ensure documentation granularity) |  |  |  | Medium | Low
Develop common documentation standards and templates | Developed a centralized inventory for documents, with clear organization scheme and owners attached | Documentation | Jon Watson |  | Yes | Identified central storage warehouse for documents |  | Defined organization scheme for documents (e.g., by Y 14A line item, v. legal entity) |  | Defined ownership for each document in each category |  | Defined owner roles and responsibilities |  | Trained owners on orgnization scheme and inventory access |  | Medium | Medium
Create centralized documentation aggregation and review process | Detailed documentation hand-off process including calendar of hand-offs and dates | Documentation | Jon Watson |  | No | Developed calendar of review and challenge sessions in line with |  | Defined steps in review process for incorporating feedback, correctionsm and controls to ensure evidence of review is incorporated |  | Mapped out detailed documentation hand-off process, including calendar of hand-offs and R&C session, with dates for submission | [5 empty] | Medium | Low
Create centralized documentation aggregation and review process | Established central oversight to own document aggregation | Documentation | Jon Watson |  | No | Defined ownership of and accountability for dcoumentation process |  | Assigned central team documentation liaisons in each core documentation area | [7 empty] | Medium | Medium
Redesign and centralization of the CCAR end-to-end process | Developed spreadsheet inventory and standardized controls | E2E process and controls | Jon Watson |  | No | Compiled list of all spreadsheets used in each CCAR process |  | Defined organization scheme for spreadsheets (e.g., by Y 14A line item, v. legal entity) |  | Assessed criticality of each spreadsheet for classification and prioritization |  | Identified, implemented and documented all required control points |  | Defined a minimum set of spreadsheet controls (e.g., password protection) and applied to all spreadsheets |  | High | High
Restructure CCAR organization and improve staffing | Centralized oversight and execution of CCAR cycle run process within CCAR workstream | E2E process and controls | Jon Watson |  | No | Established oversight governance, i.e., CCAR leadership / oversight, decision-making, reporting lines, and escalation process |  | Defined responsibilities of oversight team (e.g., process design, change management and issue tracking) | [7 empty] | High | High
Restructure CCAR organization and improve staffing | Implemented change management process led by dedicated team | E2E process and controls | Jon Watson |  | No | Defined change management team responsibilities: identification and documentation of changes and required controls |  | Defined process for managing changes and internal controls |  | Established ownership / leadership of change management process | [5 empty] | High | High
Develop new internal controls framework and testing procedures | Developed an enhanced internal controls framework and testing plan | E2E process and controls | Jon Watson |  | No | Defined CCAR requirements for internal controls |  | Defined critical control points across CCAR cycle run process |  | Developed materiality assessment for internal control points |  | Created a governance mechanism to ensure that all control points used in the capital planning process are graded for materiality |  | Ensured robust design and testing of controls within material spreadsheets |  | Medium | Low
Develop new internal controls framework and testing procedures | Implemented internal controls across critical control points | E2E process and controls | Jon Watson |  | Yes | All material controls implemented |  | All remaining controls implemented | [5 empty] | Engaged external advisors to supplement internal teams in oversight and execution |  | High | High
Develop new internal controls framework and testing procedures | Designed and enforced governance structure to ensure consistent implementation of controls mechanisms | E2E process and controls | Jon Watson |  | No | Defined clear ownership of controls and review and challenge processes |  | Developed hand-off calendar with sign-off for audit and review tasks | [7 empty] | Medium | High
Effective process for aggreagating estimates of loss revenue | Updated IT infrastructure for generation and aggregation of loss estimates | E2E process and controls | Jon Watson |  | Yes | Developed customized SAS aggreation tool for loss and PPNR forecasts |  | Reconciled as of data set |  | Partially implemented Moody's Scenario Analyzer |  | Increased granularily of forecasts (e.g., by business line / unit) in SAS |  |  |  | High | High
CART- CCAR Unique Deliverable Inventory

## Data Sheet
Workstream | Element | Topic | Year 1 Requirement
Data & IT | Data Quality | Data Quality | Establish Key Data Elements (KDEs) for prioritized CCAR data (including models and schedules), including documenting data dictionary and lineage, measuring and remediating data quality, deploying data controls.
Data & IT | Data Quality | Data Quality | Implement a Data Quality Center of Excellence to improve the quality of the company’s data (SHUSA and all the related US entities) by centralizing the collection of data defects, analyzing and assigning the issues causing the defects, and ensuring remediation activities are completed.
Data & IT | Data Governance | Data Governance | Conduct a data industry maturity model assessment for SBNA, SCUSA and SHUSA to identify capability gaps that require further remediation.
Data & IT | Data Governance | Data Governance | Establish strict governance on KDEs to assess, ensure and report on compliance with data policies and standards.
Data & IT | Data Governance | Data Governance | Define a comprehensive data control framework, and apply it for critical CCAR and EPS / ELS related processes
Data & IT | Data Governance | Data Governance | Create the structure and organization of the CDO for SHUSA
Data & IT | Data Governance | Data Governance | Conduct data industry maturity model assessment for SHUSA, SBNA and SCUSA on an annual basis
Data & IT | Data Governance | Data Governance | Clearly define roles, responsibilities and ownership for data collection, quality, maintenance (Data Manager, Data Owner, Data Steward, DQ Admin, Tech Data Owner,……) as well as a list of Data Domains.
Data & IT | Data Governance | Data Governance | Organize data management roles along the three lines of defense model (Business, Chief Data Officer and Independent Audit)
Data & IT | Data Governance | Data Governance | Socialize data management program and implementation plan with key stakeholders.
Data & IT | Data Governance | Data Governance | Define domain scope and boundaries
Data & IT | Data Governance | Data Governance | Launch a SHUSA Data Governance Council attended by Data Manager, Data Owners, Data Stewards and CDO.
Data & IT | Data Governance | Data Governance | Assess and ensure compliance of SHSUA, SBNA and SCUSA practices against the Data Management Policy and Standards
Data & IT | Infosecurity | Infosecurity | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.)
Data & IT | Infosecurity | Infosecurity | Finding and Remediation Management Capability and Governance (including 2014 IT SOX Finding Remediations)
Data & IT | Infosecurity | Infosecurity | Governance: Policy, Standards, Roles and Responsibilities Development (EPAP, RTS)
Data & IT | Infosecurity | Infosecurity | Identity and Access Management Solution (SailPoint for Attestation, Access Request)
Data & IT | Infosecurity | Infosecurity | Data Flow Control from Upstream Feeders into Golden Sources and from Golden Sources to Downstream Reporting Systems
Model Development | Governance Tools | Governance Tools | In partnership with MRMG, promulgate an Enterprise Model Policy that includes standards for: Data, Model development, Documentation, Testing and implementation, Validations, Monitoring, Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services
Model Development | Governance Tools | Governance Tools | Review, and modify if needed, working group charters
Model Development | Governance Tools | Governance Tools | Best Practices Library
Model Development | Governance Tools | Governance Tools | Ensure model performance monitoring reports are being regularly generated for all tier 1 models
Model Development | Governance Tools | Governance Tools | Define a Model Development organizational structure that establishes clear lines of control between SHUSA and LOBs
Model Development | Governance Tools | Governance Tools | LOB Modeling Frameworks and Procedures
Model Development | Governance Tools | Governance Tools | Templates, checklists, and other standardized (but adaptable) controls
Model Development | Professional Development | Professional Development | Develop standardized job descriptions across SHUSA (e.g. Analyst Level I, Analyst Level II, etc.)
Model Development | Professional Development | Professional Development | Assess recruiting needs and begin recruiting of qualified FTEs
Model Development | Professional Development | Professional Development | Standardized skills assessments for senior analysts and managers
Model Development | Professional Development | Professional Development | Introduce Professional Qualification Standards (PQS) at the SHUSA level
Model Development | Professional Development | Professional Development | Classroom and online training
Model Development | Professional Development | Professional Development | Establish Model Forum
Model Development | CCAR | CCAR | FRB letter gap analysis
Model Development | CCAR | CCAR | Inventory of models needed for CCAR 2016
Model Development | CCAR | CCAR | Construct at least one set of models with dual CCAR and business purposes
Model Development | CCAR | CCAR | Demonstrate substantial improvement on Model Development
Operational Risk | Risk Appetite | SHUSA Operational Risk Tolerance Statement | Simplify SHUSA Operational Risk Tolerance Statement Limits
Operational Risk | Risk Appetite | SHUSA Operational Risk Tolerance Statement | Align with Capital Measures described in the Basel Consultative document (Total Potential OR Losses as a % of Gross Income, Single OR Loss Event > $10MM)
Operational Risk | Governance & Organization | Establish a SHUSA Operational Risk Management Framework | Establish a SHUSA Operational Risk Management Framework (Develop ORM principles, 3 LoD roles and responsibilities, SHUSA ORM organizational structure, ORM ERM methodology)
Operational Risk | Governance & Organization | Enhance Ops Risk Policies | Perform gap analysis of policy inventory in line with regulatory guidance supporting SHUSA policy requirements
Operational Risk | Governance & Organization | Enhance Ops Risk Policies | Update SHUSA enterprise Ops Risk policies as required
Operational Risk | Governance & Organization | Training & Awareness | Gap analysis to identify training needs for staff of SHUSA and Subsidiaries with respect to SHUSA enterprise Ops Risk policies and standards
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Determine OR organizational structure between SHUSA and Subsidiaries
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Determine and select short-term / medium-term resource requirements (internal and external) to deliver Year 1/2/3 priorities
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Recruit and onboard necessary talent
Operational Risk | Risk Measurement | Risk Identification and Assessment Design & Implementation | Establish the process to enforce and improve the identification and management of open issue and remediation efforts
Operational Risk | Risk Measurement | Risk Identification and Assessment Design & Implementation | Implement the issue management tool for the identification, capture and management of issues
Operational Risk | Risk Measurement | Material Event Escalation Process | Review the Material/Significant Event thresholds in line with peer institutions
Operational Risk | Risk Measurement | Enhance/Refine ORM Risk Identification and Assessment Tools and Processes | Review, evaluate and select RCSA methodology based on industry standards
Operational Risk | Risk Measurement | Enhance/Refine ORM Risk Identification and Assessment Tools and Processes | Review, evaluate and select RCSA methodology based on industry standards
Operational Risk | Risk Measurement | Scenario Analysis Tool | Evaluate Scenario Analysis Tools and Processes
Operational Risk | Risk Measurement | Scenario Analysis Tool | Complete scenario analysis program for SHUSA and Subsidiaries
Operational Risk | Risk Measurement | ORM Modeling Tool | Complete CCAR OR Loss Estimates
Operational Risk | Risk Measurement | ORM Modeling Tool | Refine operational risk loss forecasting model - Internal/External Loss Data Tools and Processes
Operational Risk | Risk Measurement | ORM Modeling Tool | Improve manual processes for OR Loss Event/Incident identification and collection
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Refine methodology to focus on emerging threats and vulnerabilities
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Evaluate threats and changes across regulatory landscape and industry standards
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Develop and automate assessment processes
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Refine methodology to focus on emerging threats and vulnerabilities
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Evaluate threats and changes across regulatory landscape and industry standards
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Refine Third Party Inherent Risk Classification methodology to determine scope and frequency of third party reviews
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Complete the new Inherent Risk Classification questionnaire for critical third party services
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Perform onsite reviews for all critical third parties (scope/frequency will be driven by inherent risk questionnaire)
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Develop and automate assessment processes
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review for program changes as a result of regulatory and SHUSA Policy changes
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review and refine existing Business Impact Analysis (BIA) of SBNA and SCUSA
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Identify gaps from current BIAs for SBNA and SCUSA critical processes, applications and testing
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review existing exercise results for each SBNA and SCUSA
Operational Risk | Risk Management | Update Internal Reporting | Continue to complete the baseline Ops Risk dashboard reporting for all Subsidiaries
Operational Risk | Risk Monitoring | Refine External Reporting | Develop timely reporting mechanisms and processes to satisfy OR Y-14Q reporting requirements
Operational Risk | Risk Monitoring | Refine External Reporting | Define automated system requirements for Ops Risk
Operational Risk | Risk Monitoring | Refine External Reporting | Hiperos roll-out in SBNA, begin implementation for New York branch
Operational Risk | Risk Monitoring | Refine External Reporting | Everbridge Crisis Management System roll-out to SHUSA and Subsidiaries
Operational Risk | Data & Systems | Data & Systems | Continue roll-out of iGRC within SBNA
Operational Risk | Data & Systems | Data & Systems | Select BCM tool across all SHUSA subsidiaries
Finance Transformation | Finance Planning and Analysis | Strategic Planning and Forecasting | Establish and execute foundational Planning and Forecasting framework including process governance, process timelines, clear roles and responsibilities and controlled approval processes
Finance Transformation | Finance Planning and Analysis | Strategic Planning and Forecasting | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management)
Finance Transformation | Finance Planning and Analysis | Business Performance | Incorporate cost of contingent liquidity across all IHC entities
Finance Transformation | Finance Planning and Analysis | Business Performance | Create high-level cost allocation model to support organizational and product group profitability to improve accuracy of contribution and ROE reporting
Finance Transformation | Finance Planning and Analysis | SHUSA Reporting & Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting
Finance Transformation | Finance Planning and Analysis | SHUSA Reporting & Analysis | Definition of requirement to supporting effective management decision making at SHUSA
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Define FP&A Target Operating Model (clear roles and responsibilities, ownership and governance between holdco and entities)
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Define requirements to support interim and target state business, data and reporting requirements to support planning and forecasting, management reporting and multi-dimensional profitability
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Technology design and rationalization based on methodology and system decisions for planning, forecasting and reporting
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Develop a detailed project plan with T&O based on release schedule for target state implementation
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Enhance capital adequacy and capital planning governance
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Establish staffing and conduct adequate training across the end-to-end CCAR review cycle
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Develop capital expectations for IHC entities commensurate with size / complexity
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Establish hand-off process from businesses to aggregation team, with a clearly defined operating model of sub-functions and activities to be centralized at SHUSA vs performed at each entity (specifically, NY, MIA, PR)
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Operationalize processes for escalation to board, potential suspension of capital actions, and implementation of contingency plans (improve analysis and documentation of contingency actions)
Finance Transformation | Capital Management |  | Develop clear linkage between Risk ID and scenario generation and develop BHC specific scenarios
Finance Transformation | Capital Management | Capital policy and planning | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities
Finance Transformation | Capital Management | Capital policy and planning | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC)
Finance Transformation | Capital Management | Capital policy and planning | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements
Finance Transformation | Capital Management | Capital policy and planning | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board
Finance Transformation | Capital Management | Capital policy and planning | Enhance Capital Plan for 2016
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Develop clear linkage of Risk, Capital, liquidity, and strategic planning across reporting and Risk Tolerances
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Establish enhanced monthly capital reporting / tracking
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Improve financial analysis at consolidated and legal entity view
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Conduct training sessions to prepare reviewers of aggregated results
Finance Transformation | Capital Management | RWA modeling and calculation methodology | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies
Finance Transformation | Treasury | Operating Model | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions
Finance Transformation | Treasury | Intraday Cash and Collateral Management | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate
Finance Transformation | Treasury | Intraday Cash and Collateral Management | Incorporate intraday procedures in SHUSA’s Cash Management and Funding policy and procedures
Finance Transformation | Treasury | Asset/Liability Management | Develop first version of Board-approved Enterprise and Operating policies, procedure and charter for Interest Rate Risk
Finance Transformation | Treasury | Asset/Liability Management | Enhance QRM operating environment including prudent mix of Chart of Accounts and dimensions, access controls and optimization of processes
Finance Transformation | Treasury | Stress Testing/Cash Flow Projections | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced
Finance Transformation | Treasury | Stress Testing/Cash Flow Projections | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests
Finance Transformation | Treasury | Regulatory Reporting (Treasury) | Develop capability to submit 2052a reports by 1/1/16
Finance Transformation | Treasury | Regulatory Reporting (Treasury) | U.S. LCR reporting (though not currently required, is expected to be produced as a result of the granularity of 2052a reporting)
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Establish a set of reconciled and clean current and historical financial data (internal sources where possible) to use for reporting and to support forecasting capabilities (CCAR and Strategic Planning)
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Establish effective governance and controls over Chart of Accounts for all IHC entities
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Improve the quality of information in the general ledger needed to complete the chart of accounts and execute reporting
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Improve the amount of general ledger information available from direct system feeds rather than manual processes
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Deployment of a uniform reconciliation tool (SHUSA and subsidiaries)
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting).
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Comprehensive documentation of controls over reporting process (centralized and distributed components)
Finance Transformation | Accounting, Tax & Reporting | End User Application Controls | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Report Group Results on Business Day 4
Finance Transformation | Accounting, Tax & Reporting | Operating Model | Finalize the implementation of Target Operating Model
Finance Transformation | Accounting, Tax & Reporting | Operating Model | Uniform application of accounting policies across subsidiaries (was part of IHC plan)
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Improve efficiency of Regulatory Report production (Incorporate all legacy systems not completed as part of the original FRS implementation).
Finance Transformation | Internal Controls | Operating Model | Finalize implementation of target operating model
Finance Transformation | Internal Controls | Operating Model | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA
Finance Transformation | Internal Controls | Implement programs to roll-out internal controls operating model | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries
Finance Transformation | Internal Controls | Reporting & Tools | Implementation of common software tools such as Cluster7 and Archer to manage the documentation, monitoring, evaluation, governance and reporting of internal control across all IHC entities
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | Re-design RAS for SHUSA enterprise
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | RAS reporting, breach escalation and breach penalty mechanism
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | Preliminary RAS communication and socialization materials
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | Cascade RAS to priority subsidiaries
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | RAS for all subsidiaries/BUs (aligned with overall SHUSA RAS)
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | RAS reporting, breach escalation and breach penalty mechanism (cascaded version)
Risk Transformation | Re-design and embed Risk Appetite Statement | Embed RAS in material processes | Board Risk Committee Training
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Strengthen SHUSA Board and Management Committee guidance
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Formalize engagement model between SHUSA and Parent Group
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Board Risk Committee reporting
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Updated committee composition, mandates, charters and compensation structure for high priority committees
Risk Transformation | Strengthen Board and Management oversight | Set a strong ‘Tone at the top | Revised and consistent risk-related messaging (link to articulation of ‘risk culture’):
Risk Transformation | Strengthen Board and Management oversight | Develop link between risk mgt. and performance assessment and compensation | Risk based / risk aware performance assessments and compensation framework and principles:
Risk Transformation | Strengthen Board and Management oversight | Continue and enhance Risk training for the Board Risk Committee | Risk training curriculum and schedule for Board Risk Committee including: (Training Materials, Detailed risk training objectives, Assessment and improvement process, Delivery)
Risk Transformation | Enhance Limits and Controls Framework | Review and update credit process controls and limits for underwriting and origination | High level review of credit process limits / controls
Risk Transformation | Enhance Limits and Controls Framework | Define risk oversight framework for IRR / liq. risk | Framework for risk oversight of key IRR and liquidity risk assumptions and parameters
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Future risk organizational model for SHUSA / subsidiaries
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Design risk management organizational structure in accordance with 3LoD principles
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Recruit priority staff
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Communication materials to convey org. changes to enterprise
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Updated articulation of risk management roles and responsibilities across the three lines
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Training materials to explain model and key changes
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Implementation of risk management organizational structure in accordance with 3LoD principles
Risk Transformation | Re-design operating model and talent management | Design risk staff recruitment / retention strategy and onboard talent | Development and execution of Phase 1 Talent Management Strategy,
Risk Transformation | Re-design operating model and talent management | Improve risk culture | Risk culture assessment across the organization
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Improve effectiveness of policies and procedures
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Frameworks defined and approved across all risk types
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Policy attestation process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Enhance risk identification and assessment process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Defined risk ID and assessment process, integrated into the end-to-end CCAR process:
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Initial register of risks, encompassing both modeled and non-modeled risks across all relevant legal entities / BUs
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Policy/procedure for Risk Identification and Assessment cycle (specifying frequency, stakeholders, duration, approvals, etc.)
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Demonstrated linkage of risk ID process to capital planning (CCAR) process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Demonstrated linkage of risk ID process to risk mitigation, management and reporting
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Conduct high level credit risk review and deliver quick wins
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Definition of credit-related roles and responsibilities and lines of control across 3LoD
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Initial roll-out of 3LOD across credit risk management
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Create IRR and Liquidity Risk framework
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Conduct liquidity risk gap analysis
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Improvement of liquidity stress-testing
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Conduct Compliance Risk Management Framework Review
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Conduct Reputational / Strategic Risk Management Framework Review
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Conduct new Product / New Business process Review
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Execute Compliance Risk Mgt. Remediation Plan
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Execute New Product / New Business Remediation Plan
Risk Transformation | Update internal monitoring and reporting | Define risk reporting landscape | Enhance internal reporting
Risk Transformation | Update internal monitoring and reporting | Define risk reporting landscape | Update internal monitoring process
Risk Transformation | Update internal monitoring and reporting | Define risk reporting landscape | Risk reporting landscape, by audience and risk type
Risk Transformation | Update internal monitoring and reporting | Develop and socialize prototype reports | Prototype reports and socialization of high priority reports to Board & Senior Management
Risk Transformation | Update internal monitoring and reporting | Develop business requirements | Define initial business and data requirements
Risk Transformation | Update internal monitoring and reporting | Develop business requirements | Identification of risk aggregation needs to support reporting
Risk Transformation | Update internal monitoring and reporting | Determine resourcing needs to produce reports | Reporting resourcing
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Create business and data requirements | Requirements defined for all data-related risk measurement, management, and reporting activities
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Create business and data requirements | Prioritization of data requirements, both within and across individual business requirement documents
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Define systems architecture to support data needs | Review current systems architecture and identify improvements
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Provide training on MRM regulatory requirements and industry practices (Board, BERC, EMC)
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC)
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Enhance model risk remediation reporting, governance, controls
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board)
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Develop model risk workstream (CART) reporting, governance, controls
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection
Model Risk Management | Talent and Staffing | Talent and Staffing | Hire for known staffing requirements based on volume of validation req'd
Model Risk Management | Talent and Staffing | Talent and Staffing | Conduct talent and staffing assessment for MRMG
Model Risk Management | Talent and Staffing | Talent and Staffing | Conduct First Line and auxiliary functions (IT, etc.) staffing assessment (Dependency on Model Development)
Model Risk Management | Talent and Staffing | Talent and Staffing | Develop staffing/hiring strategy (including external resources) and plan based on assessment, backlogs, and workloads
Model Risk Management | Talent and Staffing | Talent and Staffing | Implement hiring strategy/plan in partnership with the First Line/Model Development
Model Risk Management | Governance Oversight and Reporting | Governance Oversight and Reporting | Define Target Operating model (including org structure)
Model Risk Management | Talent and Staffing | Talent and Staffing | Commence hiring strategy/plan in partnership with the First Line/Model Development
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Include MRMG specialist in SCUSA pricing governance
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Enhance SCUSA pricing policies and procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Enhance Provisional Approval (PA) process, clarify roles and responsibilities
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Develop Framework - enhance decision making authority & roles and responsibilities for approving models and model changes (including model retirement)
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Enhance training based on updated Policy, Procedures, and Development Standards
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Train MRMG staff on the new validation procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Begin targeted training on enhanced MRM Policy and Model Development Standards including training on SR 11-7 Standards and expectations (as a precursor to the Policy/Procedure rollout)
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | MRM Policy, Procedures / Standards, Controls, and Training | Implement Policy and Procedures/Standards
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Address Legacy Model Validation Backlog
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Conduct gap assessment (e.g. conceptual soundness, etc.)
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Commence Validation not completed in in the initial gap assessment and initial validation for all models. Updates to Findings Log
Model Risk Management | Model Validation | Model Validation | Evaluate internal/external model pipeline management and reporting tools/process
Model Risk Management | Model Validation | Model Validation | CCAR model validation
Model Risk Management | Data | Data | Define model data validation data and reporting requirements aligned to model risk management framework and validation standards
CART Workstream Year 1 Requirements Initiative Mapping