## Slide 1
RDA Discovery
High level & Detailed Implementation Plans
NYB SIS
April 23, 2015

## Slide 2
MRI Implementation (1)
1. NYB & SIS
Timeline Overview and Plan
Detailed Plan
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Q1
Q2
Including gaps detected
2016
2015
Local Framework Implementation
GS Formalization (SI PBC / NP)
Generation of metrics2 (feed to SI PBC/NP)
DD Tool Local Implementation
Certification
Certification (preliminary)
Top Mgmt. Metrics E2E traceability
SHUSA Dependencies
RRF
Individual WS
Data Dictionary
Data Quality
Credit Risk
Market Risk
Operational Risk
AML / Conduct
Finance
Certification
NY RDA Plan definition
Implementation of RDA USA Gov. Model Committees
Functional definition of metrics
Analyze, adjust and approve the frameworks at the local level
Receive Target Operating Model SHUSA
SHUSA approve and distribute the frameworks1
Implementation of CDO/Risk MI
Reporting Generation Documents
Financial information anticipation
Generation of metrics2 (feed to Capa de Agr. Corp. de R.de Crédito)
MRI Implementation (2)
GS Assessment
(ACERO)
Generation of metrics1 (feed to San SIRO)
Provisioning / Adequation of ACERO
Generation of metrics1 (feed to Cristine)
Provisioning / Go Live of Equation
ALM
Generation of reports2 (upload to Argus)
SHUSA Argus Implementation (TBD)
DQ Governance Local
Implementation
DQ Program implementation for critical lines of action
Data Clusters model plan completed
DQ KPIs scorecard implemented
Plan Review according with identified gaps