## Slide 1
SHUSA Risk Reporting Framework
Next Steps to Finalize Business Requirements

## Slide 2
1. SHUSA Risk Reporting Framework: AS-IS
Preliminary set of reports and metrics for SHUSA/IHC and SBNA
Risk Area |  | Corporate Metrics |  | Local Reports |  |  | Local Metrics |  | 
 |  |  |  | SHUSA | SBNA |  | SHUSA | SBNA | 
Credit Risk |  | 117 |  | 7 | 62 |  | 67 | 216 | 
Operational Risk |  | 76 |  | 11 | 12 |  | 209 | 207 | 
Trading/Market Risk |  | 92 |  | 71 |  |  | 137 |  | 
ALM/Market Risk |  | 90 |  | 49 |  |  | 9 |  | 
Compliance |  | 312 |  | 2 |  |  | 135 |  | 
Other Non-Prudential Risks |  | 7 |  | 7 | 17 |  | 7 | 12 | 
ERM |  | 694 |  | 5 | 8 |  | 273 | 119 | 
Top of the House (TOH)
Reports
Metrics
Management
161
338
53
247
Regulatory
77
333
TOTAL
249
864
Breakdown by Audience:
Next Steps?

## Slide 3
Approach
Objective
There are two main objectives to be achieved to fulfil the end goal:
Analysis and rationalization of the total universe of metrics and reports.
  Top of the House (TOH): Board reports and level 1 Management Committees, risk reports of each specific risk area to the ERMC, Risk Aggregation/ERM and Credit Risk Review reports. Also includes reports sent to senior management in Spain.
  Management: level 2 Management Committee reports, such as the risk reports presented at the Market, Credit, Operational Risk Committees and lower level committees.
  The reports need to be defined at the SHUSA/IHC level as well as per type of audience: TOH, Management and Regulatory
Gathering and documentation of user requirements per risk area at SHUSA level
2. SHUSA Risk Reporting Framework
Next steps to finalize business requirements definition
To finalize the SHUSA Risk Reporting Framework definition, these are the next steps that needs to be finalized by the end of May.
Review all materials received and identify missing information and rationalization criteria
Analyze reports and metrics ensuring: no local metrics are repeated in several reports, no metrics overlap with corporate metrics, all reports are correctly classified (in terms of audience) and necessary, list of reports is complete at all levels, etc.
Define common business requirements to be used as a guide to ensure all critical aspects are considered and covered
Schedule meetings with risk managers to:
  Review the results of the metrics and report analysis and gather feedback, focusing in the perimeter of each of the reports and the audience.
  Review each requirement category and gather specific information for the area
Determine final set of reports and metrics at each level and for each audience
Document SHUSA requirements for Risk area
Verification and Rationalization of Reports and Metrics
Gathering, Documentation and Validation
PHASE I
PHASE II

## Slide 4
RDA principles Requirements
Common Requirements
The “standard” to meet each RDA principle (Slides 7 and 8). For each principle, describe what has to be in place (capabilities, processes, etc.) to achieve compliance
Common requirements applicable across the organization (Slides 5 and 6)
The processes, deliverables, organization, capabilities, etc. that have to be established across the bank in order to be RDA compliance in the context of the Intermediate Holding Company. Do not vary by RDA principle, risk type, etc.
3. SHUSA Risk Reporting Framework
Approach to gather the business requirements
This document includes a set of points for discussion to facilitate the completion of user requirements for SHUSA Risk reporting
Risk type specific Req.
Compile and further specify requirements that are affected or differ by risk type, as defined by the ERM Framework.
  Rationalization of inventory of metrics and reports
  Identification of RDA deliverables to be created for each risk type
  Identification of differences between risk types, such as regulatory requirements
1
2
3

## Slide 5
3.1 SHUSA Risk Reporting Framework
Common Requirements
Common Requirements |  | 
1. | Scope | Ability to support different aggregation structures (SHUSA/IHC and Consolidated US Operations) and also have the information by operating entity. Centralized target operating model at SHUSA/IHC, to ensure consistency of information presented locally (senior management and regulators) and to Spain.
2. | Organization | Organization (teams fully dedicated to project), detailed implementation plan and budget defined
3. | Documentation | Controls should be documented, have defined roles / responsibilities, and be subject to regular independent verification. SHUSA should be able to produce evidence that it has met the requirement – e.g. process documentation, data glossary, providing names of data stewards, and sign-offs/approvals of documents.
4. | Capabilities under stress conditions | SHUSA should run tests or drills to aggregate the necessary data or produce the required reporting; results of the tests and drills should be documented.
5. | Information Archiving | Required systems and processes to store a great deal of information in a way that users are able to reprocess past information at their request.
6. | Information Enrichment | Ability to slice and dice the information in different data attributes (I.e. chart of accounts). Drill-down abilities to report on underlying risk data and information exists for each material risk, and is available (on an ad hoc basis) to the relevant risk management functions.
7. | Change management | Process defined to provide flexibility to add additional metrics and reports on a timely manner.
8. | Security / Accessibility | Determine the level of access required to both critical information and detailed drill-downs depending on user profiles.
9. | Record Keeping / Audit Trail | Ability to capture historical versioning of the metrics (audit trail, including comments field for explanations) and/or calculation or threshold changes.
1

## Slide 6
3.1 SHUSA Risk Reporting Framework
Common Requirements (cont’d)
Common Requirements |  | 
10. | Data Standardization | Required systems and processes to provide a unified layout for all its data feeds providing steadiness and uniformity, integrating all the required information in a single information system while reducing manual requirements by automating all processes involved.
11 | Data Dictionary requirements | Consistency of information at SHUSA level: unique definition of metrics at SHUSA level, end to end traceability of the metrics for each entity and aggregation rules defined
1

## Slide 7
3.2 SHUSA Risk Reporting Framework
“Standard” to meet RDA Principles
RDA Requirements |  | 
1. | Governance | - Key risk reporting capabilities are subject to an oversight capability that is responsible for approving contents, production, and distribution of each risk report - Ownership, accountability, and decision rights for reports and data across the data lifecycle and data lineage are defined and documented
2. | Data architecture and IT infrastructure | Overarching governance and coordination of risk data and system architecture design. Senior management is taking a structured approach to prioritizing risk data and system investments
3. | Accuracy and integrity | -Processes to source, use, and manipulate risk data for risk data aggregation and reporting purposes are subject to validation controls that ensure numbers are consistently correct and up-to-date -These validation controls are consistently used across the business to drive congruence of all functions and groups across risk types - SHUSA can demonstrate the measures to ensure accuracy in normal and stress/crisis conditions
4. | Completeness | -The data necessary to fulfill the risk reporting requirements set by SHUSA’s risk managers is recorded and available for reporting purposes -Control processes are in place to check completeness of risk data over time and across operating entities and businesses to drive congruence for the entire organization -SHUSA can demonstrate that it produces the complete set of risk data it needs during normal and stress/crisis conditions
5. | Timeliness | The data necessary to fulfill the risk reporting requirements set by the SHUSA’s risk managers, is available for reporting purposes at the frequency, response time, and data latency as outlined in the risk data report requirements
6. | Adaptability | SHUSA can generate aggregated risk data meeting the specific ad hoc and customized risk data reporting requirements in times of crisis, supervisory queries, or other unforeseen reporting requests
2

## Slide 8
3.2 SHUSA Risk Reporting Framework
“Standard” to meet RDA Principles (cont’d)
RDA Requirements |  | 
7. | Reporting Accuracy | -Risk reporting accuracy lays out the correctness requirements for items and exhibits produced for individual risk reports. -Report items and exhibits are subject to validation processes that confirm the correctness of the report outputs, the relevance for the intended risk decision making, and the consistency with other data and data sources that might be provided.
8. | Comprehensiveness | -Drill-down abilities to report on underlying risk data and information exists for each material risk, and is available (on an ad hoc basis) to the relevant risk management functions. SHUSA has a structured process to identify and update the catalogue of material risk areas
9. | Clarity and usefulness | -Procedures and guidelines that document the use of specific risk data, metrics, exhibits, and concepts to report on each material risk for the relevant scope of the specific risk report . -Risk reporting concepts are consistent across the various risk reports, but may vary in scope due to the scope of each individual risk report.
10. | Frequency | For each key risk report; frequency and availability of the report is specific and documented as part of the risk reporting requirements.
11. | Distribution | Key risk reports specify in the requirements and procedures what the distribution processes, tools, and required security measures are.
2

## Slide 9
3.3 SHUSA Risk Reporting Framework
Risk Type Business Requirements - Overview
Verification and Rationalization of the inventory of reports and metrics
Identification of Regulatory Requirements and differences between risk types
Identification of RDA deliverables to be created for each risk type
Key Activities
Key Outcomes
-Identify TOH, Management and Regulatory reports and metrics
-Analyze reports to understand all key data and reporting dimensions for each type of risk:
• Capture the granularity needed for reporting, along with the different cuts, aggregations, and views required
-Develop a list of requirements that must be created for each risk type, leveraging:
• Report analysis
• “Standards” to meet RDA principles
• Common requirements
• Expert knowledge
  -Group these risk-type level requirements by the RDA principle they directly affect
-Identify unique characteristics about risk types that will affect their ability to comply with the principles, including:
• Upcoming regulatory requirements (ELS, Volcker Rule etc.)
• Current regulatory disclosures (Basel III, CCAR, etc.)
• Qualitative features of reports (e.g. Ops Risk Executive Loss Events)
• Off-balance sheet exposures
-Group these specific differences by the RDA principle they directly affect
-Detailed understanding of the specific reporting requirements for each risk type
-List of key data and reporting dimensions each risk type requires for reporting
-Detailed list of requirements each risk group must fulfill
-Matching of requirements to the principles they affect
-List of specific differences individual risk types will have to take into account with respect to RDA
-Matching of differences to the principles they affect
Next Steps after inventory of metrics and reports completion

## Slide 10
Risk Type Specific Requirements: TOH and Management |  | 
1. | Reports | Determine key risk reports, purpose, audience (senior management, regulatory and management), frequency and due dates.
2. | Metrics | Identify metrics and document metrics definition and methodology.
3. | Granularity / Dimensions | Specification of the level of details necessary for data feeding, upload, and analysis. The lowest level is determined by the users in order to ensure capability for a “drill-down” into the metrics. Credit Risk: Deals / Metrics Operational Risk: Loss amount / Loss events AML / Conduct Risk: AML Cases / AML Metrics, Conduct cases / Conduct Metrics
4. | Data enrichment/ attributes | Determine the need to enhance information with additional dimensions, elements, etc. The dimensions (output) are defined by input contractual data. Some examples of dimensions assigned can be: Credit Risk: NPL status, WO status, etc. Operational Risk: BIS category, Business Line, etc. AML / Conduct Risk: Products, etc.
5. | Addition of fields | Required flexibility / capabilities needed to add fields when necessary: Credit Risk: Collateral, Rating/Scoring, etc. Operational Risk: Recoveries, etc. AML / Conduct Risk:
3.3 SHUSA Risk Reporting Framework
Risk Type Business Requirements (1/3)
3.1

## Slide 11
Risk Type Specific Requirements: Identification of RDA deliverables for each risk type |  | 
2. | Data architecture and IT infrastructure | Required systems and processes to guarantee the quality of the information with a robust control process to keep the information under strict control from getting spoiled or manipulated.
3. | Accuracy and integrity | Required systems and processes to ensure traceability throughout the data handling and maintenance process, all the way to its source end to end.
4. | Completeness | Determine all data to be available to ensure completeness, specifying data sources and repositories in scope. Applicability of the risk type for each operating entity in scope (IHC/US). Determine level of consolidation of information required (i.e.: level of aggregation / disaggregation, etc.)
5. | Timeliness & frequency | Define frequency, response time, and data latency of data by risk type. Determine critical versus non-critical information.
6. | Adaptability | Define capabilities to generate aggregated risk data meeting the specific ad hoc and customized risk data reporting requirements in times of crisis, supervisory queries, or other unforeseen reporting requests
7. | Reporting Accuracy | List detailed requirements for items and exhibits to be produced for individual risk reports. Determine required reconciliation processes to ensure data integrity (e.g. GL reconciliation)
8. | Comprehensiveness | Determine drill-down abilities to report on underlying risk data and information
9. | Clarity and usefulness | Determine risk reporting standards to be applicable across the organization
11. | Distribution | Specify security measures and procedures to document the distribution processes key risk reports specify in the requirements
3.3 SHUSA Risk Reporting Framework
Risk Type Business Requirements (2/3)
3.2
Adapting RDA principles to specific requirements by risk type.

## Slide 12
3.3 SHUSA Risk Reporting Framework
Risk Type Business Requirements (3/3)
Risk Type Specific Requirements: Regulatory Requirements |  | 
1. | Regulatory scope | List of all relevant regulations to be considered in order to respond to potential regulatory requests.
2. | Regulatory reporting | Determine the required regulatory reports to be produced and the information to be included in each of them to ensure accessibility to the required information when needed and meeting regulatory deadlines.
3.3
Understanding regulatory reporting needs (CCAR, ELS, Volcker etc.) – RDA principles can improve future production and quality of data used in those disclosures. Gap assessment to identify potential differences, synergies and dependencies with in-flight initiatives

## Slide 13
SHUSA ERM Framework and Governance

## Slide 14
SHUSA senior management committees – ERM Framework
Top of the House (TOH): Board and LEVEL 1 Management Committees | 
Management: Level 2 Management Committees and sub-committees |