## Slide 1: Risk Transformation: Project Plan (1/6)
JUNE 24 WIP PLAN
  Deliverables
    Examples of milestones under the deliverable
Risk Appetite Statement (RAS)
Milestones / Deliverables | Start | Finish | Owner | Resources (FTE)
SHUSA-level RAS Re-Design | 6/8/2015 | 8/28/2015 | B. Shapiro / R. Parrish | Current resource estimates do not consider resources required for T.O.M. implementation as this will not be known until implementation planning steps are complete. Total (SHUSA): 7 Current Internal: 3 Current External: 4 New Internal: 0 New External: 0
Define guidelines and approach for choosing metrics and setting limits | 6/8/2015 | 6/26/2015 |  | 
Articulate enterprise-wide core values, RAS principles and major risk categories | 6/8/2015 | 6/26/2015 |  | 
Detail material risks and constraints, determine qualatative risk appetite statement, identify key metrics and calibrate limits | 6/8/2015 | 8/14/2015 |  | 
Consolidate qualitative and quantitative statements into SHUSA-level RAS and socialize with stakeholders | 8/17/2015 | 8/28/2015 |  | 
SHUSA-level RAS Implementation, supporting processes and documentation | 7/6/2015 | 8/14/2015 | B. Shapiro / R. Parrish | 
Document SHUSA-level RAS reporting, monitoring and escalation processes | 7/6/2015 | 7/31/2015 |  | 
Document SHUSA-level RAS development and governance process | 7/20/2015 | 8/14/2015 |  | 
SHUSA-level RAS framework approval process | 8/31/2015 | 11/2/2015 | B. Shapiro / R. Parrish | 
Definition of approach for cascading SHUSA-level RAS to subsidiaries and levels below | 8/3/2015 | 8/14/2015 | B. Shapiro / R. Parrish | 
Document approach for cascading SHUSA-level RAS to subsidiaries and levels below | 8/3/2015 | 8/14/2015 |  | 
Cascade RAS for priority subsidiaries SBNA & SCUSA | 8/17/2015 | 2/24/2016 | B. Shapiro / R. Parrish | 
Detail material risks specific to SBNA and SCUSA | 8/17/2015 | 8/28/2015 |  | 
For each risk, determine a qualitative risk appetite statement | 8/31/2015 | 9/18/2015 |  | 
For quantifiable statements, identify key metrics and calibrate limits | 9/14/2015 | 11/6/2015 |  | 
Consolidate qualitative and quantitative statements into SBNA RAS and SCUSA RAS and socialize with stakeholders | 11/9/2015 | 11/20/2015 |  | 
Secure Board approval of RAS for priority subsidiaries | 11/20/2015 | 12/31/2015 |  | 
Communicate SHUSA, SBNA, and SCUSA RAS to enterprise | 12/31/2015 | 2/24/2016 |  | 
RAS for remainder of subsidiaries and select Bus (SIS NY, Puerto Rico, Miami) | 2/1/2016 | 6/30/2016 | B. Shapiro / R. Parrish | 
Embed RAS in material processes across the enterprise | 8/17/2015 | 11/27/2015 | B. Shapiro / R. Parrish | 
Plan implementation of RAS in all material processes | 11/30/2015 | 1/12/2016 | B. Shapiro / R. Parrish | 
Continue to cascade the risk appetite statement for the remainder of subsidiaries and business units and ensure alignment with overall SHUSA risk appetite statement | 1/1/2016 | 6/30/2016 | B. Shapiro / R. Parrish | 
Embed risk appetite statement in key processes at lower levels of the organization | 1/1/2016 | 6/30/2016 | B. Shapiro / R. Parrish | 
Continue to communicate risk appetite statement throughout the enterprise, including training in the new escalation and remediation process | 4/1/2016 | 9/30/2016 | B. Shapiro / R. Parrish | 
Periodically enhance risk appetite statement based on the latest results of material risk identification and improved risk measurement across the enterprise | 10/3/2016 | 6/30/2017 | B. Shapiro / R. Parrish | 

## Slide 2: Risk Transformation: Project Plan (2/6)
JUNE 24 WIP PLAN
  Deliverables
    Examples of milestones under the deliverable
Risk Governance & Organization
Milestones / Deliverables | Start | Finish | Owner | Resources (FTE)
Diagnostic of Risk Mgmt. Committee effectiveness | 7/13/2015 | 7/13/2015 | E. Smith | Current resource estimates do not consider resources required for T.O.M. implementation as this will not be known until implementation planning steps are complete. Total (SHUSA): 16 Current Internal: 6 Current External: 8 New Internal: 3 New External: 0
Conduct Training for Board | 6/22/2015 | 8/31/2015 | E. Smith | 
Determine Scheme of Coordination Between SHUSA and Parent and Define Risk Committees Composition / Mandates / Charters | 7/13/2015 | 11/2/2015 | E. Smith | 
Enhance Performance Scorecards | 11/2/2015 | 11/30/2015 | E. Smith | 
Finalize CRO reporting lines and Risk organizational structure charts and subsidiary reporting schemes submitted to CRO for approval (SHUSA) | 6/22/2015 | 7/24/2015 | E. Smith | 
Design Target Operating Model aligned with 3LoD principles - by risk type | 6/22/2015 | 6/20/2016 | E. Smith | 
Update framework, talent assessment, implementation planning: Risk type A (Most likely Credit) | 6/22/2015 | 9/14/2015 |  | 
Update framework, talent assessment, implementation planning: Risk type B (Most likely ERM + RAS + Strategic) | 6/22/2015 | 9/14/2015 |  | 
Update framework, talent assessment, implementation planning: Risk type C (Most likely Market & Liquidity) | 9/14/2015 | 12/7/2015 |  | 
Update framework, talent assessment, implementation planning: Risk type D (Most likely Compliance) | 9/14/2015 | 12/7/2015 |  | 
Update framework, talent assessment, implementation planning: Risk type E (Most likely Risk Management Information) | 12/7/2015 | 2/29/2016 |  | 
Update framework, talent assessment, implementation planning: Risk type F (Most likely Capital Risk) | 12/7/2015 | 2/29/2016 |  | 
1st Round Post Implementation Review Conducted | 12/7/2015 | 1/4/2016 |  | 
2nd Round Post Implementation Review Conducted | 2/29/2016 | 3/25/2016 |  | 
3rd Round Post Implementation Review Conducted | 5/23/2016 | 6/20/2016 |  | 
Articulate Strong and Desired Risk Culture | 2/29/2016 | 4/18/2016 | E. Smith | 
Rollout Performance Assessment and Compensation Frameworks across the Organization | 4/1/2016 | 1/2/2017 | E. Smith | 
Design risk-based compensation framework | 4/1/2016 | 6/30/2016 |  | 
Communication and stakeholder engagement | 4/1/2016 | 9/30/2016 |  | 
Updates to performance assessment templates | 7/1/2016 | 1/2/2017 |  | 
Communication and training for organizational changes related to 3 LOD | 1/1/2016 | 1/2/2017 | E. Smith | 
Design recruitment and retention mechanisms | 7/1/2016 | 4/4/2017 | E. Smith | 
Recruitment and retention mechanisms (e.g. Professional development and job rotation programs, job satisfaction assessments, and compensation structure) | 7/1/2016 | 9/30/2016 |  | 
Assess Risk Culture across the Organization | 7/1/2016 | 9/30/2016 |  | 

## Slide 3: Risk Transformation: Project Plan (3/6)
JUNE 24 WIP PLAN
  Deliverables
    Examples of milestones under the deliverable
Risk Measurement
Milestones / Deliverables | Start | Finish | Owner | Resources (FTE)
SHUSA - Business Entity Material Risk Program | 9/1/2015 | 12/10/2015 | D. Allaire | Current resource estimates do not consider resources required for T.O.M. implementation as this will not be known until implementation planning steps are complete. Does not account for SHUSA Risk Managers resource requirements, may be significant during initial summer months. Total (SHUSA): 9 Current Internal: 6 Current External: 3 New Internal: 0 New External: 0
SHUSA Aggregation Workshops | 9/9/2015 | 9/25/2015 |  | 
SHUSA Top Down Aggregation | 9/25/2015 | 10/9/2015 |  | 
Material Risk SHUSA Approval | 10/9/2015 | 11/3/2015 |  | 
Risk ID and Assessment Policy | 9/25/2015 | 12/10/2015 |  | 
SBNA - Business Entity Material Risk Program | 5/28/2015 | 9/1/2015 | D. Allaire | 
Inventory Material Risk - SBNA | 5/28/2015 | 6/30/2015 |  | 
SBNA Aggregation Workshops | 7/1/2015 | 9/1/2015 |  | 
SCUSA - Business Entity Material Risk Program | 6/29/2015 | 9/2/2015 | D. Allaire | 
Inventory Material Risk - SCUSA | 6/29/2015 | 6/30/2015 |  | 
SCUSA Aggregation Workshops | 7/1/2015 | 7/28/2015 |  | 
New York Santander Investment Securities (SIS) - Business Entity Material Risk Program | 6/29/2015 | 9/2/2015 | D. Allaire | 
Inventory Material Risk - SIS | 6/29/2015 | 6/30/2015 |  | 
NY SIS Aggregation Workshops | 7/1/2015 | 7/28/2015 |  | 
Puerto Rico - Business Entity Material Risk Program | 5/28/2015 | 9/2/2015 | D. Allaire | 
Inventory Material Risk - PR | 6/29/2015 | 6/30/2015 |  | 
PR Aggregation Workshops | 7/1/2015 | 7/28/2015 |  | 
Miami - Business Entity Material Risk Program | 5/28/2015 | 9/2/2015 | D. Allaire | 
Inventory Material Risk - Miami | 6/29/2015 | 6/30/2015 |  | 
Miami Aggregation Workshops | 7/1/2015 | 7/28/2015 |  | 
Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place | 1/18/2016 | 1/29/2016 | E. Smith | 
Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes | 2/1/2016 | 3/14/2016 | E. Smith | 
Develop remediation of Foundational Risk Process plan | 3/14/2016 | 3/28/2016 | E. Smith | 
Updated risk taxonomy | 11/2/2015 | 11/30/2015 | E. Smith | 
Updated material risk inventory template and guidance | 12/1/2015 | 12/31/2015 | E. Smith | 
Automated interface for risk inventory template | 1/1/2016 | 3/31/2016 | E. Smith | 
Training materials, policies and procedures based on updated process | 4/1/2016 | 5/31/2016 | E. Smith | 
Database for foundational inputs and data sources for risk ID | 3/15/2016 | 11/15/2016 | E. Smith | 
Development of technology requirements and BRDs for database with business entity level foundational inputs and data sources | 3/15/2016 | 4/15/2016 |  | 
Training materials, policies and procedures for risk ID database and process | 11/15/2016 | 1/13/2017 | E. Smith | 

## Slide 4: Risk Transformation: Project Plan (4/6)
JUNE 24 WIP PLAN
  Deliverables
    Examples of milestones under the deliverable
Risk Management Processes
Milestones / Deliverables | Start | Finish | Owner | Resources (FTE)
Implement Target Operating Model aligned with 3LoD principles by (six) risk types for SHUSA, SBNA, and SCUSA (Final order of implementation TBD) | 9/11/2015 | 5/24/2016 |  | Current resource estimates do not consider resources required for T.O.M. implementation as this will not be known until implementation planning steps are complete. Total (SHUSA): NA Current Internal: NA Current External: NA New Internal: NA New External: NA
Risk type A (Most likely Credit) Framework Implemented at SHUSA, SBNA, and SCUSA | 9/11/2015 | 12/9/2015 |  | 
Risk type B (Most likely ERM + RAS + Strategic) Framework Implemented at SHUSA, SBNA, and SCUSA | 9/11/2015 | 12/9/2015 |  | 
Risk Type C (Most Likely Market & Liquidity) at SHUSA, SBNA, SCUSA and Other Entities | 12/4/2015 | 3/1/2016 |  | 
Risk type D (Most likely Compliance) Framework at SHUSA, SBNA, SCUSA, and Other Entities Implemented | 12/4/2015 | 3/1/2016 |  | 
Risk type E (Most likely Risk Management Information) Framework at SHUSA, SBNA, and SCUSA Implemented | 2/26/2016 | 5/24/2016 |  | 
Risk type F (Most likely Capital Risk) Framework at SHUSA, SBNA, and SCUSA Implemented | 2/26/2016 | 5/24/2016 |  | 
Targeted, high-level review of wholesale credit | 2/29/2016 | 4/29/2016 |  | 
High-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA | 2/29/2016 | 4/29/2016 |  | 
Gap analyses and remediation plans for the management of credit, market and trading, interest rate and strategic/reputational risk | 6/27/2016 | 9/16/2016 |  | 
Gap analyses and remediation plans for each risk (credit, market and trading, interest rate and strategic/reputational) | 6/27/2016 | 9/16/2016 |  | 
Implementation of new Credit Risk Ratings to reflect statistically valid rating methodology (CRE Q1-16 /C&I Q2-16) | 10/2/2014 | 6/10/2016 | D. Spector | 
Rating Determination (Includes Model Development) | 10/2/2014 | 6/10/2016 |  | 
Liquidity Stress Test Challenge Process Framework | 6/1/2015 | 12/31/2015 | M. Aya | 
Liquidity Stress Test Challenge Process Framework Prepared | 6/1/2015 | 6/15/2015 |  | 
Committees Approvals and Review | 6/29/2015 | 12/31/2015 |  | 

## Slide 5: Risk Transformation: Project Plan (5/6)
JUNE 24 WIP PLAN
  Deliverables
    Examples of milestones under the deliverable
Risk Monitoring
Milestones / Deliverables | Start | Finish | Owner | Resources (FTE)
Quick-win enhancements for priority reports (Board and Level 1 Risk Committees) | 6/15/2015 | 8/17/2015 | P. Coutinho | Current resource estimates do not consider resources required for T.O.M. implementation as this will not be known until implementation planning steps are complete. Assumes 1 existing internal resource will be needed per Risk Type, variance 50%. Total (SHUSA): 11 Current Internal: 7 Current External: 3 New Internal: 1 New External: 0
Assessment of current reporting landscape (for Board and Level 1 Risk Committee reports only) | 6/15/2015 | 7/27/2015 |  | 
Assessment of governance around reports (for Board and Level 1 Risk Committee reports only) | 6/22/2015 | 7/27/2015 |  | 
Implementation of quick-win enhancements (for Board and Level 1 Risk Committee reports only) | 7/27/2015 | 8/17/2015 |  | 
Definition of target risk reporting landscape | 7/27/2015 | 9/7/2015 | P. Coutinho | 
Wave 1 of reporting enhancements | 8/31/2015 | 11/9/2015 | P. Coutinho | 
Development of template reports and socialization of Wave 1 | 8/31/2015 | 9/25/2015 |  | 
Roll-out of Wave 1 reports | 9/28/2015 | 11/9/2015 |  | 
Wave 2 of reporting enhancements | 10/5/2015 | 12/28/2015 | P. Coutinho | 
Development of template reports and socialization of Wave 2 (based on materiality) | 10/5/2015 | 10/30/2015 |  | 
Roll-out of Wave 2 reports | 11/2/2015 | 12/28/2015 |  | 
Wave 3 of reporting enhancements | 12/28/2015 | 4/1/2016 | P. Coutinho | 
Development template reports and socialization of Wave 3 (Remaining Entities) | 12/28/2015 | 4/1/2016 |  | 
Roll- out of Wave 3 reports | 4/1/2016 | 4/1/2016 |  | 
Gap Analysis of Current Data Against Enhanced Report Data Requirements | 10/26/2015 | 1/8/2016 | P. Coutinho | 
Data Inventory of Wave 1 of Enhanced Reports Created | 10/26/2015 | 10/30/2015 |  | 
Current Data Inventory Assessed Against Wave 1 of Enhanced Reports | 11/2/2015 | 11/13/2015 |  | 
Data Inventory of Wave 2 of Enhanced Reports Created | 12/21/2015 | 12/25/2015 |  | 
Current Data Inventory Assessed Against Wave 2 of Enhanced Reports | 12/28/2015 | 1/8/2016 |  | 
Gap Analysis of Current Data Against Enhanced Reporting | 6/30/2016 | 6/30/2016 | P. Coutinho | 
Data Inventory of Wave 3 of Enhanced Reports Created | 6/30/2016 | 6/30/2016 |  | 
Current Data Inventory Assessed Against Wave 3 of Enhanced Reports | 6/30/2016 | 6/30/2016 |  | 
Develop and launch additional waves of reporting enhancements | 4/1/2016 | 9/30/2016 | P. Coutinho | 
Refinements to monitoring documentation and automation | 4/1/2016 | 9/30/2016 | P. Coutinho | 
Develop controls for additional reporting | 4/1/2016 | 9/30/2016 | P. Coutinho | 
Assess resource needs and conduct additional refinements to monitoring requirements | 4/1/2016 | 3/31/2017 | P. Coutinho | 

## Slide 6: Risk Transformation: project plan (6/6)
Key dependencies (examples)
  Outgoing:
  CCAR
    Risk id will feed scenario generation for CCAR
  Operational Risk, Model Risk and Model Developement
    Risk RAS for individual Risk types to be aligned with the overall
    Risk reporting framework and templates is dependent on overall Risk reporting template
  Incoming:
  Data & IT
    Year 2-3: Risk ID tool for repeatable Risk IT process
Risks
  TBD