## Consolidated
Task Name | Planned Start | Planned Finish | % Complete | Contact
Risk Measurement
SHUSA - Business Entity Material Risk Program | 2015-09-01 | 2015-10-31 | 0% | David Mael
Preparation for Aggregation to Create SHUSA Material Risk Inventory | 2015-09-01 | 2015-09-15 |  | David Mael
ERM Collects Risk Inventories from Entity Risk Managers | 2015-09-01 | 2015-09-08 |  | David Mael
ERM Sorts risks and groups by Risk Type | 2015-09-01 | 2015-09-08 |  | David Mael
ERM Creates pre-Workshop, pre-read Materials and instructions for SHUSA Risk Managers | 2015-09-01 | 2015-09-08 |  | David Mael
ERM Distributes Workshop Materials to Responsible parties | 2015-09-08 | 2015-09-09 |  | David Mael
MILESTONE | 2015-09-15 | 2015-09-15 |  | David Mael
SHUSA Aggregation Workshops | 2015-09-09 | 2015-09-25 |  | David Mael
Credit Risk Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Credit Risk performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Credit pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Credit Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
Operational Risk Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Operational Risk performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Operational Risk pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Operational Risk Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
Compliance Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Compliance performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Compliance pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Compliance Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
Model Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Model Risk performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Model pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Model Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
Market Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Market Risk performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Market pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Market Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
Liquidity Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Liquidity Risk performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Liquidity pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Liquidity Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
Strategic Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Strategic Risk performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Strategic pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Strategic Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
Reputational Material Risk Aggregation | 2015-09-09 | 2015-09-25 |  | David Mael
Reputational Risk performs pre-Read and analysis | 2015-09-09 | 2015-09-15 |  | David Mael
Risk Managers Conduct Reputational pre-Workshop Enrichment and Aggregation Activites | 2015-09-09 | 2015-09-15 |  | David Mael
ERM facilitates Reputational Aggregation and Enrichment Workshop | 2015-09-15 | 2015-09-23 |  | David Mael
Present to Level II Subcommittees | 2015-09-23 | 2015-09-25 |  | David Mael
MILESTONE | 2015-09-25 | 2015-09-25 |  | David Mael
SHUSA Top Down Aggregation | 2015-09-25 | 2015-10-09 |  | David Mael
ERM consolidates risks into SHUSA Inventory | 2015-09-25 | 2015-09-28 |  | David Mael
ERM distributes inventory to SHUSA Business and Risk executives | 2015-09-28 | 2015-09-30 |  | David Mael
ERM facilitates top down risk aggregation | 2015-09-30 | 2015-10-09 |  | David Mael
ERM incorporates final risks into SHUSA Inventory | 2015-09-30 | 2015-10-09 |  | David Mael
MILESTONE | 2015-10-09 | 2015-10-09 |  | David Mael
Material Risk SHUSA Approval | 2015-10-09 | 2015-10-30 |  | David Mael
Present SHUSA Material Risks to BERC | 2015-10-09 | 2015-10-16 |  | David Mael
Present SHUSA Material Risks to ERMC | 2015-10-16 | 2015-10-30 |  | David Mael
Present SHUSA Material Risks to CCAR | 2015-10-30 | 2015-10-30 |  | David Mael
MILESTONE | 2015-10-30 | 2015-10-30 |  | David Mael
SBNA - Business Entity Material Risk Program | Thu 5/28/15 | Mon 8/31/15 | 0% | R. Alhadeff/M. Carbone
Retail Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Small Business Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Cards Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Mortgages Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Purchased Portfolios (RV/Marine) Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Individual Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Wealth Management Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Retail: Create Retail Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Commercial Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Commercial and Industrial Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Specialties Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Government Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Commercial: Create Commercial Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Global Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MRG Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Large Corporates Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Global: Create Global Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Automotive Finance Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
CEVF Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Leasing Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Dealer Floor Plan Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Automotive: Create Automotive Finance Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Commerical Real Estate Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Financial Management Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Corporate Center Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Legal Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
HR Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Tech and Operations Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Finance Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | R. Alhadeff/M. Carbone
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | R. Alhadeff/M. Carbone
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | R. Alhadeff/M. Carbone
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | R. Alhadeff/M. Carbone
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | R. Alhadeff/M. Carbone
SBNA Aggregation Workshops | Wed 7/1/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
Credit Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
Operational Risk Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
Compliance Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
Model Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
Liquidity/Market Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
Reputational/Strategic Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | R. Alhadeff/M. Carbone
Conduct SBNA Top Down Review |  |  |  | R. Alhadeff/M. Carbone
Present Results to SBNA ERMC |  |  |  | R. Alhadeff/M. Carbone
Present Results to SBNA BERC |  |  |  | R. Alhadeff/M. Carbone
SCUSA - Business Entity Material Risk Program | Thu 5/28/15 | Mon 8/31/15 | 0% | J. Smith/T. Ploetz
Automotive Finance Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | J. Smith/T. Ploetz
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | J. Smith/T. Ploetz
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | J. Smith/T. Ploetz
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | J. Smith/T. Ploetz
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Personal Lending Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | J. Smith/T. Ploetz
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | J. Smith/T. Ploetz
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | J. Smith/T. Ploetz
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | J. Smith/T. Ploetz
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Human Resources Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | J. Smith/T. Ploetz
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | J. Smith/T. Ploetz
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | J. Smith/T. Ploetz
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | J. Smith/T. Ploetz
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Finance and Accounting Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | J. Smith/T. Ploetz
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | J. Smith/T. Ploetz
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | J. Smith/T. Ploetz
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | J. Smith/T. Ploetz
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Technology and Operations Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | J. Smith/T. Ploetz
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | J. Smith/T. Ploetz
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | J. Smith/T. Ploetz
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | J. Smith/T. Ploetz
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Legal Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | J. Smith/T. Ploetz
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | J. Smith/T. Ploetz
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | J. Smith/T. Ploetz
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | J. Smith/T. Ploetz
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | J. Smith/T. Ploetz
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | J. Smith/T. Ploetz
SCUSA Aggregation Workshops | Wed 7/1/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
Credit Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
Operational Risk Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
Compliance Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
Model Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
Liquidity/Market Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
Reputational/Strategic Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | J. Smith/T. Ploetz
Conduct SCUSA Top Down Review |  |  |  | J. Smith/T. Ploetz
Present Results to SCUSA ERMC |  |  |  | J. Smith/T. Ploetz
Present Results to SCUSA BERC |  |  |  | J. Smith/T. Ploetz
New York Santander Investment Securities (SIS) - Business Entity Material Risk Program | Thu 5/28/2015 | Mon 8/31/15 | 0% | M. Murphy
GBM-Cash Equities Brokerage Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
GBM- Debt Underwriting Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
GBM Equity Underwriting Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
GBM- Fixed Income/Bond TradingMaterial Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
GBM - Futures Brokerage Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
GBM - Fixed Income and Equity Research Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
Human Resources Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
Finance Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
Technology and Operations Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
Legal Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | M. Murphy
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | M. Murphy
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | M. Murphy
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | M. Murphy
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | M. Murphy
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | M. Murphy
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | M. Murphy
NY SIS Aggregation Workshops | Wed 7/1/15 | Tue 7/28/15 |  | M. Murphy
Credit Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | M. Murphy
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | M. Murphy
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | M. Murphy
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | M. Murphy
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | M. Murphy
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | M. Murphy
Operational Risk Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | M. Murphy
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | M. Murphy
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | M. Murphy
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | M. Murphy
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | M. Murphy
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | M. Murphy
Compliance Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | M. Murphy
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | M. Murphy
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | M. Murphy
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | M. Murphy
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | M. Murphy
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | M. Murphy
Model Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | M. Murphy
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | M. Murphy
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | M. Murphy
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | M. Murphy
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | M. Murphy
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | M. Murphy
Liquidity/Market Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | M. Murphy
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | M. Murphy
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | M. Murphy
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | M. Murphy
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | M. Murphy
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | M. Murphy
Reputational/Strategic Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | M. Murphy
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | M. Murphy
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | M. Murphy
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | M. Murphy
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | M. Murphy
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | M. Murphy
Conduct NY SIS Top Down Review |  |  |  | M. Murphy
Present Results to NY SIS ERMC |  |  |  | M. Murphy
Present Results to NY SIS BERC |  |  |  | M. Murphy
Puerto Rico - Business Entity Material Risk Program | Thu 5/28/15 | Mon 8/31/15 |  | D. Fabrizio
Retail Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Personal Loans Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Small Business Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Santander Insurance Agency Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Credit Cards Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Mortgages Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Retail Banking: Create Retail Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create Segment Material Risk Inventory (Aggregation) | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Segment head presents inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Global Banking/Commercial Banking and CRE/Speciality and Gov't Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
GBM Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Enterprise Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Institutional/Public Sector Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Mon 6/29/15 |  | D. Fabrizio
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Create Segment Material Risk Inventory (Aggregation) | Thu 5/28/15 | Tue 6/30/15 |  | D. Fabrizio
Segment head presents inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Mortgage Servicing Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Investment Services Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Trust Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Pension Plan Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Foreign Accounts Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Human Resources Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Technology and Operations Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Legal Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Finance Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
SFS - Island Finance Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
SFS - Special Assets Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Santander Overseas Bank - GBM Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | D. Fabrizio
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | D. Fabrizio
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | D. Fabrizio
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | D. Fabrizio
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | D. Fabrizio
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | D. Fabrizio
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | D. Fabrizio
Puerto Rico - Santander Bancorp Aggregation Workshops | Wed 7/1/15 | Tue 7/28/15 |  | D. Fabrizio
Credit Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | D. Fabrizio
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | D. Fabrizio
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | D. Fabrizio
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | D. Fabrizio
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | D. Fabrizio
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | D. Fabrizio
Operational Risk Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | D. Fabrizio
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | D. Fabrizio
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | D. Fabrizio
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | D. Fabrizio
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | D. Fabrizio
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | D. Fabrizio
Compliance Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | D. Fabrizio
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | D. Fabrizio
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | D. Fabrizio
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | D. Fabrizio
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | D. Fabrizio
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | D. Fabrizio
Model Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | D. Fabrizio
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | D. Fabrizio
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | D. Fabrizio
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | D. Fabrizio
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | D. Fabrizio
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | D. Fabrizio
Liquidity/Market Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | D. Fabrizio
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | D. Fabrizio
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | D. Fabrizio
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | D. Fabrizio
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | D. Fabrizio
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | D. Fabrizio
Reputational/Strategic Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | D. Fabrizio
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | D. Fabrizio
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | D. Fabrizio
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | D. Fabrizio
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | D. Fabrizio
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | D. Fabrizio
Conduct PR Santander Bancorp Top Down Review |  |  |  | D. Fabrizio
Present Results to PR Santander Bancorp ERMC |  |  |  | D. Fabrizio
Present Results to PR Santander Bancorp BERC |  |  |  | D. Fabrizio
Miami - Business Entity Material Risk Program | Thu 5/28/15 | Mon 8/31/15 | 0% | L. Madariaga
Private Banking Material Risk Inventory | Thu 5/28/15 | Tue 6/30/15 |  | L. Madariaga
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | L. Madariaga
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | L. Madariaga
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | L. Madariaga
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | L. Madariaga
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | L. Madariaga
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | L. Madariaga
Personal Lending Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | L. Madariaga
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | L. Madariaga
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | L. Madariaga
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | L. Madariaga
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | L. Madariaga
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | L. Madariaga
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | L. Madariaga
Human Resources Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | L. Madariaga
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | L. Madariaga
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | L. Madariaga
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | L. Madariaga
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | L. Madariaga
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | L. Madariaga
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | L. Madariaga
Finance and Accounting Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | L. Madariaga
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | L. Madariaga
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | L. Madariaga
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | L. Madariaga
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | L. Madariaga
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | L. Madariaga
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | L. Madariaga
Technology and Operations Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | L. Madariaga
Create risk Inventory | Thu 5/28/2015 | Fri 6/19/15 |  | L. Madariaga
Present Draft to ERM | Fri 6/19/15 | Tue 6/23/15 |  | L. Madariaga
ERM provides feedback | Tue 6/23/15 | Fri 6/26/15 |  | L. Madariaga
Deliver Final to ERM | Fri 6/26/15 | Mon 6/29/15 |  | L. Madariaga
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | L. Madariaga
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | L. Madariaga
Legal Material Risk Inventory | Thu 5/28/2015 | Tue 6/30/15 |  | L. Madariaga
Create risk Inventory | Thu 5/28/2015 | Fri 6/12/15 |  | L. Madariaga
Present Draft to ERM | Fri 6/12/15 | Fri 6/19/15 |  | L. Madariaga
ERM provides feedback | Fri 6/19/15 | Tue 6/23/15 |  | L. Madariaga
Deliver Final to ERM | Mon 6/29/15 | Tue 6/30/15 |  | L. Madariaga
Present inventory to ERMC | Mon 6/29/15 | Tue 6/30/15 |  | L. Madariaga
MILESTONE | Tue 6/30/15 | Tue 6/30/15 |  | L. Madariaga
Miami Aggregation Workshops | Wed 7/1/15 | Tue 7/28/15 |  | L. Madariaga
Credit Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | L. Madariaga
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | L. Madariaga
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | L. Madariaga
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | L. Madariaga
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | L. Madariaga
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | L. Madariaga
Operational Risk Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | L. Madariaga
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | L. Madariaga
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | L. Madariaga
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | L. Madariaga
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | L. Madariaga
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | L. Madariaga
Compliance Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | L. Madariaga
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | L. Madariaga
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | L. Madariaga
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | L. Madariaga
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | L. Madariaga
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | L. Madariaga
Model Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | L. Madariaga
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | L. Madariaga
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | L. Madariaga
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | L. Madariaga
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | L. Madariaga
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | L. Madariaga
Liquidity/Market Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | L. Madariaga
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | L. Madariaga
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | L. Madariaga
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | L. Madariaga
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | L. Madariaga
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | L. Madariaga
Reputational/Strategic Material Risk Aggregation | Wed 7/1/15 | Tue 7/28/15 |  | L. Madariaga
ERM disseminates Workshop Pre-Read Materials to Risk Managers | Wed 7/1/15 | Fri 7/10/15 |  | L. Madariaga
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities | Mon 7/13/15 | Fri 7/17/15 |  | L. Madariaga
ERM facilitates Aggregation and Enrichment Workshop | Mon 7/20/15 | Fri 7/24/15 |  | L. Madariaga
Risk Manager presents inventory to level II subcommittee | Mon 7/27/15 | Tue 7/28/15 |  | L. Madariaga
MILESTONE | Tue 7/28/15 | Tue 7/28/15 |  | L. Madariaga
Conduct Miami Top Down Review |  |  |  | L. Madariaga
Present Miami to SCUSA ERMC |  |  |  | L. Madariaga
Present Miami to SCUSA BERC |  |  |  | L. Madariaga
Note on E2: Zhang, Zhiyi: Identify SHUSA Contact
Note on E348: Zhang, Zhiyi: Confirm whether contact is M. Murphy
Note on E459: Zhang, Zhiyi: Confirm whether contact is D. Fabrizio
Note on E642: Zhang, Zhiyi: Confirm whether contact is L. Madariaga

## New York
Task Name | % Complete | Planned Start | Planned Finish | Contact
New York Santander Investment Securities (SIS) - Business Entity Material Risk Program | 0% | Thu 5/28/2015 | Mon 8/31/15 | M. Murphy
GBM-Cash Equities Brokerage Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
GBM- Debt Underwriting Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
GBM Equity Underwriting Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
GBM- Fixed Income/Bond TradingMaterial Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
GBM - Futures Brokerage Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
GBM - Fixed Income and Equity Research Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Human Resources Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Finance Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Technology and Operations Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Legal Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
NY SIS Aggregation Workshops |  | Wed 7/1/15 | Tue 7/28/15
Credit Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Operational Risk Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Compliance Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Model Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Liquidity/Market Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Reputational/Strategic Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Conduct NY SIS Top Down Review
Present Results to NY SIS ERMC
Present Results to NY SIS BERC

## SHUSA
Task Name | Complete | Planned Start | Planned Finish | Contact
SHUSA - Business Entity Material Risk Program | 0% | 2015-09-01 | 2015-10-31
Preparation for Aggregation to Create SHUSA Material Risk Inventory |  | 2015-09-01 | 2015-09-15
ERM Collects Risk Inventories from Entity Risk Managers |  | 2015-09-01 | 2015-09-08
ERM Sorts risks and groups by Risk Type |  | 2015-09-01 | 2015-09-08
ERM Creates pre-Workshop, pre-read Materials and instructions for SHUSA Risk Managers |  | 2015-09-01 | 2015-09-08
ERM Distributes Workshop Materials to Responsible parties |  | 2015-09-08 | 2015-09-09
SHUSA Aggregation Workshops |  | 2015-09-09 | 2015-09-25
Credit Risk Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Credit Risk performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Credit pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Credit Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
Operational Risk Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Operational Risk performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Operational Risk pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Operational Risk Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
Compliance Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Compliance performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Compliance pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Compliance Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
Model Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Model Risk performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Model pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Model Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
Market Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Market Risk performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Market pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Market Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
Liquidity Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Liquidity Risk performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Liquidity pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Liquidity Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
Strategic Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Strategic Risk performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Strategic pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Strategic Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
Reputational Material Risk Aggregation |  | 2015-09-09 | 2015-09-25
Reputational Risk performs pre-Read and analysis |  | 2015-09-09 | 2015-09-15
Risk Managers Conduct Reputational pre-Workshop Enrichment and Aggregation Activites |  | 2015-09-09 | 2015-09-15
ERM facilitates Reputational Aggregation and Enrichment Workshop |  | 2015-09-15 | 2015-09-23
Present to Level II Subcommittees |  | 2015-09-23 | 2015-09-25
SHUSA Top Down Aggregation |  | 2015-09-25 | 2015-10-09
ERM consolidates risks into SHUSA Inventory |  | 2015-09-25 | 2015-09-28
ERM distributes inventory to SHUSA Business and Risk executives |  | 2015-09-28 | 2015-09-30
ERM facilitates top down risk aggregation |  | 2015-09-30 | 2015-10-09
ERM incorporates final risks into SHUSA Inventory |  | 2015-09-30 | 2015-10-09
Material Risk SHUSA Approval |  | 2015-10-09 | 2015-10-30
Present SHUSA Material Risks to BERC |  | 2015-10-09 | 2015-10-16
Present SHUSA Material Risks to ERMC |  | 2015-10-16 | 2015-10-30
Present SHUSA Material Risks to CCAR |  | 2015-10-30 | 2015-10-30

## SBNA
Task Name | % Complete | Planned Start | Planned Finish | Contact
SBNA - Business Entity Material Risk Program | 0% | Thu 5/28/15 | Mon 8/31/15 | R. Alhadeff/M. Carbone
Retail Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Small Business Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Cards Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Mortgages Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Purchased Portfolios (RV/Marine) Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Individual Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Wealth Management Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Retail: Create Retail Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Commercial Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Commercial and Industrial Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Specialties Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Government Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Commercial: Create Commercial Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Global Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
MRG Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Large Corporates Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Global: Create Global Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Automotive Finance Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
CEVF Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Leasing Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Dealer Floor Plan Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Automotive: Create Automotive Finance Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create Segment Material Risk Inventory (Aggregation) |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Segment head presents inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Commerical Real Estate Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Financial Management Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Corporate Center Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Legal Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
HR Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Tech and Operations Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Finance Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | R. Alhadeff/M. Carbone
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | R. Alhadeff/M. Carbone
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | R. Alhadeff/M. Carbone
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | R. Alhadeff/M. Carbone
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | R. Alhadeff/M. Carbone
SBNA Aggregation Workshops |  | Wed 7/1/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
Credit Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
Operational Risk Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
Compliance Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
Model Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
Liquidity/Market Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
Reputational/Strategic Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | R. Alhadeff/M. Carbone
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | R. Alhadeff/M. Carbone
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | R. Alhadeff/M. Carbone
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | R. Alhadeff/M. Carbone
Conduct SBNA Top Down Review |  |  |  | R. Alhadeff/M. Carbone
Present Results to SBNA ERMC |  |  |  | R. Alhadeff/M. Carbone
Present Results to SBNA BERC |  |  |  | R. Alhadeff/M. Carbone

## SCUSA
Task Name | % Complete | Planned Start | Planned Finish | Contact
SCUSA - Business Entity Material Risk Program | 0% | Thu 5/28/15 | Mon 8/31/15 | J. Smith/T. Ploetz
Automotive Finance Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15 | J. Smith/T. Ploetz
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | J. Smith/T. Ploetz
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | J. Smith/T. Ploetz
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | J. Smith/T. Ploetz
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | J. Smith/T. Ploetz
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | J. Smith/T. Ploetz
Personal Lending Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15 | J. Smith/T. Ploetz
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | J. Smith/T. Ploetz
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | J. Smith/T. Ploetz
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | J. Smith/T. Ploetz
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | J. Smith/T. Ploetz
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | J. Smith/T. Ploetz
Human Resources Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15 | J. Smith/T. Ploetz
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | J. Smith/T. Ploetz
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | J. Smith/T. Ploetz
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | J. Smith/T. Ploetz
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | J. Smith/T. Ploetz
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | J. Smith/T. Ploetz
Finance and Accounting Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15 | J. Smith/T. Ploetz
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | J. Smith/T. Ploetz
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | J. Smith/T. Ploetz
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | J. Smith/T. Ploetz
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | J. Smith/T. Ploetz
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | J. Smith/T. Ploetz
Technology and Operations Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15 | J. Smith/T. Ploetz
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | J. Smith/T. Ploetz
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | J. Smith/T. Ploetz
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | J. Smith/T. Ploetz
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | J. Smith/T. Ploetz
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | J. Smith/T. Ploetz
Legal Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15 | J. Smith/T. Ploetz
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15 | J. Smith/T. Ploetz
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15 | J. Smith/T. Ploetz
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15 | J. Smith/T. Ploetz
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15 | J. Smith/T. Ploetz
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15 | J. Smith/T. Ploetz
SCUSA Aggregation Workshops |  | Wed 7/1/15 | Tue 7/28/15 | J. Smith/T. Ploetz
Credit Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | J. Smith/T. Ploetz
Operational Risk Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | J. Smith/T. Ploetz
Compliance Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | J. Smith/T. Ploetz
Model Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | J. Smith/T. Ploetz
Liquidity/Market Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | J. Smith/T. Ploetz
Reputational/Strategic Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15 | J. Smith/T. Ploetz
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15 | J. Smith/T. Ploetz
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15 | J. Smith/T. Ploetz
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15 | J. Smith/T. Ploetz
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15 | J. Smith/T. Ploetz
Conduct SCUSA Top Down Review |  |  |  | J. Smith/T. Ploetz
Present Results to SCUSA ERMC |  |  |  | J. Smith/T. Ploetz
Present Results to SCUSA BERC |  |  |  | J. Smith/T. Ploetz

## Puerto Rico
Task Name | % Complete | Planned Start | Planned Finish | Contact
Puerto Rico - Business Entity Material Risk Program |  | Thu 5/28/15 | Mon 8/31/15 | D. Fabrizio
Retail Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Personal Loans Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Small Business Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Santander Insurance Agency Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Credit Cards Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Mortgages Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Retail Banking: Create Retail Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create Segment Material Risk Inventory (Aggregation) |  | Thu 5/28/15 | Tue 6/30/15
Segment head presents inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Global Banking/Commercial Banking and CRE/Speciality and Gov't Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
GBM Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Enterprise Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Institutional/Public Sector Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Mon 6/29/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create Segment Material Risk Inventory (Aggregation) |  | Thu 5/28/15 | Tue 6/30/15
Segment head presents inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Mortgage Servicing Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Investment Services Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Trust Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Pension Plan Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Foreign Accounts Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Human Resources Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Technology and Operations Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Legal Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Finance Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
SFS - Island Finance Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
SFS - Special Assets Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Santander Overseas Bank - GBM Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Puerto Rico - Santander Bancorp Aggregation Workshops |  | Wed 7/1/15 | Tue 7/28/15
Credit Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Operational Risk Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Compliance Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Model Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Liquidity/Market Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Reputational/Strategic Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Conduct PR Santander Bancorp Top Down Review
Present Results to PR Santander Bancorp ERMC
Present Results to PR Santander Bancorp BERC

## Miami
Task Name | % Complete | Planned Start | Planned Finish | Contact
Miami - Business Entity Material Risk Program | 0% | Thu 5/28/15 | Mon 8/31/15 | L. Madariaga
Private Banking Material Risk Inventory |  | Thu 5/28/15 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Personal Lending Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Human Resources Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Finance and Accounting Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Technology and Operations Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/19/15
Present Draft to ERM |  | Fri 6/19/15 | Tue 6/23/15
ERM provides feedback |  | Tue 6/23/15 | Fri 6/26/15
Deliver Final to ERM |  | Fri 6/26/15 | Mon 6/29/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Legal Material Risk Inventory |  | Thu 5/28/2015 | Tue 6/30/15
Create risk Inventory |  | Thu 5/28/2015 | Fri 6/12/15
Present Draft to ERM |  | Fri 6/12/15 | Fri 6/19/15
ERM provides feedback |  | Fri 6/19/15 | Tue 6/23/15
Deliver Final to ERM |  | Mon 6/29/15 | Tue 6/30/15
Present inventory to ERMC |  | Mon 6/29/15 | Tue 6/30/15
Miami Aggregation Workshops |  | Wed 7/1/15 | Tue 7/28/15
Credit Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Operational Risk Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Compliance Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Model Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Liquidity/Market Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Reputational/Strategic Material Risk Aggregation |  | Wed 7/1/15 | Tue 7/28/15
ERM disseminates Workshop Pre-Read Materials to Risk Managers |  | Wed 7/1/15 | Fri 7/10/15
Risk Manager conducts Pre-workshop Enrichment and Aggregation activities |  | Mon 7/13/15 | Fri 7/17/15
ERM facilitates Aggregation and Enrichment Workshop |  | Mon 7/20/15 | Fri 7/24/15
Risk Manager presents inventory to level II subcommittee |  | Mon 7/27/15 | Tue 7/28/15
Conduct Miami Top Down Review
Present Miami to SCUSA ERMC
Present Miami to SCUSA BERC