## Slide 1: Risk Transformation - Summary
Key deliverables
Key dependencies
Due by
Sub-workstreams in Risk Transformation
Summary of FRB feedback
Potential execution risks
Risk management framework is not sufficiently developed to provide full subsidiary oversight and support capital adequacy framework
Lack of aligned enterprise-wide and legal entity specific Risk Appetite Statements
Risk identification process does not identify nor appropriately account for all risks when assessing capital needs
Lack of process to consider early warning indicators in the stress scenarios
Risk governance and organization: organizational structure of risk management to enforce the risk appetite statement, and oversight by the SHUSA Boards
Risk appetite: establish and communicate Board approved risk appetite
Risk ID & measurement: tools and processes to quantify the enterprise’s risks
Risk management processes: measurement and management of the enterprise’s risks and application to strategic business decisions
Risk monitoring / Risk reporting: summarize enterprise’s key risks for internal and external stakeholders
Risk data & systems: IT architecture to support effective risk management (integration with IT workstream TBC)
    Limited data availability and data quality across enterprise
    Management of dependencies and related activities spanning multiple Risk workstreams (e.g. RAS, target operating model, reporting framework and templates)
    Execution risk due to effective transfer of knowledge and capabilities from external resources / consultants
    Staffing and skills requirements of the Target Operating Model will be determined during the implementation planning process; significant gaps may affect deliverables in years 2-3
    Model Development: Development of commercial ratings models
    Model Risk Management: Validation of commercial ratings models
    Finance:
      Liquidity Data Mart and tools to support analytics process by second line of defense liquidity risk management
      Implementation of the TOM across IHC entities to support LRM Framework implementation including stress testing scenarios and LST calculations (stressed inflows/outflows >90 days, non-maturity deposits)
    Data & IT:
      IT development to support Commercial Risk Rating implementation / embedding in relevant processes
      IT development for RAS, Risk ID and Risk reporting (pending planned definition of business/data requirements)
    First Line: Input to Material Risk Program (business line / segment Material Risk Inventories)
11/02/15
SHUSA Top-level RAS design and approval
01/12/16
Initial embedding of top-level RAS in material SHUSA processes and plan further embedding across the enterprise
12/10/15
Develop and execute Material Risk Program
08/14/15
Strengthen the structure of risk leadership
09/30/16
Assess Risk Culture and define enhancement objectives
11/20/15
Strengthen Board and Management committee oversight
TBD
Implement Target Operating Model for each Risk Type / Function
    Roll out new commercial risk ratings for CRE and C&I
06/10/16
09/07/15
    Define target risk reporting landscape and scope of remediation
04/01/16
    Implement enhancements in SHUSA’s Risk reporting
12/31/15
SBNA & SCUSA RAS design and approval
03/18/16
    Target Operating Model design and implementation planning
TBD
Design and roll-out foundational Risk ID processes
1/8/16
Enhanced Top-level risk policies and 3 LOD articulation

## Slide 2: Risk Transformation: Project Plan (1/5)
Risk Governance & Organization
Deliverables/milestones | Start | Finish | Owner
Strengthen Board and Management committee oversight | 7/13/2015 | 11/20/2015 | B. Gunn
Diagnostic of Risk Mgmt. Committee effectiveness | 7/13/2015 | 7/31/2015 | 
Conduct Training for Board | 7/13/2015 | 9/18/2015 | 
Review and redesign governance and coordination mechanisms between SHUSA / Group | 8/3/2015 | 8/28/2015 | 
Definition of composition / mandates / charters for BERC and Level 1 Risk Committees | 8/10/2015 | 10/9/2015 | 
Definition of composition / mandates / charters for Level 2 Risk Committees | 9/21/2015 | 11/20/2015 | 
Strengthen the structure of risk leadership (SHUSA and subsidiary CROs, Risk Control Officers) Notes : Combined into Strengthen Board and Mgmt Committee Oversight in SG version | 7/13/2015 | 8/14/2015 | B. Gunn
Enhanced Top-level risk policies (“Frameworks” for each risk type/function) with clear articulation of three lines of defense roles and responsibilities , clear distribution between SHUSA and subsidiaries | 7/13/2015 | 1/8/2016 | B. Gunn
Design and implement operating model/organizational structure aligned with 3LoD principles by risk type/function | 7/13/2015 | TBD | B. Gunn
Determine operating model / organizational structure design sequence by risk type/function | 7/13/2015 | 9/25/2015 | 
Risk Type / Function A&B (Most likely Credit, ERM + RAS + Strategic) | 7/27/2015 | 10/2/2015 | 
Formalized Risk group org. structure and corresponding talent assessment (including resource requirements / target headcount) | 7/27/2015 | 8/28/2015 | 
Implementation planning, specification of interrelationships | 8/31/2015 | 10/2/2015 | 
Risk Type / Function C&D (Most likely Market & Liquidity, Compliance) | 10/19/2015 | 12/25/2015 | 
Risk Type / Function E&F (Most likely Risk Management Information, Capital Risk) | 1/11/2016 | 3/18/2016 | 
Implementation of Target Operating Model for each Risk Type / Function 1 | 10/2/2015 | TBD | 
Post Implementation Review Conducted 1 | TBD | TBD | 
Articulation of strong and desired risk culture based on senior management input | 3/21/2016 | 5/6/2016 | B. Gunn
Rollout Performance Assessment and Compensation Frameworks across the Organization | 4/1/2016 | 1/2/2017 | B. Gunn
Communication and training for organizational changes related to 3 LOD | 1/1/2016 | 1/2/2017 | B. Gunn
Design recruitment and retention mechanisms | 7/1/2016 | 4/4/2017 | B. Gunn
Assess Risk Culture across the Organization and define multi year plan to achieve a sound risk culture | 7/1/2016 | 9/30/2016 | B. Gunn
1 – Note: Dates dependent on the implementation plans to be developed as a prior step.
  Deliverables
    Milestones under the deliverable
    Completed
Notes: Meaning difference (1)
Notes: Splited from “Rollout…Org.” (3)
Notes: Combined two items in v1 into
one item in SG (2)

## Slide 3: Risk Transformation: Project Plan (2/5)
Risk Appetite
Deliverables/milestones | Start | Finish | Owner
SHUSA Top-level Risk Appetite Statement (RAS) Design and Approval | 6/8/2015 | 11/2/2015 | E. Smith / R. Parrish
Top-level RAS Design | 6/8/2015 | 8/28/2015 | 
Top-level RAS Processes and Documentation (e.g. breach escalation and remediation process – including consequences) | 7/6/2015 | 8/14/2015 | 
Top-level RAS approval process, including Board training on approach and their role | 8/31/2015 | 11/2/2015 | 
Define cascading approach of Top-level RAS to subsidiaries and below | 8/3/2015 | 8/14/2015 | E. Smith / R. Parrish
SBNA & SCUSA RAS Design and Approval | 8/17/2015 | 12/31/2015 | E. Smith / R. Parrish
SBNA & SCUSA RAS Design – follows similar process as SHUSA | 8/17/2015 | 11/20/2015 | 
Secure Board approval of RAS | 11/20/2015 | 12/31/2015 | 
Communicate SHUSA, SBNA, and SCUSA RAS to enterprise | 12/31/2015 | 2/24/2016 | E. Smith / R. Parrish
RAS Design and Approval for remaining subsidiaries (NY, Puerto Rico, Miami) | 2/1/2016 | 6/30/2016 | 
NY RAS design and approval | 2/1/2016 | 6/30/2016 | 
Puerto Rico RAS design and approval | 2/1/2016 | 6/30/2016 | 
Miami RAS design and approval | 2/1/2016 | 6/30/2016 | 
Initial embedding of RAS in material SHUSA processes and plan for embedding RAS across the enterprise | 11/2/2015 | 1/12/2016 | E. Smith / R. Parrish
Identify key processes (e.g. strategic planning, capital planning) and update process maps with explicit RAS links | 11/2/2015 | 11/27/2015 | 
Plan implementation of RAS in all material processes | 11/30/2015 | 1/12/2016 | 
Continue to cascade the risk appetite statement for the remainder of subsidiaries and business units and ensure alignment with overall SHUSA RAS | 1/1/2016 | 6/30/2016 | E. Smith / R. Parrish
Embed RAS in key processes at lower levels of the organization | 1/1/2016 | 6/30/2016 | E. Smith / R. Parrish
Continue to communicate RAS throughout the enterprise, including training in the new escalation and remediation process | 4/1/2016 | 9/30/2016 | E. Smith / R. Parrish
Periodically RAS based on the latest results of material risk identification and improved risk measurement across the enterprise; including incorporation of risk-based capital metrics | 10/3/2016 | 6/30/2017 | E. Smith / R. Parrish
  Deliverables
    Milestones under the deliverable
    Completed

## Slide 4: Risk Transformation: Project Plan (3/5)
Risk ID & Measurement
Deliverables/milestones | Start | Finish | Owner
Material Risk Program | 2/2/2015 | 12/10/2015 | D. Allaire
Program design and approval (risk taxonomy, tools, templates, guidance) | 2/2/2015 | 5/1/2015 | 
Subsidiary / Business Entity Material Risk Program | 5/28/2015 | 9/1/2015 | 
Compile Business Line / Segment Material Risk Inventory | 5/28/2015 | 7/31/2015 | 
Subsidiary / Business Entity Aggregation Workshops (include 2 LOD challenge) and Governance (Material Risk Inventory Reviews / Approvals) | 7/1/2015 | 9/1/2015 | 
SHUSA Material Risk Program | 9/1/2015 | 12/10/2015 | 
Preparation for Aggregation to Create SHUSA Material Risk Inventory | 9/1/2015 | 9/15/2015 | 
SHUSA Aggregation Workshops (include 2 LOD challenge) | 9/9/2015 | 9/25/2015 | 
SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge) | 9/25/2015 | 10/9/2015 | 
Material Risk SHUSA Approval (final aggregation, Board and Management review and challenge) | 10/9/2015 | 11/3/2015 | 
Risk ID and Assessment Policy – drafting and approval | 9/25/2015 | 12/10/2015 | 
Establish clear linkage of MRP outputs to capital planning scenario design process | 10/5/2015 | 11/3/2015 | 
Review Foundational Risk ID Processes and Build Multi-Year Enhancement Objectives | 1/18/2016 | 3/28/2016 | E. Smith
Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place | 1/18/2016 | 1/29/2016 | 
Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes | 2/1/2016 | 3/14/2016 | 
Develop Foundational Risk Process remediation plan | 3/14/2016 | 3/28/2016 | 
Updated risk taxonomy | 11/2/2015 | 11/30/2015 | E. Smith
Updated material risk inventory template and guidance | 12/1/2015 | 12/31/2015 | E. Smith
Training materials, policies and procedures based on updated Material Risk Program process | 1/1/2016 | 3/31/2016 | E. Smith
Identification of technology needs, requirements definition and implementation planning to support risk identification | 4/1/2016 | 5/31/2016 | E. Smith
Development and implementation of planned data and technology solutions (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.) | 3/15/2016 | 11/15/2016 | E. Smith
  Deliverables
    Milestones under the deliverable
    Completed

## Slide 5: Risk Transformation: Project Plan (4/5)
Risk Management Processes
Deliverables/milestones | Start | Finish | Owner
Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements | TBC | TBC | M. Aya
Liquidity Stress Test Challenge Process Framework-design and approval | 6/1/2015 | 12/31/2015 | M. Aya / M. Lasso
Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA | 2/1/2016 | 3/31/2016 | J. Hennessy / C. Cuervo
New Commercial Risk Rating 1 | 5/4/2015 | 6/10/2016 | D. Spector
Ratings governance (drafting and approval of risk rating charter and policy) | 6/1/2015 | 7/31/2015 | 
CRE rating |  |  | 
CRE model development and validation (refer to Model Dev. / Model Risk workstreams) |  |  | 
CRE UAT / pilot testing | 12/1/2015 | 1/31/2016 | 
CRE end-user training | 12/1/2015 | 3/31/2016 | 
CRE initial model implementation / rollout | 2/2/2016 | 2/28/2016 | 
C&I rating |  |  | 
C&I model development and validation (refer to Model Dev. / Model Risk workstreams) |  |  | 
C&I UAT / pilot testing | 2/1/2016 | 4/1/2016 | 
C&I end-user training | 2/1/2016 | 5/27/2016 | 
C&I initial model implementation / rollout | 4/4/2016 | 4/29/2016 | 
Data and technology end-to-end solution requirements definition (CRE and C&I model) | 5/4/2015 | 2/12/2016 | 
IT development and implementation (Data Technology to implement end-to-end solution for CRE and C&I models) | 6/1/2015 | 6/10/2016 | 
Conduct gap analyses and launch remediation plans for the management of credit, market and trading, interest rate, and strategic and reputational risks | 7/1/2016 | 9/30/2016 | J. Hennessy / E. Smith
1 – Note: Deliverables / Dates for Commercial Risk Rating activities still in final stages of review and are subject to change.
  Deliverables
    Milestones under the deliverable
    Completed

## Slide 6: Risk Transformation: Project Plan (5/5)
Risk Monitoring / Risk Reporting
Deliverables/milestones | Start | Finish | Owner
Assess current reporting landscape and make quick-win enhancements to priority reports (Board and Level 1 Risk Committees) and reporting protocols | 6/15/2015 | 8/17/2015 | P. Coutinho
Define target risk reporting landscape and scope of remediation (linked to committee structure) | 7/27/2015 | 9/7/2015 | P. Coutinho
Identify risk aggregation needs and cultivate dedicated resources to manage reporting | 8/31/2015 | 1/29/2016 | P. Coutinho
Wave 1 of reporting enhancements | 8/31/2015 | 11/9/2015 | P. Coutinho
Development of template reports and socialization of Wave 1 | 8/31/2015 | 9/25/2015 | 
Roll-out of Wave 1 reports | 9/28/2015 | 11/9/2015 | 
Review business and data requirements for both interim and target state of Wave 1 reports and make additions as necessary | 9/28/2015 | 10/23/2015 | 
Identify and document data gaps and develop remediation plans | 9/28/2015 | 11/9/2015 | 
Pilot reports using available data (manual where necessary) | 9/28/2015 | 10/9/2015 | 
Collect feedback from key stakeholders and refine reports | 10/26/2015 | 11/6/2015 | 
Implement refined reports in-production | 11/6/2015 | 11/9/2015 | 
Wave 2 of reporting enhancements | 10/5/2015 | 12/28/2015 | P. Coutinho
Development of template reports and socialization of Wave 2 (based on materiality) | 10/5/2015 | 10/30/2015 | 
Roll-out of Wave 2 reports (similar process as Wave 1) | 11/2/2015 | 12/28/2015 | 
Wave 3 of reporting enhancements | 12/28/2015 | 4/1/2016 | P. Coutinho
Development of template reports and socialization of Wave 3 (Remaining Entities) | 12/28/2015 | 1/29/2016 | 
Roll- out of Wave 3 reports (similar process as Wave 1) | 2/1/2016 | 4/1/2016 | 
Execution of Remediation Plans as defined in Roll-out of Enhanced Reports | 4/1/2016 | 1/2/2017 | P. Coutinho
Develop and launch additional waves of reporting enhancements at multiple levels of granularity | 4/1/2016 | 9/30/2016 | P. Coutinho
Refinements to monitoring documentation and data requirements/resources | 4/1/2016 | 9/30/2016 | P. Coutinho
Develop controls for additional reporting | 4/1/2016 | 9/30/2016 | P. Coutinho
Assess resource needs and conduct additional refinements to monitoring requirements | 4/1/2016 | 3/31/2017 | P. Coutinho
  Deliverables
    Milestones under the deliverable
    Completed