## Slide 1: Risk Transformation: Project Plan (1/4)
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
12/21/15
  08/03/15
  09/21/15
  10/09/15
  11/20/15
8/14/2015
TBD
  08/14/15
  09/25/15
  10/02/15
  07/24/15
  08/28/15
  10/02/15
  12/25/15
  03/18/16
  TBD
  TBD
  Ongoing
  05/06/16 09/30/16
  12/18/15
  01/02/17
  04/04/17
07/13/15
  07/13/15
  07/13/15
  08/3/15
  09/21/15
7/31/2015
07/13/15
  07/13/15
  07/13/15
  07/13/15
  07/13/15
  07/27/15
  08/31/15
  10/05/15
  12/28/15
  10/02/15
  TBD
  01/01/16
  03/21/16
  07/01/16
  06/15/15
  04/01/16
  07/01/16
  B. Gunn
  B. Gunn
  B. Gunn
  B. Gunn
  B. Gunn
  C. Briongos/J. McCoy
  B. Gunn
  B. Gunn
  E. Smith/ R. Parrish
  E. Smith / R. Parrish
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
Strengthen Governance and Oversight by SHUSA Board and Management Committees
    Assess the effectiveness of existing Board and Management committees and assess gaps
    Re-design committee structures
    Define composition, charters, and roles for redesigned committees
    Provide training to the Board on the redesigned committee structure and the role of the Board
Enhance top of the house risk policies with clear articulation of roles across the 3 LODs, oversight, decision rights
Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement
    Identify and implement near tem changes to the risk organization and reporting lines across SHUSA
    Determine the prioritization of operating model design and rollout by risk type / function
    Define org structure, roles, talent and skill sets and implementation plans for Risk Type / Function A & B (Most likely Credit, ERM + RAS + Strategic)
      Define risk management roles and responsibilities across the lines of defenses
      Define organization structure and assess talent needs
      Develop rollout plan
    Develop org structure, roles, talent / skills and implementation plan for Risk Type / Function C & D (Most likely Market & Liquidity, Compliance)
    Develop org structure, roles, talent / skills and implementation plan for Risk Type / Function E & F (Most likely Risk Management Information, Capital Risk)
    Implement the redesigned Operating Model for each Risk Type / Function1
    Conduct post Implementation reviews1
  Rollout communication and training for organizational changes related to 3 LOD
  Articulate desired risk culture based on risk culture assessment and senior management input
  Define multiyear plan to achieve a sound target state risk culture
  Assess existing Risk Management Performance Scorecards and identify gaps
  Rollout systematic performance assessments and compensation structures
  Diagnose retention challenge and design recruitment and retention mechanisms
  1 Note: Dates dependent on the implementation plans to be developed as a prior step.
Risk Appetite Statement (RAS)
  Design SHUSA-level Risk RAS and obtain approvals
    Design SHUSA-level Risk appetite statement
    Establish related processes and documentation for ongoing management of RAS (e.g. breach escalation and remediation process – including consequences)
    Articulate SHUSA-level RAS approval process, and train the Board on the approach and their role
  Define approach for cascading SHUSA-level RAS to subsidiaries and below
06/08/15
  06/08/15
  07/06/15
  08/31/15
08/03/15
11/02/15
  08/28/15
  08/14/15
  11/02/15
08/14/15
Red Arrow : Significant Difference
Notes in Black and Underlined
Notes: Combined two items in v1 into
one item here
Notes: Meaning difference
Notes: Missing in v1
Notes: Missing in v1
Notes: Missing in v1
Notes: Splited from “Rollout…Org.”
Changed/Reordered some items and dates

## Slide 2: Risk Transformation: Project Plan (2/4)
  Deliverables
    Milestones under the deliverable
    Completed
Risk Appetite Statement (RAS)
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
  12/31/15
  11/20/15
  12/31/15
  02/24/16
  06/30/16
  06/30/16
  06/30/16
  06/30/16
  01/12/16
  11/27/15
  01/12/16
  06/30/16
  06/30/16
  09/30/16
  06/30/17
  08/17/15
  08/17/15
  11/20/15
  12/31/15
  02/01/16
  02/01/16
  02/01/16
  02/01/16
  11/02/15
  11/02/15
  11/30/15
  01/01/16
  01/01/16
  04/01/16
  10/03/16
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
  E. Smith / R. Parrish
Design SBNA & SCUSA RAS and obtain approvals
    Design SBNA & SCUSA RAS, establish related processes and documentation for ongoing management of RAS
    Secure Board approval of RAS
Communicate SHUSA, SBNA, and SCUSA RAS to enterprise
Design RAS for remaining subsidiaries (NY, Puerto Rico, Miami) and obtain approvals
    NY RAS design and approval
    Puerto Rico RAS design and approval
    Miami RAS design and approval
Initiate embedding of RAS in material SHUSA processes and plan for embedding RAS across the enterprise
    Identify key processes (e.g. strategic planning, capital planning) and update process maps with explicit RAS links
    Initiate implementation of RAS in all material processes
    Continue to cascade the risk appetite statement for the remainder of subsidiaries and business units and ensure alignment with overall SHUSA risk appetite statement
    Cascade the embedding of the risk appetite statement for key processes across the organization
    Continue to communicate risk appetite statement throughout the enterprise, including training in the new escalation and remediation process
    Periodically enhance risk appetite statement based on the latest results of material risk identification and improved risk measurement across the enterprise; including incorporation of risk-based capital metrics
Risk ID & Measurement
  Design and execute the Material Risk Program across SHUSA
    Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance)
    Create risk inventory for the Subsidiaries / Business Entities and hold workshops for aggregation
    Compile Business Line / Segment Material Risk Inventory
    Hold Subsidiary / Business Entity Aggregation Workshops (include 2nd LOD challenge) and Governance (Material Risk Inventory Reviews / Approvals)
    Create risk inventory for the SHUSA, hold workshops for aggregation
    Preparation for Aggregation to create SHUSA Material Risk Inventory
    Hold SHUSA Aggregation Workshops (include 2nd LOD challenge)
    Execute on SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge)
    Obtain approvals for Material Risks of SHUSA (final aggregation, Board and Management review and challenge)
    Draft Risk ID and Assessment Policy and obtain approvals
    Establish clear linkage of MRP outputs to capital planning scenario design process
  02/02/15
  02/02/15
  05/28/15
  05/28/15
  07/01/15
  09/01/15
  09/01/15
  09/09/15
  09/25/15
  10/09/15
  09/25/15
  10/05/15
  D. Allaire
  12/10/15
  05/01/15
  09/01/15
  07/31/15
  09/01/15
  12/10/15
  09/15/15
  09/25/15
  10/09/15
  11/03/15
  12/10/15
  11/03/15

## Slide 3: Risk Transformation: Project Plan (3/4)
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
Risk ID & Measurement
  Review Foundational Risk ID Processes and Build Multi-Year Enhancement Objectives
    Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place
    Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes
    Develop Foundational Risk Process remediation plan
  01/18/16
  01/18/16
  02/01/16
  03/14/16
  E. Smith
  03/28/16
  01/29/16
  03/14/16
  03/28/16
  Updated SHUSA Risk taxonomy
  Updated material risk inventory template and guidance
  Develop training materials, policies and procedures based on updated Material Risk Program process
  Identify technology needs, requirements definition and implementation planning to support risk identification
  Develop and implement planned data and technology solutions (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.)
  11/02/15
  12/01/15
  01/01/16
  04/01/16
  03/15/16
  E. Smith
  E. Smith
  E. Smith
  E. Smith
  E. Smith
  11/30/15
  12/31/15
  03/31/16
  05/31/16
  11/15/16
Risk Management Processes
  Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements
  Design Liquidity Stress Test Challenge Process Framework and get approvals
  Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA
  Rollout Commercial Risk Ratings 1
    Establish governance and oversight on commercial risk ratings governance
    Rollout redesigned CRE rating models
      CRE model development and validation (refer to Model Dev. / Model Risk workstreams)
      CRE UAT / pilot testing
      CRE end-user training
      CRE initial model implementation / rollout
    Rollout redesigned C&I rating models
      C&I model development and validation (refer to Model Dev. / Model Risk workstreams)
      C&I UAT / pilot testing
      C&I end-user training
      C&I initial model implementation / rollout
    Create requirement definitions for technology solution or CRE and C&I model implementation
    Develop and implement technology solution for CRE and C&I models)
  TBC
  12/31/15
  03/31/16
  06/10/16
  07/31/15
  TBC
  01/31/16
  03/31/16
  02/28/16
  TBC
  01/31/16
  03/31/16
  02/28/16
  01/12/16
  06/10/16
  TBC
  06/01/15
  02/01/16
  05/04/14
  06/01/15
  TBC
  12/01/15
  12/01/15
  02/02/16
  TBC
  12/01/15
  12/01/15
  02/02/16
  05/04/15
  06/01/15
  M. Aya
  M. Aya / M. Lasso
  J. Hennessy / C. Cuervo
  D. Spector
  1 Note: Deliverables / Dates for Commercial Risk Rating activities still in final stages of review and are subject to change.
  Deliverables
    Milestones under the deliverable
    Completed
Moved start and finish date forward for two months

## Slide 4: Risk Transformation: Project Plan (4/4)
Risk Management Processes
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
  Conduct gap analyses across risk types (credit, market, interest rate, and strategic and reputational risks) focusing on methodology, tools, processes and benchmark with
  Create remediation plans to address gaps and initiate remediation actions
  09/30/16
  07/01/16
Risk Monitoring / Risk Reporting
  Assess current reporting landscape and make quick-win enhancements to priority reports (Board and Level 1 Risk Committees) and reporting protocols
  Define target risk reporting landscape and scope of remediation (linked to committee structure)
  Identify risk aggregation needs and cultivate dedicated resources to manage reporting
  Develop and implement Wave 1 of reporting enhancements
    Develop template reports for Wave 1 and socialize
    Roll-out of Wave 1 reports (similar process for all waves)
      Review business and data requirements for both interim and target state of Wave 1 reports and make additions as necessary
      Identify and document data gaps and develop remediation plans
      Pilot reports using available data (manual where necessary)
      Collect feedback from key stakeholders and refine reports
      Implement refined reports in-production
  Develop and implement Wave 2 of reporting enhancements
    Development of template reports and socialization of Wave 2 (based on materiality)
    Roll-out of Wave 2 reports (similar process as Wave 1)
  Develop and implement Wave 3 of reporting enhancements
    Development of template reports and socialization of Wave 3 (Remaining Entities)
    Roll- out of Wave 3 reports (similar process as Wave 1)
  Execute on Remediation Plans and Roll-out Enhanced Reports
  Develop and launch additional waves of reporting enhancements as needed
  Refine data requirements/resources to enhance quality of reports
  Develop quality assurance plans and controls for newly enhanced reports
  Assess resource needs and implement additional refinements to monitoring requirements
  08/17/15
  09/07/15
  01/29/16
  11/09/15
  09/25/15
  11/09/15
  10/23/15
  11/09/15
  10/09/15
  11/06/15
  11/09/15
  12/28/15
  10/30/15
  12/28/15
  04/01/16
  01/29/16
  04/01/16
  01/02/17
  09/30/16
  09/30/16
  09/30/16
  03/31/17
  06/15/15
  07/27/15
  08/31/15
  08/31/15
  08/31/15
  09/28/15
  09/28/15
  09/28/15
  09/28/15
  10/26/15
  11/06/15
  10/05/15
  10/05/15
  11/02/15
  12/28/15
  12/28/15
  02/01/16
  04/01/16
  04/01/16
  04/01/16
  04/01/16
  04/01/16
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  P. Coutinho
  Deliverables
    Milestones under the deliverable
    Completed
  J. Hennessy / E. Smith
Notes: Missing in v1
Need to fill in Start/Finish dates